| 2017/2018 IDP Review | Mpofana Local Municipality |
| --- | --- |

10 Claughton Terrace

Mooi-River

3300

Tel: (033) 263 1221

Fax: (033) 263 1127

Website: www.mpofana.gov.za

“Ikusasa lisezandleni Zethu, Masakhe”

Foreword By The Honourable Mayor: Cllr X Duma	5

Introduction By The Municipal Manager: Mr Max Moyo	6

Section A: Executive Summary	8

A1. Overview	8

A2. IDP Development Process	9

A 2.1 Overview	9

A2.2. Adoption Of Process Plan And Consultation Dates	9

A3. Development Challenges Facing Mpofana	11

A3.1. Overview	11

A3.2. Municipal Transformation & INSTITUTIONAL DEVELOPMENT	11

A3.3. Basic Service Delivery	11

A3.4. Local Economic & Social Development	11

A3.5. Municipal Financial Viability & Management	12

A3.6. Good Governance & Public Participation	12

A3.7. Cross Cutting	12

A4. Mpofana Lm Long Term Vision	13

A5. Mpofana Lm Long Term Development Goals	13

A 5.1. Development Goals	13

A5.2. Opportunities And Strategies To Address The Challenges	14

A 5.3.  Spatial Vision And Approach	16

A6. Outputs, Outcome And Deliverables	18

A6.1. Municipal Transformation and Institutional Development	18

A6.2. Basic Service Delivery	19

A6.3. Local Economic Development	20

A6.4. Municipal Financial Viability and management	20

6.5. Good governance and public participation	21

A6.6. Cross Cutting Measures /Interventions	22

A7. Monitoring And Evaluation	23

Section B. Government Priorities	24

B1. CoGTA KZN Planning Development Principles	24

B2. Government Priorities	26

B2.1. Overview	26

B2.2. Millennium Development Goals (MDGS)	30

B 2.3.The 12 National Outcomes	32

B 2.4. The 5 National Priorities	34

B2.5. National Development Plan 2030	35

B2.6. Provincial Growth And Development Strategy	35

ALIGNMENT OF THE Provincial Growth and Development Strategy to Mpofana Local Municipality Goals	37

B2.7. Operation Clean Audit	40

B2.8. State Of The Nation Address	40

Section C: Situational Analysis	61

C1. Spatial Analysis	61

C1.1. Regional Context	61

C1.2. Administrative Entities	61

B1.3. Structuring Elements	61

B1.4. Nodes Assessment And Development Corridors	62

C1.5. Land Cover And Broad Land Uses	67

C1.6. Land Ownership	70

C1.7. Land Reform	70

C1.8. Environmental Analysis and LAND CAPABILITY	71

C1.9. Spatial & Environmental: SWOT ANALYSIS	77

C1.10. Disaster Management	79

C2. Demographic Characteristics	84

C2.1. Demographic Indicators	84

C2.2. Key Findings	85

C3. Municipal Transformation & Institutional Development Analysis	89

C3.1. Municipal Transformation	89

C3.2. Organisational Development	89

C3.7 Municipal Transformation & Organisational Development: SWOT Analysis	96

C4.1.1 Water and Sanitation	97

C4.2. Energy Sources	99

C4.2  Solid Waste Management	103

4.2.2.2 SOLID WASTE STATUS	103

Waste Disposal Site 4.2.3	104

C.4.2.4 State of Waste Disposal site	104

C.4.2.5 IWMP ADOPTION AND IMPLEMENTATION	104

4.2.7 DIVERSION OF WASTE INITIATIVE(S)	104

C4.3. Transportation Infrastructure	106

C.4.3.3 PROVISION OF NEW ROADS	106

C.4.3.4 Operational and Maintenance Plan	106

C.4.3.5 Integrated Transport Plan	106

C4.5. Access To Community Facilities	109

C.4.5.2 Status, backlogs, needs and priorities	109

C4.6. Human Settlements	113

C.4.6.1 Housing Developer for Human Settlement	113

C.4.6.2 Housing Sector Plan	113

C.4.6.5 Existing Housing Project	113

4.6.7 Mechanism for Co-ordination of Housing Developments with Service providers	113

HOUSEHOLDS WITH ACCESS TO TELECOMUNICATIONS	114

C4.8. Infrastructure Development Projects	115

C.4.9 Basic Service Delivery: SWOT Analysis	123

C5. Local Economic & Social Development Analysis	124

C5.1. Local Economic Development Analysis	124

AGRI-PARKS	137

5.2  Social Development Analysis	148

C.5.2.9.Social Development: SWOT Analysis	154

C.5.3.2 FOOD Security and Nutrition	155

C.5.3.3 HOUSEHOLDS SUPPORTED	155

C.5.3.4 GARDENS ESTABLISHED	155

C.5.3.5 National School Nutrition Programme	155

C.5.3.6.Number of hectares and projects under-utilised land	155

C.6.1 CAPITAL FUNDING AND EXPENDITURE TO ADDRESS SERVICE DELIVERY	156

C6.1. Capital funding and expenditure to address service delivery	157

C6.2. Social and Economic Redress Via Indigent Management	157

C.6.3. Revenue Raising Strategies	158

C6.4. Debt Management	159

C6.5. Financial Management	159

C.6.5.1 SCM FUNCTIONALITY OF THE SCM	159

Alignment of Procurement Plan with SDBIP	159

Challenges with the SCM Unit	159

BID COMMITTEES	160

C.6.5.2 Budget and Treasury OFFICE	163

C.6.5.3 TECHNICAL SERVICES	164

C.6.5.4 ASSETS AND INFRASTRUCTURE	164

C.6.5.5 REPAIRS AND MAINTENANCE	164

C.6.5.6 FINANCIAL RATIO’S	165

C6.6. Loans/  Borrowings and Grant Dependency	168

C6.7. Expenditure Management	168

C.6.8 AUDITOR-GENERAL’S OPINION	168

C6.9. Supply Chain Management (SCM)	169

C6.9 Financial Viability & Management: SWOT Analysis	172

C7. Good Governance & Public Participation	173

C7.1. Good Governance Analysis	173

C7.10.1 Municipal Risk Management	178

C.7.10.2 ANTI-FRAUD AND ANTI-CORRUPTION STRATEGY	178

C.7.10.3 Risk Management Committee	178

C.7.11 Council adopted Municipal Policies	178

C.7.12 Municipal By-laws	179

C.7.14 MUNICIPAL PUBLIC ACCOUNTS COMMITTEE	180

C.7.14 MPAC	182

C.7.15 PORTFOLIO COMMITTEES	182

Public Participation Analysis	182

C7.16. Good Governance & Public Participation: SWOT Analysis	182

C.7.17 DISTRICT Rural Development Plan	183

C.7.18 WARD BASED PLANS	183

C.7.19 LAND USE MANAGEMENT	183

C.8.1 KEY CHALLENGES PER KPA AND EXPLANATION	183

Municipal Transformation & INSTITUTIONAL DEVELOPMENT	183

Basic Service Delivery	183

Local Economic & Social Development	183

Municipal Financial Viability & Management	185

Good Governance & Public Participation	185

Cross Cutting	185

C.8.2 EXPLANATION OF EACH KEY CHALLENGE (SEE THE ABOVE)	185

C.8.4 PREVIOUS YEAR PERFORMANCE	185

C8. Combined Swot Analysis	186

Section D: Vision, Goals, Objectives And Strategies	188

D1. Long Term Vision	188

D2. Mission Statement	188

D.2.-D4 Goals, Objectives & Strategies	189

D.5 ALIGNMENT WITH KZN PGDS	191

D.6 GOALS, OBJECTIVES AND KPAs (ALSO SEE TABLE ON D2)	191

Section E: STRATEGIC Mapping & Implementation Plan	192

E2. Five (5) Year Implementation Plan	192

E.2 IMPLEMENTATION PLAN	195

Section F: Financial Plan	205

F1. Overview	205

F2. Municipal 3 to 5 Year Budget	207

F2.Capital & Operational Budget	207

F.3 Operational And Maintenance Costs	208

F4 Debt Collection	209

F4. Revenue Generation	211

F2.4. Asset Management	211

Budget	212

Financial Statements	212

Borrowing Costs	212

Section G.1 (Annual Operational Plan)	213

G.2 ALIGNMENT of the SDBIP with Goals and associated Objectives and the Municipal Budget	221

G.3 PERFORMANCE INDICATORS	222

SECTION H. ORGANISATIONAL AND INDIVIDUAL PERFORMANCE MANAGEMENT SYSTEM	222

H1 ORGANISATION KEY PERFORMANCE INDICATORS LINKED TO DEPARTMENTAL INDICATORS	222

H2 DEPARTMENTAL INDICATORS LINKED TO OUTPUTS IN THE PERFORMANCE AGREEMENTS	222

H.3 Alignment of OPMS (Departmental and Individual Indicators)	222

H4. BACK TO BASICS	222

SECTION I.1 ANNEXURES	223

1.3 SDF ( Attached separately) Disaster Management Plan	225

I.3 DISASTER Management Plan	231

Disaster	237

Disaster Risk Management	237

Disaster Risk Reduction	237

Mitigation	238

Response	238

Recovery	238

Relief	238

Disaster Risk	238

Disaster Risk Assessment	238

Human-Made Hazards	239

Natural Hazards	239

Vulnerability	239

Capacity	239

STAKEHOLDERS DATABASE	258

# Foreword By The HonourableMayor:Cllr X Duma

At Mpofana Municipality we compromise of five wards which are very under developed hence as a government of today it is very important that we take IDP very seriously and make sure that we prioritize key service delivery issues that are at the heart of our people to ensure that the government budget is spent on the needs of the community.

When we start the processes of integrated development planning, we go to each and every ward, have community meetings facilitated by the ward councillors in collaboration with ward committees and all relevant stakeholders that are developmentally active in those wards like NPO’s, NGO’s religious sectors, ratepayers associations but mostly the community is responsible for tabling issues that needs to be considered and captured in the IDP budget. Our capable officials working the IDP manager then consolidate a report from each ward that has to be reported to the Municipal Manger and the director of the department to prepare a report for the sectors and stakeholders briefing where all provincial and district departments that  are complementing our work in terms of service delivery will make input and comments to drive to a strategic direction then the municipality is able to prepare a draft document to council after deliberation, then council adopts the draft. It can then be publicized for further comment and input where it is consolidated into a final IDP document which is credible, inclusive and has priorities from wards 1 to 5.

The municipality will then prepare a budget for the roads and maintenance projects that will be funded by the MIG, then the district will prepare a budget for shared services, for water and sanitation and the rest of the items will be funded provincially like human settlement, small town rehabilitation, provincial roads, rural development land claims, agricultural farm development, arts and culture programme, social development programmes. Some departments like Cogta and Department of Treasury provide support in terms of capacity and institutional development for the municipality whilst the rest of the other issues are funded nationally like the development of N3 Roads, dams, forestry, minerals and energy.

It is always an important milestone for the ANC government to deliver a credible IDP to ensure that we address the imbalances of the past and deliver best services to the previously disadvantaged communities, so we urge everyone who understands the call of radical economical transformation to work with us to bring more investment into Mpofana so that we can create more sustainable jobs and rally behind a campaign that we have launched at Sierra Ranch last year which is “Operation bring back jobs to Mooi River” where the industrial site is a catalyst project for factories and industries that can restore our economy.

As a municipality we are doing our level best to ensure proper customer care, we have trained our staff in terms of “Batho Pele” principles. All Senior Management have signed the key performance indicators in terms of the SDBIP. In all our community projects we have steering committees and we have launched and trained all ward committees, we are in a programme of reviving operation Sukuma Sakhe in all the wards therefore we are urging all the communities to support the municipality by buying electricity, paying for services such as refuse removal, rates, water and sanitation to ensure that we are a sustainable government. If that is done we can fix all the potholes, build more roads and address the issue of street lights, lack of solid waste bins hence it is important to fight the crime and keep Mpofana clean. We have got over a hundred staff that understands the national democratic revolution which is to transform our society towards the national democratic society.

I want to close with a special quote by Nelson Mandela “Do not judge me by my successes, judge me by how many times I fell down and got back up again.”

Together we can do more for Mpofana. God Bless Mpofana and the rest of the country.

# Introduction By The Municipal Manager: Mr MaxMoyo

This is the time of the year when municipalities are required to prepare and to plan for the new financial year and in the process they are critical steps that the municipality must take in ensuring that the processes comply with the legislative requirements that guide the municipality in preparing its Integrated Development Plan. Most importantly these plans are derived from the inputs drawn from the ward committees through public participation engagementnamely Community Based Planning that was conducted with the Ward Committees that the municipality has vigorously embarked upon in order for the IDP to give meaning to the needs and aspirations of our communities. These engagements will still go on up until such a time that a final document will be produced.

Whilst the financial year 2016/17 IDP has improved in terms of credibility, a lot still needs to be done to address the MEC letter and all outstanding matters. The relations between the labour, administration and Council have also improved. IIt should also be noted that the negative audit opinion that the municipality obtained, which portrays stagnation in relation to the audit of the previous year, was attributed on the main, to prior year issues that had not been attended to for a long time. Over and above all this the issues of capacity and cash-flow challenges continue to adversely affect the municipality in all its efforts to turn around the situation. A financial recovery committee has thus been established.

It should further be noted that our IDP has a bias towards the service delivery implementation as well as the reversal of service delivery backlogs, maintenance of our dilapidated infrastructure and creation of jobs, amid the very limited financial resources at our disposal;we are committed to putting people first

The preparation of this IDP has been a well thought through process built on a strong foundation created through diverse efforts whose aim is to improve the lives of our communities and most importantly management will ensure that the desired objectives are achieved by creating an environment that is results oriented and purpose driven. If there are any outstanding issues in this draft IDP, Those issues would be addressed in the final IDP. Mpofana citizenry can expect an administration and a council that is geared towards service delivery.

# Section A: Executive Summary

## A1. Overview

Mpofana Municipalityis one of seven local Municipalities that makes-up uMgungundlovu District Municipality. It is located along the N3,approximately 70km west of Pietermaritzburg.  It borders ontouMngeni, uMshwathi, uMvoti, Imbabazane and uMtshezi Municipalities. The name Mpofana is derived from a river which runs through the town a unique feature.

Map 1. Location within KZN

The Mpofana Municipality has a population of 38 103 as per the 2011 Census with an unemployment rate of 23.9% in spite of the challenges with attraction of investors in Mooi River. Asa predominantly rural Municipality, Mpofana Local Municipality has a large number of its population employed in the agricultural sector. The other key Economic contributors are Tourism, Textile and Building and Construction.

Map 2. Employment Status per Ward

The map below highlights the employment status per ward. The level of unemployment is high in Mpofana, this cripples the Municipality’s ability to collect revenue. A lot of the citizenry falls under the indigency.

Source: Census 2011

The political leadership of this Municipality consists of seven (7) Councillors of which, four (4) are Ward Councillors and the remaining three (3) are Councillors elected as Proportional Representatives of their political parties. The 5 wards which make up Mpofana Municipality are 1, 2, 3,4 and 5. There has been an inclusion of the fifth ward, as per the Demarcation Board’s decision.

Map 3: Ward Boundaries

Source: Ward Boundaries Demarcation Board 2011

## A2. IDP Development Process

### A 2.1 Overview

In developing this plan, the municipality took cognizance of the process 	plan that was adopted by council in terms of the Municipal Systems Act, 32 of 2000 to embark on extensive consultative process.  The plan also establishes a firm foundation for the alignment of the IDP,budget preparation and performance management processes.

The table below outlines the milestones that have been achieved as per the adopted IDP Process Plan, Strict compliance to the adopted process plan was the order of the day in the review of the 2017/18 IDP.

### A2.2. Adoption Of Process Plan And Consultation Dates

| TASK | DATE |
| --- | --- |
| IDP/Budget & OPMS Process Plan adoption | August 2016 |
| CBP (Community Based Planning) | 15 February (Ward 4) 27 February (Ward 1,2,3 and 5) |
| IDP Strategic Planning Session | 03-04 November |
| IDP Consultative Meetings in all Mpofana’s 5 Wards. |  |
|  | Ward 1- 05 April 2017 Ward 2- 06 April 2017 Ward 3-04 April 2017 Ward 4- 07 April 2017 10 April 2017 Ward 5- 5 April 2017 10 April 2017 |
| Tabling and Approval of Draft 2017/18 IDP | 31March 2017 |
| IDP/Budget IMBIZO | 06 May 2017 |
| Approval of 2017/18 IDP | 30 June 2017. |

The IDP Engagements will be advertised in all our Notice Boards and the notices will be circulated in all the wards.

Needless to say the Process Plan has thus far been adhered to and the Ward Committeesengaged the process of compiling this draft IDP.

This IDP is informedhas been crafted bearing in mind the National and Provincial Development priorities as reflected in the National Development Plan (Vision 2030), the New Growth Path, the uMgungundlovu District Municipality’s District Growth and Development Plan (DGDP), KZN Provincial Growth Development Strategy (PGDS). Great care has also been taken to ensure that this IDP which has been prepared in-house responds to the 6 National Key Performance Areas as outlined in the new IDP Framework Guide developed by COGTA. This IDP further address MEC Comments which were raised based on the 201/17 submitted IDP.  A section addressing the findings as per the MEC’s assessment is later covered in this document, wherein issues that were raised by the MEC are highlighted and with specific action(s) to address the issues being put forth in this document.

## A3. Development Challenges Facing Mpofana

### A3.1. Overview

Over the next five year period, the municipality intends to channel its development in the most tangible and effective manner which will directly benefit all of its inhabitants. As with the previous, the current IDP entails projects that will bring about institutional transformation which shall assist in creating an enabling environment for its employees to deliver on its mandate. Municipal

### A3.2. Municipal Transformation &INSTITUTIONAL DEVELOPMENT

The municipality also faces a high rate of staff turnover, which impacts negatively on the ability of the municipality to meet its objectives and targets on time. The downtime during the departure of one employee and recruitment and filling in of the post impacts negatively on service delivery. This has been worsened by the Municipal cash flow situation, which makes it difficult to fill posts including critical ones.

### A3.3. Basic Service Delivery

It’s a reality that cannot be ignored that there has been slow progress in the delivery of essential services to our community over the last five years and as such this plan serves as a realistic strategy to realising our objectives. The implementation of projects is hindered by the lack of funding available or the planning process where funds are available especially in the area of housing. As a strategy, closer working relations with the different government sectors will be essential, moving forward and COGTA will have to play a major role in formulating closer working relations. The plan has been formulated with the national, provincial, and regional objectives in mind. It is noted with great concern that the backlogs in terms of basic services exist.

### A3.4. Local Economic & Social Development

There has been a very slow Economic Development Progress and investors shy away from Mpofana due to many inhibiting factors that the municipality currently endeavours to address. Degenerating town characterised by crumbling and dilapidated infrastructure and poorly maintained buildings have contributed to the inability to attract new investors to boost Mpofana economy and create job opportunities and jobs.

### A3.5. Municipal Financial Viability & Management

Debt collection problems, electrical distribution losses were very high due to electricity theft and unpaid services. The electricity losses have exacerbated cash-flow challenges shortage and financial distress resulting in the municipality not being able to meet its short and long term goals.

### A3.6. Good Governance & Public Participation

The following are the challenges impacting negatively on good governance:

Poor systems, processes and procedure

Poor monitoring and evaluation of municipal decisions

Poor implementation of municipal by-laws and policies

It is worth mentioning that in comparison to the previous IDP Ward Committee functionality and community participation has improved immensely. Although there is still a need to capacitate Ward Committees in terms of their roles and responsibilities, A training has been scheduled which would assist Ward Committees in executing their duties and responsibilities.

### A3.7. Cross Cutting

The following are cross-cutting challenges facing the municipality:

Poor land use management systems (LUMS)

Lack of prioritisation of environmental matters (The Municipality has not employed an Environmental management Officer)

## A4. Mpofana Lm Long Term Vision

“By the year 2030, Mpofana will be a sustainable, socially and economically developed municipality, that encourages community participation and whose residents live in a safe and healthy environment. Mpofana will, in addition have substantially increased its contribution to its districts gross domestic product whilst also having realized substantially decreased its share of poverty”

## A5. Mpofana Lm Long Term Development Goals

In terms of the vision there are certain elements that provide guidelines for decision-making. These elements form the basis for any decision made by the Municipality, stakeholders, interested and affected parties and potential investors.

### A 5.1. Development Goals

The following are Goals the Municipality is planning to achieve between 2017& 2022.

| National KPA | Goal |
| --- | --- |
| Municipal Transformation and Organisation Development | To increase organisational capacity |
| Basic Service Delivery | To increase access to Municipal Basic Services |
| Local Economic & Social Development | To boost the Local Economy |
| Municipal Financial Viability and Management | To increase own revenue and be financially sustainable |
| Good governance and Public Participation | To achieve a clean audit |
| Cross Cutting Issues | To increase environmental and community safety |

### A5.2. Opportunities And Strategies To Address The Challenges

#### A5.2.1. Municipal Transformation and Organizational Development KPA

The municipality has developed an organogram that is inclusive of a Performance Management Unit in order to ensure that the municipality is accountable in terms of the issues that it has promised. In relation to the previous IDP it should be noted that not all section 57 positions were filled. But it’s however a relief that the Municipality has filled all Section 57 positions are now filled; The Municipality is now a well oiled organisation with all Senior Positions filled. The municipal Audit committee in partnership with the council constantly monitors the performance of the organisation, maintain discipline and accountability. Furthermore, the municipality has a functional Municipal Public Accounts Committee (MPAC) as well as the Audit Committee whose function is to ensure compliance with governance matters and oversight.

#### A5.2.2. Basic Service Delivery KPA

Investment in the maintenance and expansion of essential utilities and services, such as water and sanitation, electricity, solid waste removal and disposal, roads, storm water, and transport infrastructure, is fundamental to improve services and quality of life for all citizens as well as to encourage local and foreign investors to invest in other economic infrastructure areas. As part of the next generation IDP, the municipality has recognized a need to develop an Infrastructure Plan and a Waste and Management Sector Plan which would form part of its strategic objectives. The municipality has since 2015 benefited from the Small Town Rehabilitation Programme managed by COGTA. The Municipality is due to receive an amount of R3, 000, 000 in the ensuing year. Some milestones in this project have been achieved since its a multi year project, with Street lights already installed, Market Stalls in place, Ablutions facilities already in place, Speed Calming measures are already operation including signage. The project will focus on Testing Route for the financial year.  The Small Town Rehabilitation Programme will further assist in terms of reviving confidence of the business sector to invest in Mpofana and the retention of existing businesses. Staff retention through integrated skills management is also one of the priorities of this organisation to ensure sustainable service delivery. While bringing in external talent is a very important component to business continuity, growing and retaining the internal capacity is a far more reliable approach. Integrated talent management is a strategic initiative aimed at attracting, appointing, and training, developing, retaining and placing competent people in all positions.

The integrated components of this approach include:

Departmental Staffing Strategies and Staff Planning;

Skills Assessments and Audits;

Personal Development Plans;

Competency Management;

Attraction and Retention;

Training and Development;

Leadership Development;

Mentoring and Coaching;

Career and Succession Planning;

Individual Performance Management; and

Workplace skills plan

#### A5.2.3. Local Economic Development KPA

The District has finalised its District Growth Development Strategy, Mpofana’s LED strategy is subject to review as it has to be aligned to the District one, The current Mpofana LED Strategy aims to increase economic growth by seizing the opportunities in the agriculture and agro-process sector, nature based tourism and. Special manufacturing and services opportunities, where advantage can be easily built in the identified areas. At the present moment, Mpofana services over 20 SMMEs. Special attention has been paid to the LED unit in that the key drivers of this KPA in terms of Human Resources is to be increased in this financial year, this is to be done through the employ of the LED and Tourism Manager who is to spearhead and co-ordinate all LED related matters.

#### A5.2.4. Financial Viability and Management KPA

The Property Rates Act has been effective as of July 2008 and will help to improve the municipal operations, fund capital projects and go a long way in improving the financial viability of the municipality. However the collection of rates has to be balanced with ascertaining that the community can actually afford this revenue generating avenue through the creation of jobs in order for people to pay for municipal services rendered. The Municipality’s financial status is not positive; this can be explained by the non-payment of services by our customers who are mostly indigent.

#### A5.2.5. Good Governance and Public Participation

The municipality embarked on a strategic planning session and identified critical areas of focus to improve good governance, namely

Improve municipalities with all legislative and Auditor general’s requirements

Strengthen governance, administrative and IGR structures.

Strengthen public participation and deepen community participation by reviving Ward Committees.

#### A5.2.6. Cross Cutting Issues KPA

The municipality has advertised the Spatial Development Framework and is in the process of completing the Land Use Management Scheme for the next financial year in order to address spatial and land use management issues within the municipality. The preparation and adoption of the LUMS will be essential in complying with the KZN Planning and Development Act No. 6 of 2008 whereupon a municipality must within five years from the commencement of this Act adopt a scheme or schemes for its whole area of jurisdiction.

### A 5.3.  Spatial Vision And Approach

To enable the development of a Spatial Development Framework, a set of principles needs to be adhered to during development. This will assist with conflict resolution between the importance of different land uses and indicate preferred land uses above another. The following sections deal with the principles set out by the Spatial Planning and Land Use Management Bill, as well as the principles set out by the KwaZulu-Natal Provincial Growth and Development Strategy, and based on the current situation in Mpofana combine them into a Logical Framework for strategy implementation in the development of.

The approach and execution of this study is guided by the following key principles;

Rural Specific

Considering promoting and developing the rural character of the municipality, while ensuring a co-ordination between the urban-rural continuum and the interdependencies of the rural economies and the urban and peri-urban centres.

Map 4: Agricultural Potential

Integration

Using the spatial basis of the study for:

the integration of development intention between the municipality and surrounding municipalities including the district municipality,

the physical integration of fragmented areas within the municipality towards improved economic imputes and service delivery and

Sectorial integration of various public and private contributors and departments toward co-ordinated development of individual projects.

Strategic  Direction

Providing  strategic  analysis  and direction to the effective utilisation of land within the municipality towards social, economic and environmental development while address current and historic  deficiencies  and providing  future spatial direction within the context of the unique spatial structure of the municipality.

Map 5: Economic Nodes and Corridors

Land Use Management

Ensuring that the SDF serves as an effective tool between the development intentions within municipalityand the practical and responsible management of land uses. Thus providing sufficient intended land use direction to the further development of the land  use management system and future planning schemes within the municipality.

Map 6: Land Use Designation

This document is combined report of the outcomes of the first two phases of the process including the IDP spatial issues and the status quo reports.

Thus this phase serves as a guiding input to the next phase intending to conduct a survey of the current situation within the municipality.

## A6. Outputs, Outcome And Deliverables

The municipality programmes and projects have been geared towards delivering of basic services, economic infrastructure development, reducing unemployment and poverty developing thriving communities able to sustain itself and the municipality.

The municipality in partnership with other stakeholders has been working hard to deliver on the following outcomes adopted by the Cabinet Lekgotla in January 2010. The community should expect the following outcomes and deliverables emanating from the implementation of this Integrated Development Plan.

### A6.1. Municipal Transformation and Institutional Development

| Ref No. | Objective | STRATEGY | Ref No. | Deliverable | Outcome 9 Output |
| --- | --- | --- | --- | --- | --- |
| A1 | To improve functionality of Municipal Performance Management System | Implementation of Municipal PMS Policy & Framework | A1.1 | Adopted and Approved PMS Policy and Framework | Differentiated approach to Municipal financing planning and support |
|  |  |  | A1.2 | Quarterly OPMS Reports |  |
| A2 | Reengineer Organisation to enhance strategic needs. | Conduct and Implement Organisational design | A2.1 | Approved Organogram |  |
|  |  |  | A2.2 | Section 56 and other critical posts |  |
|  |  |  | A2.3 | Approved Employment Equity Plan |  |
|  |  | Implementation of adopted WSP | A2.4 | Skills Audit report |  |
|  |  |  | A2.5 | Approved WSP |  |
| A3 | To improve administrative systems and processes | Development / Reviewal and implementation organisational policies | A3.1 | Approved policies |  |
|  |  |  | A3.2 | Policy Implementation |  |
|  |  | Develop required administrative system and structures. | A3.3 | Required systems in place |  |

### A6.2. Basic Service Delivery

| Ref No. | Objective | STRATEGY | Ref No. | Deliverable | Outcome 9 Output |
| --- | --- | --- | --- | --- | --- |
| B1 | To improve access to basic services | Improve access to electricity | B1.1 | Increased number of Consumer units with access to electricity | Improved access to basic services |
|  |  |  | B1.2 | IncreasedNumber of new consumer units with access to electricity |  |
| B2 |  | Improve access to refuse removal | B2.1 | Number of Existing consumer units with access to refuse removal |  |
|  |  |  | B2.2 | Number of new consumer units with access to refuse removal |  |
| B3 |  | Improve access to Roads | B3.1 | Improved state of Municipal road infrastructure |  |
|  |  |  | B3.2. | Improved state of rural roads |  |
|  |  |  | B3.3 | Increased number of Municipal access roads |  |
| B4 |  | Improve access to adequate shelter | B4.1 | Comprehensive Housing Sector Plan in Place |  |
|  |  |  | B4.2 | New Housing Developments |  |
| B5 |  | Provision of free basic water sanitation and refuse removal | B5.1 | Increased number of existing household with free basic Services |  |
|  |  |  | B5.2 | Increased number of New household with free basic Services |  |
| B6 |  | Develop and Implement Infrastructure Maintenance plan | B6.1 | Comprehensive Infrastructure Maintenance Plan |  |

### A6.3. Local Economic Development

| Ref No. | Objective | STRATEGY | Ref No. | Deliverable | Outcome 9 Output |
| --- | --- | --- | --- | --- | --- |
| C1. | To strengthen the economic environment. | Develop and Implement strategies to Improve LED. | C1.1 | Conducive business climate | Community work Programmes implemented and cooperatives supported |
|  |  |  | C1.2 | Increased revenue Generated from Tourism Establishments |  |
| C2. |  | Establishment of partnerships with other stakeholders | C2.1 | Functional LED Forum |  |
| C3. |  | To promote sustainability of SMMEs and Co-operatives entrepreneurship | C3.1 | Increased support and capacitation of SMME’s and Co-operatives |  |
| C4 |  | Creation of Employment opportunities | C4.1 | Increased number of Jobs created through LED and EPWP and programmes |  |
|  |  |  | C4.2 | Increased number of Youth women and disabled employed in LED and EPWP programmes |  |

### A6.4. Municipal Financial Viability and management

| Ref No. | Objective | STRATEGY | Ref No. | Deliverable | Outcome 9 Output |
| --- | --- | --- | --- | --- | --- |
| D1 | Increase funding and revenue generation | Financial viability debt recovery ratio | D1.1 |  |  |
|  |  | % of Municipal operations funded | D1.2 |  |  |
| D2 | Improve expenditure and maximise the economies of scale. | Financial viability cost recovery ratio | D2.1 |  |  |
|  |  | SCM performance rating | D2.2 |  |  |
| D3 | Optimise budgeting and accountability of finances | % compliance with MFMA calendar | D3.1 |  |  |

### 6.5. Good governance and public participation

| Ref No. | Objective | STRATEGY | Ref No. | Deliverable | Outcome 9 Output |
| --- | --- | --- | --- | --- | --- |
| E1 | To Improve compliance and audit opinion | Establish and maintain effective audit structures. Resolve AG Audit queries | E1.1 | Approved Audit Committee report | Deepened democracy through refined ward committee system |
|  |  |  | E1.2 | Approved Internal Audit report |  |
|  |  |  | E1.3 |  |  |
| E2 | To Improve Municipal Governance | Development / Review and implementation of organisational By-Laws | E2.1 | Approved By-Laws and Gazetted |  |
|  |  |  | E2.2 | Improvement in the Enforcement of Municipal By-Laws |  |
| E3 | To Improve public participation and awareness | Ensure Functional community participation structures | E3.1 | Improved ward committee Meeting Frequency |  |
|  |  |  | E3.2 | Increased number of Ward committee member attendance |  |
|  |  |  | E3.3 | Increased number of Functional ward committees |  |
| E4 | Improve municipal internal and external communication | Training and implementation of Batho Pele Principles | E4.1 | Improved understanding of the public opinion on the Municipality |  |
|  |  | Develop/Implement and review communication strategy | E4.2 | Approved Communication strategy |  |

### A6.6. Cross Cutting Measures /Interventions

| Ref No. | Objective | STRATEGY | Ref No. | Deliverable | Outcome 9 Output |
| --- | --- | --- | --- | --- | --- |
| F1 | To Strengthen Governance and IGR | Develop partnership with relevant stakeholders | F1.1 | Participation in IGR Structures | Single window of coordination |
| F2 | To prevent and mitigate the occurrence of disasters. | Establish Disaster Management Unit. | F2.1 | Functional Disaster management structure |  |
|  |  |  | F2.2 |  |  |
|  |  | Facilitation of Disaster Management Awareness campaigns | F2.3 | Disaster Management awareness campaigns |  |
|  |  | Improve response to disasters in collaboration with the District Municipality. | F2.4 | Improved response to Disasters |  |
| F3 | To promote credible, Strategic and spatial municipal planning | Develop a Credible IDP | F3.1 | Credible IDP |  |
|  |  | Improved SDF Planning | F3.2 | Adopted SDF |  |
|  |  |  | F3.3 | Identified Spatial Development Priorities |  |
| F4 | To promote and develop support programmes for Youth and vulnerable groups within the community. | Support the implementation campaigns directed to Youth and vulnerable groups. | F4.1 | Increased number of people benefiting from Special programmes |  |
|  |  |  | F4.2 | Increased number of programmes conducted |  |
|  |  | Co-ordinate the implementation of HIV & AIDS Strategy | F4.3 | Increased number of Functional Structures |  |

## A7. Monitoring And Evaluation

This IDP contains SMART Objectives, Key Performance Indicators, and Targets which will serve as a guide to measure its performance. The municipal service delivery is guided by legislation and its performance is measured through Performance Management System and Service Delivery and Budget Implementation Plan. This IDP and SDBIP refine and provide more detail to the outputs, targets, indicators and key activities for each strategic objective, and identify required inputs and clarify roles and responsibilities. It also spells out who will do what, by when and with what resources. Monitoring is therefore inevitable. The New Council has taken it upon itself to closely monitor the implementation of the SDBIP in collaboration with the Administration.

In all programmes, strict monitoring will be rigorously adhered to in order to ensure that the objectives of constant service delivery are always being met. Only by being completely open and constantly monitoring ourselves, we can ensure that we deliver on our Constitutional mandate.

# Section B. Government Priorities

## B1. CoGTA KZN Planning Development Principles

The 2017/18 IDP review, aims to address the development principles contained in different National and Provincial legislations and programmes. Amongst other things, the following are the principles that the IDP will adhered to:

| DEVELOPMENT PRINCIPLE | Source | APPLICATION OF THE PRINCIPLE AT MPOFANA |
| --- | --- | --- |
| Development / investment will only happen in locations that are sustainable | (NSDP) | The National Spatial Development plan by directing investment in areas closer to developed infrastructure and along development nodes and corridors with high economic activities, seeks to create decent work, reduce inequality and defeating poverty by labour absorption as well as the composition and rate of growth. The National Spatial Development plan has identified certain areas within the SA economy where employment creation is possible. The key sectors identified have a 2020 goal which is aligned to the municipality’s long terms vision. With regard to the key sectors, the municipality’s plans are centred around the infrastructure, the agricultural value chain, tourism but without trying to exclude the other sectors. The above mentioned key sectors are vital in not only addressing unemployment but in the economic growth of the municipality. |
| Our IDP will discourage urban sprawl by encouraging settlement at existing and proposed nodes and settlement corridors, whilst also promoting densification. | (NSDP) | Future settlement and economic development opportunities will be channelled into activity corridors and nodes that are adjacent to or that link the main growth centres .The municipality is currently reviewing its Spatial Development framework which will highlight various land uses, environmental sensitive areas, development nodes and corridors. |
| In localities with low demonstrated economic potential, development / investment must concentrate primarily on human capital development by providing education and training, social transfers such as grants and poverty-relief programmes | (NSDP) | Coordination and facilitation of social services, education and training is the priority of the Municipality. This is done through ward based Operation Sukuma-hSakhe strategy. Volunteers have conducted profiling of the household to which form the basis for intervention from Government Departments. The programme has resulted in increased in number of people accessing social grants as a safety net for poverty relief. |
| There should be a Balance between urban and rural land development in support of each other | (DFA Principles) | The Mpofana Municipality controls any development and protects land with high agricultural potential. Hence there is a projects initiated with Department of Agriculture and Rural Development to revive farms that were purchased for land reform beneficiaries. These farms will supply vegetables to the agro-processing hub located in the industrial hub of Mooi River. |
| Provision of Basic services (water, sanitation, access and energy) to all households |  | The municipality plays a critical role in ensuring that all the households have access to basic services such as water, sanitation and electricity. The UMgungundlovu District however is responsible for the provision of water and sanitation. |
| If there is a need to low-income housing, it must be provided in close proximity to areas of opportunity (“Breaking New Ground”: from Housing to Sustainable Human Settlements) |  | Rosetta, Bruntville and Townview are located in close proximity to Mooi River where there are opportunities for jobs. Community members do not have to spend lot of money paying for transport. The had earned cash is invested in other areas to improve the standard of living. Communities have access to educational, health and recreational facilities. The principle of self-sufficiency is promoted. Development must be located in a way that reduces the need to travel, especially by car and enables people as far as possible to meet their need locally. |
| Furthermore, the principle is underpinned by an assessment of each areas unique competencies towards its own self-reliance and need to consider the environment, human skills, infrastructure and capital available to a specific area and how it could contribute to increase its self-sufficiency | (KZN PGDS) | In partnership with the DOE, t. The municipality has invested in skills development of young people. Currently there are ten young people attending skills development programme run by UMgungundlovu FET in partnership with the Department of Economic Development and Tourism. Services SETA also has a programme wherein young people are given an opportunity to take part in a learnership which is facilitated by Services SETA. There are plans in place to address unemployment and inroads have been made to create an enabling environment for business to invest in the town. The Industrial Hub and establishment of Kentucky Fried Chicken in town of Mooi River will go a long way in attracting further investments in the town. |

The constitution of the Republic of South Africa stipulates the role that the local government should play in deepening democracy and promoting of socio-economic and environmental development. Furthermore the municipality provides basic services and conduct its business in accordance with the Municipal Structures Act 1998, Municipal System Act 2000, Municipal Finance Management Act 2003 and Municipal Property Rates Act 2004.  Section 34, Chapter 5 of the Local Government Systems Act, 32 of 2000 makes provision for the Integrated Development Plan review process.  Hence Mpofana municipality has engaged in a consultative process to comply with legislative mandate regulating the review process.

## B2. Government Priorities

### B2.1. Overview

In order for municipality to ensure that there is a better vertical alignment of the municipality’s plans and other government plans, the 2017/18IDP review will also have to address  Government priorities. The Honorable President,Mr Jacob Zuma delivered his State of the Nation Address in February 2017in which he emphasised critical development priorities to be addressed this financial year. As Mpofana municipality, we are going to ensure that we enhance partnerships with other stakeholders and coordinate our resource efficiently to achieve these goals in our 2017/18 IDP. In his state of the nation address amongst other things the following are the government priorities that the municipality has to address with its2017/18 IDP:

The municipality will continue to pay more attention on Infrastructure development, creation of sustainable human settlement, provision of water, sanitation and electricity as one of the priorities that were highlighted in the last State of the Nation Address. The Municipality has since the last generation of IDPs introduced a Project which seeks to deal with the Electrification of houses in the Rural areas, this will further see the electrification of the Mangaung area which falls under Ward 5, a predominantly urban area. This is as a result of a funding which has been provided by the Department of Energy. Currently some areas have been electrified, however more still needs to be done, that is why the electrification of other households is currently going on this will see the completion of electrification of the Mangaung area.

Also the following are the Development Goals.

Millennium Development Goals;

The 12 National Outcomes;

The 5 National Priorities

The State of the Nation Address

The KZD GDS

State of the Province Address

The Municipal Turnaround Strategy/ Recovery Plan

| President’s Focus | Applicability in Mpofana |
| --- | --- |
| Revitalising agriculture and the agro-processing value chain. | Mpofana has established an Agri-Parks and has further established a Farmers Production Support Unit (FPSU) so as to revitalise agro-processing in Mpofana. |
| Include industrialization, mining and beneficiation, agriculture and agro-processing, energy, small, medium and micro enterprises (SMMEs), managing workplace conflict, attracting investments, growing the oceans economy and tourism | Mpofana has earmarked a land for industrialization, a session was held at Sierra-Ranch 2016 after the inception of the new council wherein open dialogues where held with potential investors. Mpofana currently services over 90 SMMEs as per its database, A project namely Small Town Rehabilitation is operational and aims at beautifying the town whilst attracting investments. An LED and Tourism Manager is to be employed during the year under review so that Mpofana takes advantage of all its tourism opportunities. |
| The fight against corruption continues | Mpofana is developing its Customer Care Unit so as to fast-track responses in terms of customer complaints and issues. The Municipality has further adopted an Anti-corruption policy which is enforcable and a Whistle-Blowing Policy which will give members of the public an opportunity to report any suspicious activities by any official or councillor. |
| Government will also address the increasing delays and backlogs in registration and issuing of title deeds to beneficiaries of housing projects funded by the capital subsidy. | The Municipality has recently embarked on a project to issue out title deeds for the Riversdale area to the rightful owners. This has been long outstanding, but in this IDP review it is a priority. |
| Effective poverty alleviation programmes | Mpofana Local Municipality benefits through the EPWP Programme which sees the employment of over 65 impoverished community members. This has since been complemented by the inception of the CWP (Community Works Programme) which targets to employ over 400 community members. |
| We mean fundamental change in the structure, systems, institutions and patterns of ownership, management and control of the economy in favour of all South Africans, especially the poor, the majority of whom are African and female, as defined by the governing party, which makes policy for the democratic government | Mpofana subscribes to the view that past economic imbalances are to be addressed and rectified. The Municipality has preferential procurement policy wherein previously marginalized groups are a priority in economic opportunities that the Municipality has. |
| State reform and boosting the role of state owned companies, information and communications technology (ICT) infrastructure or broadband roll-out, water, sanitation and transport infrastructure as well | The community has free access to the internet in the Town Library, it is hoped that free access to the internet will expand to other areas that fall under Mpofana Local Municipality. |

The set of development principles in this section is derived from the recently enacted Spatial Planning and Land Use Management Act No. 16 of 2013 commonly known as SPLUMA in the planning fraternity. Efforts have and will be been made to ensure that these principles are used as a guide in the preparation of the different facets entailed in the municipal IDP. Table 1 below demonstrates how Mpofana Local Municipality is applying or intending to apply these principles in its area of jurisdiction.

| NO. | PRINCIPLE | MUNICIPAL RESPONSE |
| --- | --- | --- |
| 1 | Spatial Justice | - Since the start of local government in 2000 the Municipality has planned and implemented projects that address issues of improved access to and use of land in previously disadvantage areas but also improving on the already developed areas. - At the start of every elected council, the Municipality develops an SDF which forms part of the IDP and gets reviewed annually. The development of the SDF covers the entire jurisdiction of Mpofana Municipality with an inclusion of persons and areas that were previously unplanned for. - The municipality is currently in advanced stages of developing a municipal wide land use scheme which also incorporate rural areas - The current LUMS of the municipality permit for different types of land use and zones which allows for flexible and appropriate management of previously disadvantage areas - Mpofana is also looking into setting up the Municipal Planning Tribunal which is to abide by the development principles and norms standards. |
| 2. | Spatial Sustainability | The development of municipal strategies and plans are developed within the economic means and capabilities of the Municipality The SDF has since been reviewed which will allow Mpofana to develop an individual restructuring plans and stimulate the effective and equitable functioning of land markets. The implementation of the long term goals has considered all the current and future costs to all affected parties. |
|  | Efficiency | Mpofana is committed to efficiency, in that development is encouraged in areas that are already serviced. This means that the planning is efficient The Municipality has recently filled the post of Building Inspector and the Town Planner which help deal with PDA applications, every effort is made that there is strict compliance with Development Applications. |
| 4 | Spatial Resilience | The Municipal LUMS is in such a way that where a land has been catergoried for other uses, this can be changed through following proper steps |
| 5 | Good Administration | The new council views good administration as an important component of the |

### B2.2. Millennium Development Goals (MDGS)

South Africa a member of the United Nations member state has agreed to achieve Millennium Development goals by the year 2015. It is only just that Mpofana ascribes to the Development goals, since implementation occurs at a local level of government, Mpofana municipality IDP will contribute towards meeting the MDGs especially since the goals are to be met by this year.

| Goal | Application of the Goal in Mpofana |
| --- | --- |
| Eradication of poverty and hunger- | Mpofana Municipality is committed to the Millennium Development Goals that is why the EPWP programme intake has increased by 15 in comparison to the previous IDP; this is just another way by which we are trying to eradicate hunger as per Millenium Development Goal by having an increased intake of the EPWP Programme |
| Achievement of universal primary education | The Department of Education has seen to it that there are a number of Primary and Secondary schools across Mpofana, although a challenge has been identified in Bruntville with overcrowded classrooms, The Department has been made aware of this and as such has responded by making it known that they plan to build another primary school in Mpofana. |
| Promotion of gender equality and empowerment of women | The Municipality ascribes to the norms of the South African Constitution of which one of them is equity. The employment equity plan is in place and is thus adopted by council, suffice to say that the gender equality and the empowerment of women is given the attention it needs in Mpofana, Our EPWP staff are mostly women. August being Women month sees the Municipality engage in extensive programmes so as to empower women. |
| Reduction in child mortality | The data with the District Health Offices shows that this goal is being achieved within our District, the availability of quality health care system within Mpofana Municipality makes one hopeful that indeed child mortality is at a decrease, The incidents of child mortality are not so rampant at Mpofana |
| Improvement of maternal health | Achieving this goal within the Municipality is underpinned by the Department of Health extensive policy initiatives aimed at reducing maternal mortality and improving the quality of health throughout the health care system. The Department is visible within the Municipality to ensure that there is improvement in the maternal health. |
| Combating HIV/AIDS, malaria and other diseases | The Municipality has an established Local AIDS Council which is chaired by the Mayor, which is tasked with combating the spread of HIV/AIDS this council meets monthly and comprises of CCGS, CDWs and Health Officials. Furthermore WAC (Ward Aids Councillors) are in effect in all the Wards. An HIV/AIDS strategy is also in place. |
| Ensuring environmental sustainability | Mpofana has an adopted SDF, which highlights environmentally sensitive areas and is in line with the IDP. Environmental Impact Assessments are carried out prior to the commencement of some projects, where projects directly interfere with the environment, the project scope is altered. |
| Developing a global partnership for development | The new council has most welcome fostering relations with international stakeholders for the development and betterment of Mpofana citizenry. Efforts are made to try and attract global investors into Mpofana, the Mayor has been at the forefront of these efforts while the Municipal Manager supports the mayor in this regard. |

### B 2.3.The 12 National Outcomes

In January 2010, Cabinet adopted 12 outcomes within which to frame public-service delivery priorities and targets. Cabinet ministers have signed performance agreements linked to these outcomes. More detailed delivery agreements have since been developed to extend targets and responsibilities to national and provincial departments, agencies and municipalities. Mpofana Municipality is attempting to comply with the 12 outcomes by taking them into consideration in the budget and IDP process.

| OTCOME NUMBER | OUTCOME | OUTPUT |
| --- | --- | --- |
| 1 | Improve the quality of basic education | Improve quality of teaching and learning Regular assessment to track progress Improve early childhood development A credible outcomes-focused accountability system Improve quality of teaching and learning |
| 2 | Improve health and life expectancy | Increase life expectancy to 58 for males and 60 for females Reduce maternal and child mortality rates to 30-40 per 1000 births Combat HIV/Aids and TB Strengthen health services effectiveness |
| 3 | All people in South Africa protected and feel safe | Reduce overall level of crime An effective and integrated criminal justice system Improve perceptions of crime among the population Improve investor perceptions and trust Effective and integrated border management Integrity of identity of citizens and residents secured Cyber-crime combated |
| 4 | Decent employment through inclusive economic growth | Faster and sustainable inclusive growth More labour-absorbing growth Strategy to reduce youth unemployment Increase competitiveness to raise net exports and grow trade Improve support to small business and cooperatives Implement expanded public works programme |
| 5 | A skilled and capable workforce to support inclusive growth | A credible planning institutional mechanism Increase access to intermediate and high level learning programmes Increase access to occupation specific programmes (especially artisan skills training) Research, development and innovation in human capital |
| 6 | An efficient, competitive and responsive economic infrastructure network | Improve competition and regulation Reliable generation, distribution and transmission of energy Maintain and expand road and rail network, and efficiency, capacity and competitiveness of sea ports Maintain bulk water infrastructure and ensure water supply Information and communication Technology Benchmarks for each sector |
| 7 | Vibrant, equitable and sustainable rural communities and food security | Sustainable agrarian reform and improved access to markets for small farmers Improve access to affordable And diverse food Improve rural services and access to information to support livelihoods Improve rural employment opportunities Enable institutional environment for sustainable and inclusive growth |
| 8 | Sustainable human settlements and improved quality of household life | Accelerate housing delivery Accelerate housing delivery Improve property market More efficient land utilisation and release of state-owned land |
| 9 | A response and, accountable, effective and efficient local government system | Differentiate approach to municipal financing, planning and support Community work programme Support for human settlements Refine ward committee model to deepen democracy Improve municipal financial administrative capability Single window of coordination |
| 10 | Protection and enhancement of environmental assets and natural resources | Enhance quality and quantity of water resources Reduce greenhouse gas emissions; mitigate climate change impacts; improve air quality Sustainable environment Management Protect biodiversity |
| 11 | A better South Africa, a better and safer Africa and world | Enhance the African agenda and sustainable development Enhance regional integration Reform global governance institutions Enhance trade and investment between South Africa and partners |
| 12 | A development-orientated public service and inclusive citizenship | Improve government performance Government-wide performance monitoring and evaluation Conduct comprehensive expenditure review Information campaign on constitutional rights and responsibilities Celebrate cultural diversity |

### B 2.4. The 5 National Priorities

Government’s priorities affect all South Africans, the majority of whom are women and girls. Particularly black women and girls suffer multiple forms of discrimination and are among the most socio-economically disadvantaged groups in South Africa. This review gauges how government’s priorities set for 2012 in President Jacob Zuma’s State of the Nation Address (SONA 2012) will affect the social, political and economic status of women, and measures the  advances made with regards to the five priorities the president set in the 2009 SONA, namely:

Decent Work

Education

Crime

Health

Rural development & Agrarian reform

Mpofana Municipality through its social and economic development initiatives has played a catalytic role and continue to do so in assuring that all Capital Projects are more labour intensive in order to create an opportunity for the Local communities to acquire necessary skills and employment opportunities as well as ensuring self-sustainability and efficiency. Furthermore direct programmes and awareness campaigns in agriculture, land restitution, HIV/AIDS, Youth, Tourism, Co-operatives and SMMEs are the effective tools to create jobs opportunities and combat crime actions and transmittable deceases.

### B2.5. National Development Plan 2030

The National Development Plan aims to eliminate poverty and reduce inequality by 2030. South Africa can realise these goals by drawing on the energies of its people, growing an inclusive economy, building capabilities, enhancing the capacity of the state, and promoting leadership and partnerships throughout society.

The National Planning Commission’s Diagnostic Report, released in June 2011, set out South Africa’s achievements and shortcomings since 1994.

It identified a failure to implement policies and an absence of broad partnerships as the main reasons for slow progress, and set out nine primary challenges:

Too few people work

The quality of school education for black people is poor

Infrastructure is poorly located, inadequate and under-maintained

Spatial divides hobble inclusive development

The economy is unsustainably resource intensive

The public health system cannot meet demand or sustain quality

Public services are uneven and often of poor quality

Corruption levels are high

South Africa remains a divided society.

The National Development Plan therefore sets out the following priorities, in addressing the aforesaid challenges

Economic Infrastructure

Transitioning to low carbon economy

Inclusive rural development

Positioning South Africa in the World

Human Settlements

Improving education, innovation and training

Promoting health

Social Protection

Building safer communities

Building a capable state

Promoting accountability and fighting corruption

Transforming society and uniting the country

The plan focuses on the critical capabilities needed to transform the economy and society. Achieving these capabilities is not automatic, nor will they emerge if the country continues on its present trajectory. Rising levels of frustration and impatience suggest that time is of the essence: failure to act will threaten democratic gains. In particular, South Africa must find ways to urgently reduce alarming levels of youth unemployment and to provide young people with broader opportunities. As a Municpality we are in agreement with the challenges as outlined the National Development plan and hence we realise the role that we have in addressing theseglaring challenges at a local level. The National Development Plan has been taken into account in reviewing this IDP more especially in economic infrastructure, Building Safer communities by reviving Community Policing Forums.

.

### B2.6. Provincial Growth And Development Strategy

Mpofana Municipality’s IDP is aligned to both the National and Provincial Goals and the strategies thereof,Cabinet adopted PGDS Review Framework at the February 2011 Cabinet Lekgotla. The Draft 2030 Vision and PGDS were adopted by Cabinet on 31 August 2011.

The purpose of the PGDS is to focus on a clear vision for the Province; promote vertical, horizontal and spatial alignment; mobilise all development partners to achieve predetermined development objectives and targets; and build on the strengths and opportunities of the Province, while addressing weaknesses and threats.

The Strategic Goals for the province as indicated in the document:

Job Creation

Human Resource development

Human and Community Development

Strategic Infrastructure

Response to Climate change

Governance and policy

Spatial Equity

The implementation of Vision and Strategic Goals aspire to lead to:

Position the Province as a Gateway to  South Africa and Africa

Human & Natural Resources

Safe, Healthy & Sustainable Living Environments

Healthy Educated Communities

Employable people are employed

Basic Services

More equitable Society

World Class Infrastructure

Investors’  Confidence

Skilled Labour Force

Focus on People centeredness.

Strong & Decisive Leadership

Foster Social Compacts.  Mpofana Municipality has tried by all means necessary to increase the EPWP intake thereby create Jobs, as part of the goals of PGDS, In keeping with Human Resources Development, Mpofana will be implementing its Work Skills Plan so that the Officials are trained to full capacity including, Ward Committees, The District Municipality leads Climate Change strategies, Mpofana has since followed suite in that a dedicated official has been allocated to deal with Climate Change issues, although the expertise remain a concern, since the individual dedicated to this task is a Disaster Management Officer. With the  SDF having been recently reviewed in line with SPLUMA, Spatial Equity is being given the attention it deserves at Mpofana. Governance and Policy remains a priority of the new Council, in that all structures that have been tasked with ensuring good governance meet regularly as legislated and as when required, The MPAC plays its oversight role on behalf of council, Council meets regularly to look into Service Delivery issues.

# ALIGNMENT OF THE Provincial Growth and Development Strategy to Mpofana Local Municipality Goals

Background to the alignment process of the PGDS and Mpofana 2017/18 IDP

The shared and common platform critical to alignment is made possible through a coherent set of national spatial guidelines based on the twin concepts of development potential and need. Mpofana having attended the IDP session held in Mayville and with the PGDS alignment guidelines being provided, has attempted to align this IDP with the PGDS. The normative principles and guidelines embodied in the National Spatial Development Perspective provide the central organising concept for facilitating alignment and serve as the concrete mechanisms and basic platform for better coordination and alignment of government programmes. The National Spatial Development Perspective has also been taken into account when drafting this IDP.

The spatial perspective is at the centre of our view of alignment and coordination and is directed at facilitating discussions on the development potential of the space economy and serving as a frame of reference for guiding government actions. Mpofana’s Spatial Development Framework will seek to point out development potentials for the next 5 years and will discourage development on sensitive land. The underlying principle of the PGDS is to Position the Province as a Gateway to  South Africa and Africa, this underlying principle speaks to Mpofana’s spatical location in that Mpofana is strategically located along the N3 one of South Africa’s busiest routes and provides linkages between Durban (Habour) and Johannesburg (South Africa’s highest economic player). Mpofana is therefore a gateway between KZN and Gauteng including the Eastern Cape and the Western Cape including the Free-State which is agricultural

| PGDS | Mpofana Strategic Goal | APPLICABILITY and ALIGNMENT MPOFANA |
| --- | --- | --- |
| Job Creation | Accelerate Job Creation | Mpofana Municipality has tried by all means necessary to increase the EPWP intake thereby create Jobs, as part of the goals of PGDS, this initiative is being complemented by the CWP programme. Over 400 Jobs have been created |
| Human Resources Development | Facilitation of Skills Development | Mpofana will be implementing its Work Skills Plan so that the Officials are trained to full capacity, Mpofana has trained all its Finance Staff in the MFMP training so that they are knowledgeable in handling finances. Mpofana Youth currently benefits from ongoing Learnerships from Services Seta wherein over 125 learners are being trained at no cost on Water, Sanitation, Health, Business Administration and Hygien. This is in line with the PGDS goal of Human Resource Development |
| Spatial Equity |  | With the SDF being under review and in line with SPLUMA, Spatial Equity is being given the attention it deserves at Mpofana. Previously disadvantaged groups will be prioritized for development just so that spatial equity which is a national priority finds expression in Mpofana’s decision making and development. |
| Basic Services | Increase access to Basic Services | Mpofana has prioritized Basic Services such as Roads and Electricity, this prioritization can be attested to by the fact that the Municipality invests a lot of its MIG to rehabilitating Roads and that a lot of its operating budget goes towards the maintenance of electricity infrastructure. |
| Spatial and Environmental Management | Improve Spatial Planning | Provide positive environment for Industrial Development. Renewal and Regeneration of Mooi-River Small Town Rehabilitation |
| Governance and Policy | Promote Sound Governance and Policy | All IGR Forums are functional, most are co-ordinated at the District Level including the Mayor’s Forum, the Premier’s Forum and the different District Forum’s Mpofana’s Municipal Manager chairs the District Area Finance Forum DAFF. Mpofana also participates in the Planner’s Forum including the Techcinal Forum and MUNIMEC. Council meetings are held monthly as and when required. The Anti-fraud and Corruption policy has been workshoped and approved including the whistle blowing policy which allows the members of the public to report any suspcicious or corrupt behaviour by Municipal Officials. |
| Environmental Sustainability | Sustainable Environment | Awareness Campaigns have thus been conducted in Mpofana on how best we can sustain the environment. The Minister of Environmental Affairs is expected to conduct a visit on the 11th of April so as to host an Imbizo to this effect. As part of environmental sustainability, a recycling center has thus been established at the Landfill site so as to protect our environment; the Landfill Site has been established in partnership with the community. |
| Strategic Infrastructure | Upgrade and improvement of Infrastructure | Mpofana has recently completed a Weigh-Bridge which cost over R46 000 000 so as to bring about revenue and to promote Road Safety by weighing the Heavy vehicles that pass on the N3. |

The above table aims at showing how aligned our strategic objectives are to the Provincial Growth and Development Strategy, the table further shows the deliverables in terms of meeting the PGDS Goals at a local level with practical examples cited as can be seen above in terms of the interventions.

### B2.7. Operation Clean Audit

As part of the Government s’ Operation clean audit, the municipality has implemented the following plans:

The municipalityhas established MPAC, Internal Audit Unit, appointed Audit Committee and the Internal Audit Manager. The role of these committees and Audit Manager is to oversee and give advice on matters related to internal audits, control, risk management, adherence to accounting policies, review of financial statements, IDP review and implementation and monitoring of performance. The Audit Committee is responsible for development and implementation of strategies to address Auditor-General findings.

The development of the Risk Register has since commenced which is championed by the Internal Audit Manager who reports directly to the Municipal Manager.

Monitor implementation of internal audit and audit committee recommendations continuously.

Municipality has developed and implemented audit remedial plans, an Action plan has been developed which has been presented to the Audit Committee and to Council.

Monitor the implementation of audit remedial plans and ensure supporting documents on issues resolved. It should be noted that the Municipality received a qualified audit opinion in the 2015/16 financial year, Every effort is being made to move towards a better audit opinion for the 2016/17 audit. The Audit Action Plan is attached in this IDP.

### B2.8. State Of The Nation Address

Our IDP is aligned to the 2017State of the Nation Address as delivered by the President and there’s a commitment on the Mpofana Council to attend to the issues raised by the President In his State of the Nation Address . The President spoke of the need to embark on radical socio-economic transformation to push back the triple challenges (poverty, inequality and unemployment) which still affect many South Africans. The president made reference to how best we can win the war against poverty; creation of decent jobs is one of the things that he pointed out and that creating decent jobs requires a speedy growth of the economy.

Another point of interest that the president raised was the issue of low level of investments, this he said was a key constraint to economic growth. We are determined to work with the private sector to remove obstacles to investment in the Mpofana area as well. In addition to speeding up local investment we will continue to support local businesses, in that procurement of services will be from local producers.

The president also spoke of the need to be radical in fighting the economic challenges, It cannot be doubted that Mpofana’s approach to fighting the slow economy of Mooi-River has been radical this is evident by the fact that the Municipality has earmarked land which is to be used as an Industrial Hub so as to speed up economic activities in the Mpofana area. The Municipality’s policies will favour the previously disadvantaged groups so as to give effect to the president’s utterances of sharpening the implementation of the amended Broad-based Black Economic Empowerment. The Municipality has employed 10 interns so as to decrease the number of unemployed graduates, this is in line with the Government’s aim to expand the number of internships positions in the public sector as per the President’s State of the Nation Address.

The electrification programme which changes the lives of many as per the president’s sentiments will be one of the capital projects that Mpofana Municipality will be undertaking in the 2017/18 financial year. 5Million Rand has been set aside so as to continue with the Electrification Project.

The National Government is committed to continuing with the National Infrastructure Plan, the president pointed out that over 1trillion rand has been invested in new infrastructure, We are in line with the National Government’s commitment to infrastructure development in that all the 4 Wards will get a share of infrastructure development in the coming financial year.

The construction of Spring Grove Dam which falls under Mpofana’s jurisdiction that was launched in November in 2013 is seen as a tourist attraction sight for the tourists that come into the Midlands Meander, We are hoping for an increased number of tourists given the presence of the Spring Grove Dam. As the President rightly pointed out that as a nation we

hope to increase the number of tourists coming into our country, Spring Grove Dam through the Municipality will make this projection by the president a reality.

| Issues raised by the President during SONA 2017 | Application in Mpofana |
| --- | --- |
| 1. Resolving the energy challenge. | A project (which is not confirmed as yet) is likely to be implemented which will see Mpofana using Waste to make energy, The community is also educated on an ongoing basis about the challenge in energy that faces us and people are encouraged to use energy wisely. |
| 2. Revitalising agriculture and the agro-processing value chain. | Agriculture remains the dominant sector in Mpofana, Rural Development has been approached to help support the farmers which the government has handed to the previously disadvantaged groups as some of them lie doormat. The aim really is to revitalise the agricultural sector |
| 3. Advancing beneficiation or adding value to our mineral wealth. | Mpofana has no Minerals, and this cannot be applied in Mpofana |
| 4. More effective implementation of a higher impact Industrial Policy Action Plan. | Attraction of major investors is being pursued, currently there is one major industry in Mpofana, It is anticipated that most industries will be coming in at Mpofana given the efforts that are being put in this regard. |
| 5. Encouraging private sector investment. | The new council has most welcome fostering relations with international stakeholders for the development and betterment of Mpofana citizenry. Efforts are made to try and attract global investors into Mpofana, the Mayor has been at the forefront of these efforts while the Municipal Manager supports the mayor in this regard. |
| 6. Moderating workplace conflict. | Mpofana Local Municipality has a Local Labour Forum which meets to look into issues of the Staff at length, The labour is in turn represented by the chosen representatives. This forum has helped ease tension between the Labour, Council and Administration as all the three parties are represented and conflict is thus avoided. |
| 7. Unlocking the potential of small, medium and micro enterprises (SMMEs), cooperatives, township and rural enterprises. | The Municipality supported over 10 Co-operatives in the 2016/17 financial year, The support continues in the year that has just commenced. A budget to support the SMMEs has thus been set aside. |
| 8. Radical Economic Transformation | Mpofana subscribes to the view that past economic imbalances are to be addressed and rectified. The Municipality has preferential procurement policy wherein previously marginalized groups are a priority in economic opportunities that the Municipality has. |
| 9. Operation Phakisa aimed growing the ocean economy and other sectors. | Mpofana has no ocean and this does not be apply in Mpofana |

B2.9. BACK TO BASICS PROGRAMME

At the Presidential Local Government Summit the Back to Basics Strategy was presented where DCOGTA undertook a review of South Africa’s 278 municipalities.

The Back to Basics programme is designed to ensure that all municipalities perform their basic responsibilities and functions without compromise. The programme is built upon the 5 pillarsnamely:

- Putting people and their concerns first;

- Demonstrating good governance and administration;

- Delivering municipal services;

- Sound financial management and accounting; and

- Sound institutional and administrative capabilities.

The Back to Basics approach will institutionalize a performance management system that will recognize and reward good performance, and ensure sufficient consequences and appropriate support for under performance. The approach will integrate information on municipalities and ensure that the current challenges in the local government sphere, in the short and medium term specifically, are addressed. (Circular No: 47/2014)

Over and above this, municipalities will be required each month to submit information to the Minister for COGTA in order to assess performance in this regard. Provision of this information will result in intervention measures being employed by the Minister on areas where municipalities are facing challenges.

At the Presidential Local Government Summit, the level of performance of municipalities were confirmed and classified according to which category they belong. Municipalities were categorised either as functional, challenged or requiring intervention. The Mpofana Local Municipality was categorised as requiring intervention. The justification for this categorization included but not limited to;

- High Rate of Staff Turnover

- Backlogs in Housing development

- Backlogs in respect of basic services

- LED

- Debt Collection

- Electricity Distribution losses (Theft and non-payment)

- Poor systems, processes and procedures

- Poor monitoring and evaluation of municipal decisions

- Poor implementation of municipal by-laws and policies

- Lack of prioritisation of environmental matters

On the basis of the above the Municipality (both the Administrative and Political arm) have made a collective effort to address the aforementioned issues as identified through the B	ack to Basics Support Plan. A plan of action has thus been developed to address the aforementioned gaps. It is worth noting that as of the third quarter of 2017. Mpofana has been declared functional in as far as the Back to Basics is concerned.

Through the Back to Basics approach, this effort has also seen the culmination of a Support Plan which has recently been populated during COGTA’s visit to Mpofana Local Municipality. The support plan has since been sent to the Department and presented to the Council. Mpofana has also implemented the Back to Basics programme through various programmes and activities like the Clean-up Campaign and the Public Participation Meetings. There is a plan to host the official pothole filling week and is currently making plans to host the official launch of the Back to Basics Approach.

BACK TO BASICS IMPLEMENTATION PLAN and A DETAILED SUPPORT PLAN

| Challenge(s) Identified | Progress in addressing the Challenge |
| --- | --- |
| Community Protests | 1. Public participation to assist municipality with communication strategy. 2. Municipality to look at best practice with other municipalities with the same issues. 3. Public Participation Unit is to have a session with the municipality. |
| Capacity of the Municipality to deal with service delivery backlogs | The Municipality, through the consultation with Ward Committees and Councillors are trying to reduce backlogs. However, there are many constraints that the Municipality is faced with, e.g. financial constraints and lack of human capacity.. The DM assisted the Municipality by providing an excavator to clear the roads. EMakhuzeni water scheme are working with UMzinyathi DM to address the water issues. There are areas in Ward 2 that require housing; however, the challenge is the lack of infrastructure. The LM requires commitment from the DM in terms of the delivery of water and housing. Electrification has started in Ward 2 and 4, however the funds are being used from the Department of Energy’s approved funds for Ward 1 which is the licenced Ward in Mooi Mpofana. This is due to the fact that the Municipality cannot ignore the concerns of the people. Progress is made in the area of community participation. |
| Non-payment of Services | The Municipality has had a Revenue Enhancement Strategy Workshop. The main challenge is the illegal connection of electricity. Revenue Enhancement Strategy is yet to be presented to the Council for adoption and implementation. The strategy is in part being implemented although it’s yet to be approved. One of the strategy’s recommendations is that The Municipality shouldvisit their Wards with the Mayor, Officials and Councillors so as to encourage the community to pay for services. The Municipality applied to NERSA to charge companies within Mooi Mpofana normal rates. This matter was settled out of court and the companies are not paying special rates any longer. |
| MIG Expenditure | Due to the lack of cash flow, the Municipality has had challenges in fast-tracking its MIG expenditure. The municipality has since appointed a grant’s administrator who will see to it that reporting on expenditure is done. A challenge with MIG expenditure has been reporting on the actual expenditure. The grants administrator will mainly be reporting on MIG expenditure. |
| Water Provision | Once the reservoir is in place, water issues in Ward 1 and 3 will be resolved. UMDM through uMngeni Water is in the process of constructing a reservoir to ensure better access to water. |
| Housing Backlogs | The Municipality, the challenge is that the project commenced, however, the implementingagent did not complete the project. Since then the Municipality appointed another implementing agent to complete the housing project but an increase in money for the project to be completed was demanded from the IA which was not initially budgeted for. Engagement with the community has led into the project continuing. The Municipality stated that follow up must be conducted with COGTA: Municipal Finance. |
| Equitable share allocation inadequacy | The Equitable Share allocation remains a challenge for the Municipality, as it does not even cover salaries. The Municipality anticipates that with the addition of the new Ward, this will see an increased allocation of the Equitable Share. |
| Non-payment of services | With the Revenue Enhancement Strategy in place, the Municipality will be able to address this matter. The Municipality has intensified its collection effort. The revenue enhancement strategy further identifies services that the community should pay for. The Municipality will further tap into new avenues of revenue, where the community has not been paying; plans are in place to ensure that the community pays for these services. Our tariffs have also taken into account the socio-economic conditions, in that an indigent register which responds to the prevailing economic conditions that be is also in place in will be implemented in the 2017/18 financial year. |
| Critical Posts in the Finance Department | The late Chief Financial Officer had to work under severe pressure without any middle management within the Budget and Treasury Directorate. The vacancy that has been left by the CFO will be filled soon, and an advert to this effect has been advertised. Currently there is an acting appointment in the position of the CFO. The Municipality has further advertised the position of the Supply Chain Manager; this is to be filled in at the beginning of the 201/17 Financial year. Other than beefing up the staff, the appointment of the Supply-Chain Manager will further address the concerns or issues raised by the Auditor General. |

MPOFANA MUNICIPALITY: BACK TO BASICS SUPPORT PLAN as at Quarter 3 2017

MPOFANA MUNICIPALITY: BACK TO BASICS SUPPORT PLAN (Quarter 3 2017)

| NO. | Challenges | Quarterly Activities | Start Date | End Date | STATUS: Support Provided by COGTA/SECTOR & MUNICIPAL ACTIONS | QUARTERLY TARGET PROGRESS STATUS | CHALLENGES |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Strategic Issues |  |  |  |  | (To be completed by Municipality) |  |
| - PILLAR 2: BASIC SERVICE DELIVERY | Municipality is currently conducting disconnections for illegal connections. Agreements with Eskom in terms of paying the money owed to Eskom. | - Check all households in terms of connections. Pay Eskom R3 000, 000. - Carry out disconnections Pay Eskom R 3 000, 000. Hold Community Meetings. - Pay Eskom R 3 000, 000. - Pay Eskom R 3000 000. | - 4th July 2016 - 03rd October 2016 | 30 Sept 2016 Ongoing |  | - Households in Town and Riversdale Checked and 1 Community Meeting held in Riversdale. - Community Meetings held with Ward 1 and 3 and households have been checked. - Eskom paid for all months in the 3rd quarter. |  |
| PILLAR 4: SOUND FINANCIAL MANAGEMENT | Debt Management - Non-payment of services | - Advertise for Debt Collectors, Categorisation of debt through the use of age analysis - Appoint Debt Collectors - Carry out disconnections | - 4th July 2016 - 30 Sept 2016 - Ongoing | Ongoing |  | - Advertised for debt collectors - Process of appointing Debt Collector in process - Debt Collectors appointed |  |
| PILLAR 1: PUTTING PEOPLE FIRST | Non-submission of ward reports by ward councillors | 1. Enforce compliance by councillors with the councillors code of conduct. 2. Present quarterly report to speakers forum on the non-compliant councillors. | 1.01/09/2016 | 1. 6/30/2017 2. Ongoing 3. Ongoing | High-Level | - To commence in the second quarter - Not submitted - Submitted |  |
| PILLAR 2: BASIC SERVICE DELIVERY | Infrastructure Plans not In place | 1. Verification of status of plans. 1 - WSDP (WSAs), 2 - ESP (Licensees), 3 – IWMP, 4 - Housing development plan, and Roads master plan 2. Facilitate sector support for review or development 3. 3-year Capital Development Plan for MIG (exception : Ethekwini Municipality) | 1. 01/07/2016 2. 30/12/2016 | 1.01/09/2016 2.01/03/2017 | Low Support | - MEC Letter already made available wherein outstanding Sector Plans were pointed out. The outstanding sector plans have since been given to the HOD. - The Municipality has identified outstanding sector plans and will be included in the DRAFT IDP. - Electricity Maintenance Plans in place |  |
| PILLAR 2: BASIC SERVICE DELIVERY | Maintenance programme with appropriate funding | 1. Make input into policy – increase allocation for R&M and verify 6% of energy purchased 2. Verification of the current replacement cost of the infrastructure assets 3. Asset management plan 4. Ring-fencing of R&M budget 5. Monitor the budget and expenditure on R&M | 1. 30/06/2016 2. 01/09/2016 3. 01/12/2016 4. 01/03/2017 | 1. O & M guideline document adressing financial allocations by 31 January 2016 2. Confirmation of Current Replacement Costs of infrastructure assets by (Municipal Finance to advise) 3. 30 June 2016 (Municipal Finance to confirm) 4. 30 June 2016 (Municipal Finance to confirm) 5. 31 July 2016 (2014 | High Level | - Input to be made in the Adjustment Budget. - Inputs already made into the 2016/17 Adjustment-Budget - Input Made towards Maintenance programme |  |
| PILLAR 3: GOOD GOVERNANCE | MPAC meetings not held on a quarterly basis | 1. Review of MPAC guideline by DCOGTA. 2. Intensive training /capacitation of councillors. 3. Quarterly monitoring of 61 municipalities MPAC meetings (POE – attendance register, front page of Agenda and Minutes). - Consequences of non-compliance – assessment rating affected negatively. | 1. Post elections | 1. 6/30/2016 2. Quarterly 3. Quarterly | Low Support | Municipal Governance & Admin - MPAC established - MPAC trained - MPAC Meetings held |  |
| PILLAR 4: SOUND FINANCIAL MANAGEMENT | 1. To improve Municipal Audit Outcomes | 1. Analyse AG Letters 2. Cogta to create and diseminate post action plan template 3. Provincial analysis of audit action plan with feedback 4. MEC engagement with poor performing municipalities 5. Municipalities to implement post audit action plans | 2016/12/31 | 1. 31 Dec 2016 2. 31 Jan 2017 3. 31 Jan 2017 4. 28 Feb 2017 5. 30 June 2017 | High Support | Municipal Finance - Letter analysed - COGTA assisted with developing an action plan - Action Plan developed and being implemented |  |
| PILLAR 5: BUILDING CAPABLE LOCAL GOVERNMENT INSTITUTIONS | 12. Vacant MM and Section 56 posts | 1. Municipalities to inform COGTA of vacancies at least 3 months before expiry of contract and at least 7 days of resignation or termination being lodged. 2. Municipalities to inform COGTA of recruitment plans forthwith. 3. Quarterly monitoring of filling of MM and Section 56 Manager posts and taking of appropriate action in the event of failure to fill vacancies 4. Merging municipalities to submit proposals for filling of vacancies to CMCs for approval | 1. 3 months before expiry of contract and at least 7 days of resignation 2. Within 7 days 3. 01/04/2016 4. As and when vacancies occur |  | Low support | - Municipal Governance & Admin - CFO- Post advertised - Corporate Services-Post advertised and interviews to be held in the third quarter. |  |
| AUDIT OUTCOME STRATEGIES/ PILLAR 5 | Audit committees 1.The audit committee did not advise the council on matters relating to effective governance, performance management and performance evaluation as required by section 166(2)(a) of the MFMA. 2. The audit committee did not advise the council on matters relating to compliance with legislation, as required by section 166(2)(a)(vii) of the MFMA. 3. The audit committee did not review the municipality's performance management system and make recommendations to the council, as required by the municipal planning and performance management regulation 14(4)(a)(ii). 4.. The audit committee did not review all the quarterly internal audit reports on performance measurement, as required by the municipal planning and performance management regulation 14(4)(a)(i). 5. The audit committee did not submit, at least twice during the financial year, an audit report on the review of the performance management system to the council, as required by municipal planning and performance management regulation 14(4)(a)(iii). | Quarter 1 -Provide Chairperson and member of PAC with compliance checklist Quarter 2-Monitor compliance and provide recommendations Quarter 3-Monitor compliance and provide recommendations Quarter 4-Monitor compliance and provide recommendations | Quarter 1 - 1 April 2016 Quarter 2-1 July 2016 Quarter 3-1 October 2016 Quarter 4-1 January 2017 | Quarter 1 -30 June 2016 Quarter 2-30 September 2016 Quarter 3-31 December 2016 Quarter 4- 31 March 2017 |  | Municipal Finance - Audit Committee meetings held (Compliance Checklist given to the Audit Committee) - MPAC given recommendations |  |

This Back to Basics Support Plan was accepted and signed off by the Municipal Manager, The Support is being implemented.

.

ISSUES RAISED BY THE MEC AND HOW WE HAVE ADDRESSED THOSE ISSUES (MEC LETTER)

See THE ENSUING PAGE

| KPA Name | Issue(s) raised by the MEC | Progress in addressing the issues raised |
| --- | --- | --- |
| Municipal Transformation and Institutional Development | No adoption dates and the status of implementation of the Human Resource Strategy | The dates for the adoption of these plans has thus been indicated |
|  | Vacancy in the Senior Management | The post for Corporate Services Director has been advertised including the post of the CFO. It should however be noted that both these positions have acting appointments. |
|  | No indication of vacancy rate | This has been addressed in this review, Please see page of IDP |
| Local Economic Development | No indication as to when the LED Strategy was prepared and adopted. | This has been indicated |
|  | No indication of economic drivers of the Municipality. | See Organogram (Attached), furthermore, the Post of LED Manager has been advertised and will be filled in the current review. |
|  | No information from Social Development Section. | This information has been included. |
| Basic Service Delivery | Water and Sanitation graphs are technically incorrect. No inclusion of information provided by uMngeni Water. | Water and Sanitation graphs have been provided Information by uMngeni Water has been included. |
|  | No adoption of the Integrated Waste Management Plan (IWMP) | The Integrated Waste Management Plan has been adopted at a Council Sector Plans) |
|  | Inclusion of electricity section | This section has been included, please (See page 101 of the IDP) |
|  | No Spatial mapping of backlogs for telecommunication | Backlogs have been spatially referenced |
| Financial Viability and Management | The Municipality has provided limited information on its capacity to implement capital projects. | See below |
|  | The Municipality has limited Capacity to implement capital projects. | The post of Technical Director is filled, and the Municipality has spent over 90% of its Capital Budget, A manager for Roads (where most of our Capital budget is spent) is appointed. |
|  | No review of the indigents and provisions of free basic services | The Indigent Register has since been reviewed, and has been approved by Council, the community will now benefit from the provisions of free basic service. |
| Good Governance and Public Participation | No communication Plan | The Communication Plan has |
|  | Status of Bid Committees not provided (No indication of members) | The status of the Bid Committees has been provided and the members that serve in those committees are indicated |
| Cross-cutting Interventions | Partially compliance with MSA regulations | This has been taken care of |
|  | No alignment with neighbouring Municipalities | This has been aligned; The SDF has made provisions for alignment with neighbouring Municipalities. |
|  | No Capital Investment Framework | This has been included in theSDF. |
|  | No Disaster Management Sector Plan place | The Plan is in now in place and is adopted by Council. The Draft Disaster Management Plan has also been tabled. |

Provincial-COGTA has further provided assistance in terms of developing a Support-Plan for Municpalities with time frames wherein other Sector Departments will be involved in ensuring that the support plan is realizable and achievable.  Below is a plan which has recently been signed off by the Municipal Manager and is closely monitored by the Honorable Mayor, Council and COGTA. The office of the Municipal Manager is responsible for the co-ordination of the Back to Basics Programme.

# Section C: Situational Analysis

## C1. Spatial Analysis

### C1.1. Regional Context

Mpofana Municipality is one of seven local Municipalities that makes-up uMgungundlovu District. It is located along the N3 approximately 70km west of Pietermaritzburg. It borders onto uMngeni, uMshwathi, uMvoti, Imbabazane and uMtshezi Municipalities. Mooi River is the only major town in the area and provides services to areas within the municipal boundaries. The other emerging small town is Rosetta which has a smaller catchment and a strong eco-tourism character.The area is within Mooi-River catchment and is dominated by commercial farmlands. Rosetta has been included under the newly approved Mpofana Town Planning Scheme.

Mpofana municipal boundaries were delineated in terms of the Municipal Demarcation Act and the criteria set therein. This includes population movement trends, regional economic patterns and land use pattern. The municipal boundaries are not just administrative, but are also intended to promote social and economic development. They are also spatial planning boundaries in line with the municipal planning mandate of local government. To the West are the former District Management Areas of the Drankensberg that fall under the Transfrontier Development Initiative related to the World Heritage Site, Mpofana Local Municipality has thus formed close ties with uMngeni Local Municipality and uMtshezi Local Municipality that lies north of Mpofana Local Municipality.

### C1.2. Administrative Entities

The Mpofana Local Municipality is a Category 2 Municipality as established in terms of Chapter 2 of the Municipal Structures Act 1998. The Municipality functions under a plenary executive system combined with a ward participatory system. The political leadership of this Municipality consists of seven (7) Councillors of which four (4) are Ward Councillors and the remaining three (3) are Councillors elected as Proportional Representatives of their political parties.

### B1.3. Structuring Elements

The Integrated Development Plan depicts a number of challenges related to the existing spatial structure. These challenges are translated to elements that must form the basis of analysis and needs to be addressed in the spatial development framework.

These structuring elements include the following:

The majority of the area located north-eastern part of the municipal area are characterised by poor soil conditions and low mean precipitation rate;

A large number of properties acquired by the previously marginalised through the land reform program are lying idle or grossly underutilised. This has potential to undermine the viability of the agricultural sector and the economy of the area as whole;

Fragmented spatial structure with settlements located far apart from each other and away from economic/employment opportunity areas.

Environmentally sensitive areas with endemic species, which limits the nature and extent of development.

Inadequate capacity of the bulk services such as electricity, water and sewer systems.

Rugged terrain in the bush thicket areas.

It should be noted however that the Municipality is strategically located on the N3, Making it easier to access.

Most land is agricultural which has a potential of unlocking Mpofana’s economic growth.

The Municipality is located closer to the Drankensburg which is well developed and functional tourism industry.

### B1.4. Nodes Assessment And Development Corridors

In Accordance with the current Mpofana Spatial Development Framework, the following hierarchy of nodal areas is defined for the Mpofana Local Municipality.

| Large Convenience Centre | Serve as administrative and economic centre |
| --- | --- |
| Service Centre | Serves as distribution point |
| RSC Satellite | Serves as area for delivery of supplementary services. |

The proposed development nodes for Mpofana Municipality are the following:

Table 1Proposed Nodes

| Large Convenience Centre | Service Centre | RSC Satellite |
| --- | --- | --- |
| Mooiriver | Rosetta | Tendele |
|  |  | Rietvlei |
|  |  | Middelrus / R74 (Rocky Drift) |

#### C1.4.1. Primary Development Nodes / Large Convenience

Centres

Mooi-River is the major residential and commercial centre withinthe Mpofana Municipality. The town is highly accessible atboth regional and local scale with the N3 and R103 runningthrough in an east-west axis, R622 and P169 linking the townwith the Berg and areas as far as Greytown and beyondrespectively. Passenger and freight railway line linking Durbanand Johannesburg also runs through the town.

Role and Function

Mooi River performs a number of functions within its sub regionalcontext. These could be summarised as follows:

Service centre:

It provides access to a range of higherorder services to its sub-region andbeyond.

Economic hub:

It provides the highest concentration ofcommercial and industrial uses with strong functional linkageswith thesurrounding major centres suchPietermaritzburg.

Transport interchange: It provides transportation

Linkages between various parts of the municipal area andmajor urban centres such asPietermaritzburg, Durban andEstcourt.

Residential area:

A large number of people reside within

Mooi River Bruntville area.

The following interventions / developments are envisagedwithin this Node:

Industrial development based on the agro-economy;

Commercial Development;

Decentralizationpoint for local administration ofprovincial and local government services;

Higher order social and commercial services;

Integration with major urban centres;

Housing development.

#### C1.4.2. Mooi River Node

Mooi River is the only primary node within Mpofana LocalMunicipality. Mooi River Town is the primary node and the mostdenselypopulated area within the municipality. It serves as themain commercial and administrative centre and is a priority focus area. With a large concentration of people,development efforts are focused on economic development& service provision, job creation, government services andensuring basic services. The Node and a conceptual boundaryis illustrated below.

Figure 1: Mooi River Primary Node

existing facilities within this node Includes:

Primary School x 3

Secondary School x 1

Clinic x 1

Library x 1

Community Hall x 2

Post office x 1

Magistrates Court x 1

Police Station x 1

Civic Centre x 1

Sports Field x 2

Regular Bus Service

Taxi Rank x 1

Although the above table only reflects facilities within thenodal point, various projects are being implemented in thenodal area of influence. A Nodal Sphere of Influence could

technically be defined as the halfway mark between twonodal areas. This is an assumption made when a fairly evenspread of population exist. It is necessary to investigatetravelling distances, travelling times and locationalchallengeswhich impacts on accessibility of a node.

According to the Standards for Provision of Services thefollowing additional social amenities and services are to beprovided within this Primary Node.

Multi Skilling & ABET Training Centre x 1

Hospital x 1

Emergency Services Facility x 1

Church x 1

Multi-Purpose Community Centre/ Thusong Centre x 1

Old Age home & Service Centre x 1

Pension Pay Point x 1

Post Office x 1

Sports Complex (Including Swimming Pool) x 1.

#### C1.4.3. Secondary Development Nodes / Service Centres

The area of Rosetta has been identified as Secondary Node orService Centre. The town plays an important role as servicecentres to communities and farmers in the western and centralportions of the municipality, providing housing and a smallerrange of commercial and social services than what is offeredin the Primary NodeRosetta is accessed off R103linking Mooi-River town andNottingham which is within Umngeni Municipality and it formspart of the Midlands Meander. The development of the SpringGrove Dam is anticipated to lead to further developmentaround Rosetta, especially related to tourism.

#### C1.4.4 Rosetta Node

Rosetta is characterised by locally handcrafted artefacts,accommodation such B&B’s and Rosetta Hotel, restaurants,low-density residential facing the scenic views of Mooi-River,

local convenient shops and modern smallholdings. Theintention with Rosetta is to protect the country landscape(which has aesthetic value and attracts small scaleeconomicand tourism activities related to the Midlands Meander).

TheNode and aconceptual boundary are illustrated below.

Existing facilities within this node Includes:

Primary School x 1

According to the Standards for Provision of Services thefollowing additional social amenities and services are to beprovided within this Secondary Node Node.

Preschool Facilities x 1

Emergency Service Facilities x 1

Police Station Mobile x 1

Church x 1

Pension Pay Point x 1

Post Office x 1

Bus Service on Regular Basis x 1

Taxi Rank x 1

Figure 2 Rosetta Secondary Node

#### C1.4.5. Tertiary Development Nodes/ Rsc Satellite

Tertiary nodes/ RSC satellite are the lowest order nodesidentified within this SDF and maydevelop a nucleus andemerge into higherorder nodes over time. A range of servicesfor local communities could be concentratedwithin thesenodes in a sustainable way. In identifying service satellites anumber of factors should be considered to determine the mostsuitable / optimal locations.

These include, amongst other factors:

Density and distribution of population to be served

Level of existing economic activity

Proximity of transport routes and modes of transport

Topography of locality

Land Tenure arrangements

Levels of service infrastructure

#### C1.4.6. Tendele Node

Tendele identified as a tertiary node is located few kilometresaway from the P164approximately 52km south-west of Mooi-River and within the foothills of UKhahlambaDrakensberg andin close proximity to Kamberg Nature Reserve. The area isdormitory ruralresidential settlement and it currently existsinformally with limited social and economic activities takingplace within it. The node is illustrated on the figure below.

Figure 3: Tendele Tertiary Node

Existing facilities within this node Includes:

Combined School (Primary and Lower Secondary) x 1

According to the Standards for Provision of Services thefollowing additional social amenities and services are to beprovided within this Secondary Node.

Preschool Facilities x 1

Clinic x 1

Church x 1

Pension Pay Point x 1

Bus Service on Regular Basis x 1

Taxi Rank x 1

#### C1.4.7. Rietvlei Node

Rietvlei is situated directly east of Mooi River on the R622 andhas been identified as an tertiary node offering limitedservices to surrounding rural areas within the Mpofana LocalMunicipality. The node is illustrated on the figure below.

Figure 4: Rietvlei Tertiary Node

Existing facilities within this node Includes:

Combined School (Primary and Lower Secondary) x 2

According to the Standards for Provision of Services thefollowing additional social amenities and services are to beprovided within this Secondary Node.

Preschool Facilities x 1

Clinic x 1

Church x 1

Pension Pay Point x 1

Bus Service on Regular Basis x 1

Taxi Rank x 1

#### C1.4.8. Mkholwane Node

uMkholwane has been identified as a tertiary node withinMpofana Municipality and issituated in the north easterncorner of themuncipal area. As with Tendele and Rietvlei it

offers limited commercial and social facilities for surroundingrural areas. The Node and aconceptual boundary is illustratedbelow.

Figure 15: uMkholwane Tertiary Node

Existing facilities within this node Includes:

Combined School (Primary and Lower Secondary) x 1

According to the Standards for Provision of Services thefollowing additional social amenities and services are to beprovided within this Secondary Node.

Preschool Facilities x 1

Clinic x 1

Church x 1

Pension Pay Point x 1

### C1.5. Land Cover And Broad Land Uses

#### C1.5.1. Land Cover

The broad land cover found in municipality, can be depicted below. From the land cover data it is evident that the evaporation in the municipality is relatively low, with virtually the entire municipal area falling in the 1400 1600mm range (dry land and Irrigated), with especially high occurrence of this around the Mooi River area. The north and north eastern mountainous areas are mainly covered with woodland and bush land with some scattered dense bush, whilst the southern sloped areas are distinctively covered with commercial crops (dry land), plantations and some wetland areas with dense bush. The majority of settlements are characterised as rural in terms of density and character. These settlements are scattered all over the municipality occurring along national and provincial roads. The main concentration of subsistence farming is found in the northern portions of the municipality. There is a noticeable concentration of urban built up areas adjacent to the N3.

Map 3: Land Cover

#### C1.5.2. Existing Agriculture And Agricultural Potential

The various agricultural land uses in the municipality is indicated on Existing AgriculturalMap, and corresponds greatly with Map 8: Agricultural Potential This map becomes particularly useful in identifying uncultivated opportunities in the agricultural sector when it is overlaid with the land capabilities in the municipality, with specifically land capability classes I to IV. From this map it is clear that the areas with higher agricultural opportunities (or potential) in the southern and western parts of the municipality have already been utilised to a great extend for cultivated temporary commercial and cultivated permanent commercial irrigated purposes. The evaporation in the municipality is relatively low, with virtually the entire municipal area falling in the 1400 1600mm range.

Consideration of these two maps, with its medium to high rainfall and low precipitation makes it clear why large areas of the municipality is suitable for sugarcane production and has a relatively high agricultural potential. The central parts of the municipality are further given this advantage by the relatively low gradient of slopes.

Map 4: Existing Agriculture

Map5: Agricultural Potential

It is evident from the above Map that, there is a lot of agricultural potential in MpofanaSpatial & Environmental: SWOT Analysis. The agriculture sector is one booming sector which is to have an impact in the growth of the Mpofana economy; this is evidenced by the amount of land available which has agricultural potential as can be seen in the preceding map.

### C1.6. Land Ownership

The entire municipality is characterised by privately owned farms that consist of private, trust and private business ownership while State and Provincially owned land are found along the eastern boundary and in the central areas of the municipality. A relatively large area owned by Mondi can be depicted in the south eastern corner. The far western section consists of land previously known as District Management Areas (DMA). The majority of the land is privately owned, although a greater portion of the land is owned by Department of Public Works.

Map 6 Land Ownership

### C1.7. Land Reform

The implementation of the land reform program in Mpofana Municipality is progressing very slowly. As indicated on figure 11 below the land redistribution program has delivered 3 246ha (18%) and land restitution is hovering at about 3 023ha (17%). Approximately 7 050ha (40%) worth of farms are under the labour tenant program. The other restitution claims that have been lodged amount to 4 248ha (24%). Land reform projects have serious spatial implications within Mpofana Municipality. It is important for the municipality to monitor this program given its potentially serious implications for the implementation of the Municipal Property Rates Act (MPRA).

These land reform projects are located within various parts of the municipal area. It involves land ranging from good to low agricultural potential. The settlement of labour tenant applications is one of the priority programs of the Provincial Land Reform Office (PLRO). A number of labour tenant applications spread unevenly in space were lodged with the Department of Land Affairs and are currently being assessed and finalised. The outcome of this process has serious spatial implications including emergence of small isolated settlements in the middle of commercial agricultural land.

### C1.8. Environmental Analysis and LAND CAPABILITY

#### C1.8.1. Biodiversity (including Protected Areas)

Ezemvelo KZN Wildlife compiled a map depicting Critical Biodiversity and ecological support areas for the uMgungundlovu Municipality.

The image below is an extract from this map depicting the Municipality.

Map 7 : Critical Biodiversity

The map depicts Critical Biodiversity Areas (CBA’s) as well as Ecological Support Areas in Local Municipality.

The two environmental areas are defined as follow:

CBA’s depicts landscapes that need to be maintained in a natural or near-natural state in order to ensure the continued existence and functioning of species and ecosystems as well as facilitate the continued delivery of ecosystem services. Maintaining an area in a natural state can include a variety of land uses compatible with the present biodiversity resources.

Ecological support areas (ESA’s) are areas that are not essential for meeting biodiversity representation targets/thresholds but which nevertheless play an important role in supporting the ecological functioning of critical biodiversity areas and/or in delivering ecosystem services

Support socio-economic development, such as water provision, flood mitigation or carbon sequestration. The degree of restriction on land use and resource use in these areas may be lower than that recommended for critical biodiversity areas.

The purpose of CBA’s is simply to indicate spatially the locationof critical or important areas for biodiversity in the landscape.

The CBA, through the underlying land management objectivesthat define the CBA, prescribes the desired ecological state inwhich we would like to keep this biodiversity. Therefore, thedesired ecological state or land management objectivedetermines which land-use activities are compatible with eachCBA category based on the perceived impact of eachactivity on biodiversity pattern and process.

From the map above it is clearly seen that the largest part ofthe municipality is classified as Transformed Land Areas interms of its land use surface, where very little conservationstatus exist. Through rural residential and subsistence farmingactivities, the land has been transformed from ecologicalsensitive, to land uses associated with residential activities.

Drakensberg Park BoundaryScattered areas around Mooi River are classified as a CBA 1area where Critically Endangered eco-systems are functioningand strict land use management procedures needs to beimplemented.

The outer periphery towards the western boundary is depictedas CBA 1 areas. CBA 3 areas are scattered throughout thenorth eastern part of the municipal area. Other smallerresidential groupings are situated on the western boundary ofMooi River town.

Map7 Environmental Sensitivity

#### C1.8.2. Hydrology

The Mpofana Municipality falls within the Umgeni/ MooiCatchment of the Umgeni Operational Region. The uMngeni/Mooi region comprises of the two tertiary catchmentsof U20 (Mgeni River) and V20 (Mooi River).

The major urban centres of Durban and Pietermaritzburg aresituated within the Mgeni catchment. There are a number of

other urban and peri-urban centres within this region includingMooi River, Rosetta, Nottingham Road, Howick, Wartburg,

Cato Ridge, and the greater surrounds of both Durban andPietermaritzburg. The urban centres from Howick towards the

coast receive their water from the Mgeni system.

According to the Umgeni WaterInfrastructure Master Plan thedemands in the Umgeni catchment currently exceed theavailable yield. The risk of waterrestrictions within the next fewyears isunacceptably high as a result of the ever increasingdemands in the uMngeni system.

Map 7: General Layout of theUmgeni/Mooi.

The figures below illustrate the groundwater potential of theUmgeni/Mooi Region. The central area around Albert FallsDamindicates a yield of >3 l/s, with the northern section ofMpofana Municipality around Means Weir depicting >0.1-0.5L/s.

Map 8: Groundwater Potential of the Umgeni/ Mooi.

Significant growth in water demand from the Mgeni systemhas occurred since the implementation of MMTS-1, such that

the required level of assurance of supply is not being met.

Therefore it is important that Phase 2 of the Mooi-MgeniTransfer Scheme isimplemented, as it is the project closest to

Implementation and is the least expensive project per cubicmetre of yield obtained. At the end of 2007 the Minister ofWater and Environmental Affairs instructed the Trans-Calendon Transfer Association (TCTA) to implement thisproject as quickly as possible in order to augment the existing

system and reduce the risk of possible future restrictions.

Two stages were defined in the feasibility study of MMTS-2. Inthe first stage only Spring Grove Dam (MMTS-2A) would be

constructed. During this stage water will be released fromSpring Grove Dam down the Mooi River into the impoundmentof the Mearns Weir (MMTS-1) from where it will be abstractedand transferred, The Mearns Weir is situated just downstream of

the confluence of the Little Mooi and Mooi rivers.

For the second stage (MMTS-2B) a new pumping station wouldbe constructed at Spring Grove Dam from where the bulk of

the transfer from the Mooi to the Mgeni River would takeplace. This would include the construction of a new transferpipeline from Spring Grove Dam that would, apart fromfollowing an initial short route from the dam through an area ofsmallholdings to the existing transfer route, be following the

same route as that of the existing Mearns pipeline, and runningparallel to it within the existing servitude, to the dischargepoint in the Mpofana River.

Salient features of the proposedSpring Grove Dam, asdetermined during the detailed designphase of the dam are as follows:

Full supply level: 1 433.50 mASL

Minimum operating level: 1 408.00 mASL

Gross storage volume: 139.5 million m3

Water surface area at FSL: 1 021.8 ha

The figure below illustrates the proposed water resourceinfrastructure within the Umgeni/Mooi Region. Depicted on the

figure it is clear that the construction of the Spring Grove damis underway which will lighten the burden on the currentdemand of water provision.

Map 9: Proposed Water Resource Infrastructure in the Mooi/ uMngeni.

The Pipeline is due to commence soon, this will also service other areas outside of Mpofana as can be seen in the map above. The pipeline will also help with the eradication of some backlogs that exist with the public’s access to water, as areas that have not had water are earmarked to benefit from the pipeline. As it stands, there are over 8000 people that are without tap water, but are serviced with water tankers.

#### C1.8.3. Climate Change

The Umgeni Water Infrastructure Master Plan make reference that that the climate is changing globally and that this will have an amplified impact on water resources and therefore on water security and supply. In South Africa, the Department of Environment Affairs (DEA) is designated to lead the country’s climate change agenda, guided by their recently adopted Long Term Mitigation Strategy on Climate Change. Umgeni Water developed a framework to guide its efforts towards quantifying the possible impacts of a changing

climate on its business. At the core of the framework is a hydrological model wherein rainfall and temperature are altered to represent possible scenarios of the impact of future climates on runoff in rivers. The most up-to-date science has been used in this assessment but unfortunately these results are far from conclusive because performing impact studies, such as water resources, based on scenarios of future climates is relatively new and would therefore need more available data to depict any changes that might occur in the Mpofana Municipality.

#### C1.8.4. Strategic Environmental Assessment

The municipality needs to provide a strategic assessment of the environmental impact of the spatial development framework on the natural environment. This is a particularly involved task in the Municipal area, due to the importance and environmental significance of the municipal area. This statement is underpinned by the strategic importance of the UKhahlamba World Heritage Site, in particular.

Although the UDP WHS Buffer Technical Committee have proposed number of guiding principles and rules to be used by developers and authorities in establishing the appropriateness of a proposed development within the buffer to the UDP WHS, the restrictive implications of some of these proposals on the agricultural and tourism development potential of the municipality needs to be considered before is adopted as policy by the municipality. The list below provide a summary of the guiding principles proposed by the buffer committee for development within the so called “Trail Zone” and “Buffer Zone” areas associated with the UDP WHS.

### C1.9. Spatial & Environmental: SWOT ANALYSIS

STRENGHTS

LAND AVAILABILITY FOR FUTURE SPATIAL PROJECTS

SDF IS REVIEWED ANNUALLY

LOCATION ALONG THE N3

WELL DEFINED NODAL AREAS IN THE MUNICIPALITY

OPPORTUNITIES

WATER SOURCES (DAMS)

MUNICIPAL LOCATION

R622 PROVINCIAL ROAD

UNCOMMITTED LAND ALONG THE N3

congested with traffic accessing Rosettaand Nottingham Road areas.

Land Reform Projects.

The large number of land reformprojects identified within the north eastern portions ofthe municipality, and within

ANTICIPATED DEVELOPMENT CHALLENGES

In order to realise the spatial development vision proposed within this report, various anticipated development challenges will need to be acknowledged, considered and systematically addressed.

WEAKNESESS

1 PRIMARY NODE

1 AREA IDENTIFIED AS AN INDUSTRIAL HUB

LACK OF INDUSTRIAL LAND

LACK OF HUMAN RESOURCE WITHIN THE TOWN PLANNING UNIT AND BUILDING INSPECTORATE

HIGH POTENTIAL AGRICULTURAL LAND

THREATS

CLOSE PROXIMITY OF HOUSES TO THE N3 (TOWNVIEW)

NO FIRE PROOF CABINETS WITHIN THE BUILIDING INSPECTORATE UNIT

ENCROACHMENTS (LAWLESSNESS IN COMPLYING WITH PLANNING LAWS)

DETAILED RESEARCH & PLANNING

As mentioned above, certain key areas are vital economicgenerators and /or social

Table 28 : Necessary Further Planning & Research

| Detailed Research / Planning | Brief Description |
| --- | --- |
| SIP2 Corridor Interventions Planning | More detailed assessment and precinct planning around Mooi River with particular reference to its role and contribution towards the larger SIP2 Corridor initiative. This will include a detailed regional infrastructure assessment, rail linkage assessment, roads upgrading requirements especially the R103 capacity and the N3 interchanges within the municipal area etc. |
| Mooi River Urban Regeneration Plan | The Mooi River Urban Regeneration Plan is being formulated with specific attention to the potential additional facilities to be incorporated within this node to serve the wider community of the municipality. |
| Nodal Development Plans | Nodal Development Plan Study with more detailed spatial structure and implementation planning for each of the identified nodes and addressing the land requirements for proposed facilities and services. |
| Infrastructure Investigation and Sector Planning | Identify, quantify and provide location requirements of engineering infrastructure and service provision for existing and future development needs. This will include a quantification of needs and estimated budgets towards a systematic Infrastructure Investment Plan. |
| Agricultural Development Strategy | Investigation into the further expansion and diversification of agricultural production within the area. Specific focus will also be given to the potential unlocking of the agricultural potential within the eastern portions of the municipal subject to land reform projects. |
| Land Reform Investigation and Strategy | Conclusion of land reform projects as well as a sustainable implementation, rehabilitation and management plan of settled communities within especially the northern areas of the municipality. |

### C1.10. Disaster Management

#### C1.10.1. Municipal Institutional Capacity

According to section 52, subsection (1) of the Disaster Management Act of 2002, Act no.57, each Municipal entity indicated in the national or the relevant provincial or municipal disaster management framework must-

Prepare a disaster management plan setting out the way in which the concept and principles of disaster management are to be applied in its functional area;

Its role and responsibilities in terms of the National, Provincial or Municipal Disaster Management frameworks;

Its role and responsibilities regarding emergency response and post disaster recovery and rehabilitation;

Its capacity to fulfil its role and responsibilities;

Particulars of its disaster management strategies; and

Contingency strategies and emergency procedures in the event of a disaster, including measures to finance these strategies;

Co-ordinate and align the implementation of its plan with those of other organs of state and institutional role-players; and

Regularly review and update its plan.Mpofana Local Municipality has recently adopted  Disaster Management Sector Plan. A dedicated Disaster Management co-ordinator has been seconded as can be seen in the organogram.

The Municipality has recently given Disaster Management the attention it deserves, and with the assistance of uMgungundlovu District Municipality and the Provincial COGTA and other stakeholders, it is hoped that institutionally Mpofana’s Disaster Management Unit will be able to unlock the challenges. Until recent the Municipality has developed its Disaster Management Sector Plan (which is discussed greater detail later in the document) and has been adopted by Council at its seating on the 30th of June 2017. Disaster Management now rests with the Ofifice of the Municipal Manager. The responsible personnel within Mpofana attends to all disaster related issues within the Mpofana’s jurisdiction. The roles of various stakeholders for disaster management at Mpofana are listed in the following table:-

Table 3: Roles of disaster management stakeholders

| Agency | Role |
| --- | --- |
| Head: Disaster Management | Coordinate disaster management within the District, Local Municipalities, Sector Departments and other agencies. Provide strategic direction on issues of disaster risk management in the District and provide linkage on district disaster operations with the Provincial Disaster Management Centre. Co-ordinate Volunteer Teams to support the district. |
| District Disaster Advisory Forum | Advisory body which consult one another and co-ordinate their actions on matters relating to disaster management in the municipality. Provide policy directions and integration of Disaster Management programmes. |
| International Agencies/NGOs | Provide relief, coordinate with Government Departments, conduct awareness and capacity building programmes, preparedness activities at community level, assist in reconstruction and rehabilitation |
| Department of Agriculture, Environmental Affairs and Rural Development | Co-ordinate agricultural related incidents or disaster such as drought, animal epidemics and many others. Be the primary agency responsible for pest attacks, cattle epidemics, assessment of agriculture crops, livestock damage and food needs, provide seeds for early recovery. |
| Department of Social Development | Provide social relief of Distress during disaster related incident to the victims and provide counselling to the victims. Assist with profiling of social welfare special cases as and when need arise during disaster assessments. |
| Department of Health | Be the primary agency responsible for biological disasters and epidemics, first aid, health and medical care, ambulance arrangements, preventive steps for other diseases, record of dead persons, mobile clinics and supply of medicines. |
| Department of Transport | Provide road traffic management during disaster related incidents. Logistics, transfer of relief material and relocation of affected people, road repairing, alternate routes |
| Department of Public Works | Maintenance of public infrastructure, search and rescue, identify safer places, assess physical damage, identify safer routes, provide necessary equipments for search and rescue, reconstruction and rehabilitation |
| Department of Water Affairs | Be the primary agency responsible for floods, dam failures, flash floods, landslides and mud flows. Drought and flood management, watershed management, enforcement of land-use plan, evacuation from low-lying areas, identification of safer places, construct embankments, arrangement of boats and pump sets, swimmers and divers. Strengthening of river banks. |
| South African Police Services | Be the primary agency responsible security, evacuation, emergency assistance, search and rescue, law and order, communication, setting up of emergency evacuation centers, shifting of people to relief camps, traffic management. |
| Department of Human Settlements | Develop appropriate national building codes and their proper implementation. In the post disaster phase, the Department will take adequate steps to undertake building damage assessment and promote reconstruction. |

#### C1.10.2. Risk Assessment

The main hazards faced by the Mpofana Municipality are floods, house fires, veld fires, environmental pollution, transport accidents, epidemic human diseases, snow, severe storms and lighting and thunderstorm. The risk rating of severe storms and flooding is very high. It is possible or almost certain that one can expect flooding or severe storms to happen in all the wards. The houses in rural areas such as Ward 4, Muden area are of poor standards. These conditions make these areas vulnerable to floods and severe storms.

The risk level of house fires is high. This could be attributed to the lack of information. The risk level of lighting and thunderstorm is high. People are economically and socially vulnerable because of a lack of economic growth potential and high level of unemployment and poverty. Road accidents happen frequently along N3. Roads in many wards are in poor conditions.

#### C1.10.3. Risk Reduction & Prevention

Mitigation activities actually eliminate or reduce the probability of disaster occurrence, or reduce the effects of unavoidable disasters.A precursor to mitigation is the identification of risks.

Disaster mitigation planning will comprise all activities that can be done for risk reduction. Mitigation measures can be structural or non-structural. Structural measures use technological solutions like flood levees. Non-structural measures include legislation and land-use planning.

Such activities that need to be undertaken by each Department should be identified and compiled. These activities can be planned after ascertaining the condition and status of infrastructure, equipment and manpower at the disposal of each department. The activities may include creation of any new infrastructure facility for risk reduction, repair, retrofitting or upgrading of existing infrastructures, procurement, hiring, or repairing of equipment; recruitment, hiring, and training of volunteers.

The detailed planning of the above activities will lead to the preparation of budget for disaster mitigation activities.

The following activities need to be taken up for reducing the future impact of disasters:

Roads and bridges or culverts

Flood control measures

Disaster awareness campaigns

Upgrade and maintenance of landfill sites

Upgrade and maintenance of waste water treatment works

Road sidewalk maintenance

Prevent forest fires by having fire breaks

Response & Recovery

Disaster preparedness activities will be planned and decided upon by the District Disaster Advisory Forum.

The District Disaster Advisory Forum comprises the following district authorities:

Head: Disaster Management

Members

South African Police Services

Department of Transport

Department of Health

Department of Transport

Department of Water Affairs

Department of Public Works

Department of Agriculture, Environmental Affairs and Rural Department

Department of Social Development

Department of Human Settlements

Representatives of Local Municipalities

Non-Governmental Organizations

The meetings of the District Advisory Forum will be held on quarterly basis, when a disaster or major incident occurs, the district will activate all members of the forum to convene for a special meeting. Those members will form a Joint Operations Committee (JOC) to assess the situation and make prompt decision on provision of rapid and effective response to normalize the lives of the victims.

The communities pass on information on the likely occurrence of a disaster to the respective authorities or JOC. The magnitude of the incident will determine whether there is a necessity to convene a special JOC. The Head: District Disaster Management will coordinate the meeting and other logistics required for the committee to execute its tasks diligently.

During established disaster prone phases in the year, the Forum will meet as a preparedness measure and will oversee preparedness activities being implemented on the ground.

Once the Joint Operations Committee (JOC) deems magnitude of the incident to be beyond its management and capability, the committee shall activate the Provincial Disaster Management Centre (PDMC) and forward the report to the Provincial Disaster Management Centre (PDMC) to seek immediate support  and appropriate provincial/national intervention.

#### C1.10.4. Training & Awareness

Mpofana Municipality in collaboration with the District Municipality will

Identify and train volunteers in all 4 wards of the municipality.

Assess and Increase the capacity of the municipality to handle disasters and improve on the  state of readiness to deal with disasters.

Increase public awareness on disasters

Prevention and mitigation of man-made disasters.

C1.10.5. Funding arrangements

The District Municipality leads the process of Disaster and have been identified as the funders of Disaster Management Operation in all the 7 Local Municipalities. Mpofana although aware of its responsibility in Disaster Management since a lot of areas which fall within Ward 4 are prone to disasters, is heavily dependent on the District’s Funding for carrying out its Disaster Management Functions. Mpofana however has one dedicated official for the task at hand, who will still be further trained for disaster related issues including the drought crisis facing KZN province.

#### C1.10.6. Disaster Management Swot Analysis

STRENGHTS

* DISTRICT’S MUNICIPALITY’S SUPPORT

*CONSTITUTIONAL MANDATE

* LOCAL RESPONSE PERSONNEL TO DISASTER RELATED ISUSUES IN PLACE

* DISASTER MANAGEMENT OFFICER APPOINTED

*DISASTER RESPONSE VEHICLE HAS BEEN PROCURED

OPPORUNITIES

REVIEW OF THE DISASTER MANAGEMENT PLAN

EDUCATION, TRAINIING AND PUBLIC AWARENES

BUDGET SET ASIDE

WEAKNESSES

LACK OF PROPER HOUSES IN WARD 2 AND 4 (SUSCEPTIBLE TO DISASTER)

LACK OF FUNCTIONAL DISASTER MANAGEMENT ADVISORY FORUM

LACK OF CO-ORDINATED PLANNING BETWEEN MPOFANA AND NGONYAMA TRUST BOARD

CENTRALISATION OF THE DISASTER MANAGEMENT UNIT AT THE DISTRICT MUNICIPALITY

THREATS

FLOODING AND HOUSE FIRES

STORMS

NO DISASTER MANAGEMENT ADVISORY FORUM

HEAVY RAINFALL

IMMINENT DROUGHT IN KZN

EVER CHANING CLIMATE

## C2. Demographic Characteristics

### C2.1. Demographic Indicators

#### C2.1.1. Population

Local authority has a total population of approximately 38 301 according to the 2011 Population Census compared to the 36 832 in 2001. The highest numbers of residents are settled in Ward 1 and 4 with the lowest number of people situated within ward 3. It should be noted that Ward 2 had the highest number of people according to the 2001 Population Census, which means there has clearly been internal migration within the boundaries of the municipality. Ward 1 includes the dense settlements of Mooi River and Bruntville whilst Ward 4 is inclusive of Middelrus and Rietvlei.

Utilising these 2001 and 2011 figures and the growth rate between 2001 and 2011, the following table was developed which depicts the estimated population growth over the 5 year period of the 2012 to 2017 IDP cycle.

Table 3: Future Population Estimates for the Municipality

| Future Year | Future Population |
| --- | --- |
| 2012 | 38101 |
| 2013 | 38219 |
| 2014 | 38337 |
| 2015 | 38301 |
| 2017 | 38573 |
| 2017 | 38692 |
| 2018 | 38912 |

According to the IDP 2012/2013 – 2017/2018, the municipality has shown a net increase in population between 2001 and 2011. According to the IDP, the 2007 community survey estimated the population at 31 517. This indicates either a discrepancy in the data or an incline in population numbers in the more recent years. A possibility for discrepancies in numbers could be due to an undercount during the 2007 community survey. This however seems unlikely to be the cause of such a substantial difference, and specifically decline in the population with the 2001 and 2011 population figures being relatively close. This can however be confirmed by the uMgungundlovu District Population Density.

Map 10: uMgungundlovu DM Population Density

Graph 2: Population as a Percentage of the District

Graph 3: Population per Ward 2001 vs. 2011

### C2.2. Key Findings

#### C2.2.1. Age And Gender Distribution

The demographic pyramids of municipality is illustrated by the graphs below and evidently in 2001 the population of working age was far less than the population going to school and of retired age groups.

Graph 4: Gender & Age Distribution 2001

Source: Stats SA Census 2001

The situation hoverer has changed slightly with a shift in population in the 20-29 year category making it a more evenly population spread. A large portion of the population is still dependent on a relatively small portion of the population earning an income. This, combined with the high unemployment rate, the situation becomes dire.

Graph 5: Gender & Age Distribution 2011

Source: Stats SA Census 2011

Depending on the birth rates during the following years, this pattern should stay very similar in the years to come. The number of men in the municipality is slightly higher than that of women, probably indicating the pattern of male migrant workers into the municipality, seeking work on commercial farms with women tending to households needs and practicing subsistence farming in the traditional areas of the municipality, especially those areas in the central and eastern parts of the municipality.

Graph 6: Gender & Age Distribution 2001 vs. 2011

Source: Stats SA Census 2001 & 2011

#### C2.2.2 Household Size

The average household size for the Municipality is calculated by dividing households into population the population recorded. The average household size for Mpofana is 5.8 persons per household. There has been a significant increase in the number of persons per household from 2001 with the average then recorded as 3.8 persons per household. Ward 2 has the highest number of households within the municipality with Ward 1, existing mainly of Mooi River Town having the second highest number of households.

#### C2.2.3. Population Density

The population density within the municipality is illustrated by the Household Distribution Mapwhich depicts the number of household points within the Local Municipality. It is clearly visible that the household distribution is scattered throughout the entire municipal area with higher density areas found south of Rosetta, north of Middelrus and in the town of Mooi River. This scattered distribution creates a lot of challenges with regards to equal provision of services, as well as the identification of a common Economic Development Initiatives to impact on the livelihoods of all residents in the municipality.

It will be necessary to identify potential areas for densification, where provision of services can be achieved cost-effectively, and efficient economic initiatives could be implemented.

Map 11: Household Distribution

The above map shows household distribution in Mpofana.

#### C2.2.4. Settlement Pattern

As indicated previously the municipality is characterised by scattered population distribution. The population towards the central parts of the municipality especially in Mooi River and Rosetta on the Settlements Map illustrates the concentrations around these because of its economic attractions. Although the settlements are scattered in nature with relatively low spatial densities, it is important to note that these settlements are not structured in formally established towns and thus the provision of services to these areas without linear patterns and limited servitude reserves are often challenging.

There is also no identifiable hierarchy of service centres that serves as a node to the majority of the population, while the only formal town is Mooi River. This poses a challenge in the provision of services, and a densification strategy / grouping of people will have to be considered in order to ensure cost effective provision of services, especially in the scattered rural areas with large numbers of households not living in close proximity and in a serviceable urban formation.

Map12: Settlements

#### C2.2.5. Levels Of Education

The graphs below depict the levels of education for residents for 2001 and 2011. Almost 3500 of residents had no formal school education in 2011 compared to approximately 7000 people in 2001 indicating a positive change education levels.

A significant difference in population with grade 12 can be depicted on the 2001 and 2011 combined graph, Graph 9 with approximately 3000 more residents completing grade 12. It must be mentioned that the figures in the some primary (grade 1-6) category are less in 2011 than in 2001

Graph 7: Levels of Education 2001

Source: Stats SA Census 2011

OTHER FINDINGS BASED ON DEMOGRAPHICS

- The demographics show that there is an increase in as far as the population is concerned; this could be accredited to the fact that there is an existing Tai-Yuen Textile which has attracted quite a number of people from neighbouring towns.

- There is an average of 5 people per household which suggests that there might be overcrowding, this means there is a need for more Housing Projects

- It is also evident that the levels of education are quite low, numbers show that a greater number of the older generation are illiterate which therefore arises a need to develop ABET classes so the levels of illiteracy are considerably reduced.

## C3. Municipal Transformation & Institutional Development Analysis

### C3.1. Municipal Transformation

The municipality fully subscribes to the requirement and provisions of the employment equity act and in giving effect to that all section 56 positions have all been filled by historically disadvantaged individuals.

Municipal Manager: African Male

Acting- Chief Financial Officer: African Male

Acting -Director for Corporate Services: African Male

Director for Youth Economic and Social Development: African Female

Director for Infrastructure Development and Maintenance: African Male

It worth noting that a greater percentage of the Staff at middle management and lower levels  also  are mostly from previously disadvantaged communities.

### C3.2. Organisational Development

#### C3.2.1. Institutional Arrangements

Approval of key operational and strategic matters within the Municipality follows the following approval process, namelyDepartmental Meetings,MANCO, Portfolio Committees, and ultimately Council.

#### C3.2.2. Powers and Functions

Mayor

The Mayor is the chair of the Full Council and is also responsible for overseeing the functioning of the municipality in partnership with administration and duties of the Ward Committees.

Full Council

The Mpofana Local Municipality is a category B municipality as established in terms of Chapter 2 of the Municipal Structures Act 1998. The Municipality functions under a plenary executive system combined with a ward participatory system. The political leadership of this Municipality consists of seven (7) Councillors of which four (4) are Ward Councillors and the remaining three (3) are Councillors elected as Proportional Representatives of their political parties. The full council has powers to take executive decisions and delegate functions.

The Council has in total 9 seats; 7 seats for the ANC, 1 seat for the DA and 1 seat for the IFP. The Mayor is both the Mayor and Speaker of the Council, The Chief Whip who is a with a Chief whip who also serves as a Ward Councillor. Below are the names of Councillors and the Positions they hold in the governance Structures within the Municpality

mpac

MPAC continues to play an oversight role on behalf of Council, MPAC has through the COGTA’s support received extensive training so as to be fully equipped to deal with their oversight role. They are responsible for tabling the annual report to the Council and for providing comments and making recommendations to the Council. They are also empowered to look closely on public affairs in the Municipality under the authority of Council.

Portfolio Committees

Council Portfolio Committees are structured as per national guidelines and meet once a month. Issues requiring Council resolution are raised for deliberation at portfolio committee meetings. Recommendations are then made to the full Council.

The following are the Mpofana Council Portfolio Committees:

Youth, Economic and Social Services Directorate

Infrastructure and Maintenance Directorate

Budget and Treasury Directorate

Corporate Services Directorate

Management Committee (MANCO)

MANCO is chaired by the Municipal Manager and consists of the Directors of the four municipal departments and considers issues relating to the strategic issues of the said departments and makes recommendations to the relevant Portfolio Committees depending on the matter.

C3.2.3. SEE ATTACHED Organisational Structure / Organogram

The Organogram for the year under reviewhas been approved. Consultation with the Labour was done and all stakeholders are in agreement with the approved organogram. It has gone to the Portfolio Committee which has noted it and the Council which has approved it.

Overview

Mpofana Municipality consists of four departments each managed by a Director (section 56 managers) who report directly to the Municipal Manager. The functions of the Municipal Manager and each of the four departments are outlined below, Mpofana has approved its organogram for the 2017/18 Financial Year at a Council Meeting. The approved organizational structure is aligned to the long-term of the Municipality.Out of the 5 Section 57 posts, 3 have been filled. The Municipality lost its Chief Financial Officer just before the end of the Financial year (2016/17). The post has since been advertised including the post of the Corporate Services Director. These 2 posts however have acting appointments which will ensure that the organization is able to meet its strategic goals.

Office of the Municipal Manager

The Municipal Manager is responsible for the following strategic issues:-

The formation and development of an economical, effective, efficient and accountable administration.

The management of the municipality’s administration in accordance with the legislation applicable to the municipality,

The implementation of the municipality’s integrated development plan,

The management of the provision of services to the local community in a sustainable and equitable manner,

Manage the communications between the municipality administration and its political structures,

Carry out the decisions of the structures and functions of the municipality,

To administer and implement the municipal By-laws and other legislation,

Implement national and provincial legislation applicable to the municipality, and

Internal Audit and Risk Management.

Budget and Treasury Office

The Finance Department provides financial control, support and guidance to all other departments within the municipality on financial related matters. The following are the strategic issues that the department deals with:-

Financial planning and reporting

Design and implementation of internal controls

Development of financial policies

Maintenance of financial records

Revenue collection

Supply chain management

Management of Municipal Stores

Financial Interns Development

MFMA Compliance

Payroll administration

Financial planning and reporting

Corporate Services

The Corporate Governance department is responsible for the following key strategic issues:-

Human Resources Management and Development

Performance Management

Policies, Processes and Procedures

Labour Relations

Recruitment and Selection

Job evaluations

Training and Development

Compliance with legislation

Enforcing by-laws

Disaster management

Offices and buildings maintenance

Legal and Estate

Hall Bookings

Events Management and Communication Strategy

Management of Ward Committees

Fleet Management

Secretariat

Information and Communication Technology Administration

Support the mayoralty and council activities

Youth, Economic &Social Services

The Youth, Economic and Social Services department is responsible for the following key strategic issues:-

To create and ensure a conducive environment for Economic Growth

To promote and ensure coordinated land use planning and

To identify specific development activities to empower women, in

To promote road Safety and Traffic

To ensure development and implementation  of the Youth Development Strategy

To ensure improved and adequate access to educational facilities

To ensure all communities have access to basic community facilities

To promote sound Environmental Management practices

To promote access to arts and culture opportunities

To encourage participation in sporting codes for development

Technical Services

The Infrastructure Development and Maintenance department is responsible for the following key strategic issues:-

Infrastructure planning which includes

Infrastructure Budgeting and Management

Project and asset management

Contracts Management

Catchment, and River management

Storm Water Management

Waste Management

Infrastructure Maintenance

Provision of Basic Services.

Electricity

Infrastructure Planning

Provision of sustainable housing

#### C3.3 Municipal Institutional Capacity and Status of Critical Posts

The municipality has filled 3 out of 5 s57 positions, namely the Municipal Manager, the Technical Director, the Social and Community Director Services. There are 2 acting appointments in the Senior Managers level, namely the Corporate Services and the Chief Financial Officer. All the Section 56 Managers post are to be advertised since most of them are coming up in August. The Municipality has gonefurther to beef up its middle Management by filling the post of Human Resources, Manager Internal Audit and Manager IDP & PMS. The Manager LED& Tourism has also been advertised and is to be filled soon.

The VACANCY RATE

ThE VACANCY RATE IS 33%, but this is to be reduced since there are over 9 posts that have been advertised, this will help bring down the vacancy.

#### C.3.2.5. Human Resouce Development

Skills Shortages

The municipality has embarkedon a Workplace Skills Audit which will assist in the identification of the required trainings to be undertaken. This exercise will also give the Municipality a clear direction of the required scarce skills resources to be acquired in order to achieve its mandate. The findings of the Skills Audit have been brought to the attention of Council. Through the WSP the shortages identified are to be addressed.

Trainings

The municipality has conducted a number of trainings internally and externally. Future training needs will be informed by the Workplace Skills Audit Report, for the year that is upon us. It is worth mentioning that in the 2014/15 financial year the entire Finance Staff were trained on MFMP, a course that Treasury has labelled compulsory for all Finance Staff and Senior Managers.

Capacity Building

It is worth mentioning that Mpofana Local Municipality prepared its annual financial statements in-house, This was as a result of a capacity building initiative that saw a few individuals attending the course which would in turn capacitate them to prepare the Annual Financial Statements in-house. This task was normally done by external service providers. The skills audit will without any hesitation help in identifying more gaps and where there’s a need to capacitate the workforce this will take place. If more staff developmental needs are identified this will be addressed through the LGSETA and the relevant SETAs and Training Institutions, while the District’s support which has come in handy previously will also be pursued.

Shared Services

Mpofana LM has shared services arrangements with sister Municipalities within the District on Town Planning. An example is Shared Service Centre which is at uMngeni Municipality which specifically deals with GIS, Mpofana also benefits from the centre.

employment equity plan

All appointments are made in line with the approved Employment Equity Plan; It is for this reason that most of our employees are previously disadvantaged individuals. The Employment Equity plan is reviewed annually at Mpofana as recommended by the new Council.

Human resource strategy

This policy is developed and helps the Municipality in selection and retention of the employees. The Human Resource Strategy was outdated but has since been reviewed by the new Council. The appointment of the Human Resources Manager has seen the development of some positives within the HR Department, as Workplace Skills plan is implemented and all HR policies are being strictly adhered to by the administration.

C.6.4 HR Related Policies

The following Human Resource related Policies are in place:

| Name of Policy | Adopted (Yes/No) |
| --- | --- |
| Human Resource Strategy | YES |
| HR Policy | YES |
| Recruitment Policy | YES |
| Selection Policy | YES |
| Retention Policy | YES |
| Exit Policy | YES |
| Workplace Policy on HIV/AID | YES |  |
| Code of Ethics for Municipal Staff | YES |
| ICT governance Framework and Strategy | YES |
| Compliants Management Policy | YES |
| Overtime Policy | YES |
| Employment Equity Plan | YES |
| Workplace Skills Plan | YES |

The table below indicates the Human Resource related Policies, Date of Review and the implementation thereof.

| Name of Policy | Date of Adoption/ Review | Implementation of the Policy |
| --- | --- | --- |
| Human Resource Strategy | 30 March 2017 | Fully Implemented |
| HR Policy | 30 March 2017 | Fully Implemented |
| Recruitment Policy | 30 March 2017 | Fully Implemented |
| Selection Policy | 30 March 2017 | Fully Implemented |
| Retention Policy | 30 March 2017 | Fully Implemented |
| Exit Policy | 30 March 2017 | Fully Implemented |
| ICT Governance Framework and Strategy | 30 March 2017 | Fully Implemented |
| Complaints Management Policy | 30 March 2017 | Fully Implemented |
| Overtime Policy | 30 March 2017 | Fully Implemented |
| Employment Equity Plan | 30 March 2017 | Fully Implemented |
| Workplace Skills Plan | 30 March 2017 | Fully Implemented |

As depicted in the above table, It should be noted that Mpofana has an approved Human Resource Strategy which seeks to help in guiding the allocations, systems and procedures in dealing with Human Resources. Furthermore an employment Equity plan is in place and its implementation has been a smooth one, this is further evidenced by the fact that all Section 56 Manager are from previously disadvantaged groups.

C.3.6 Information Communication Technology

Mpofna Local Municipality has an ICT Framework in place as can be seen in the above table, Not only does the framework exist, The administration sees to it that it is indeed implemented. The Auditor General during their audit found Mpofana’s ICT framework to be compliant with both the national and international standards, however a few exceptions were raised which have subsequently been addressed as can be seen below.  Mpofana has its own domain, which ensures faster emails internally between staff members, In the past an internet firewall did not exist, but of late this is in effect and exists. Mpofana now has an antivirus installed on all its computers so that risk of computer crashing is minimized. During a strategic planning session, the Municipality has reviewed its ICT Risk Register. The above serves as evidence in how seriously ICT is viewed in Mpofana, all strides are made to ensure that our ICT framework and policy is compliant with national and international standards, while implementation of the adopted ICT policy is being monitored closely by the Corporate Services Department. The ICT policy has recently been reviewed and a council resolution to this regard is in place.

### C3.7Municipal Transformation & Organisational Development: SWOT Analysis

CHALLENGE

High Staff Turnover

Sense of entitlement for local community to be employed in the Municipality (Possible Protest)

Worsening Staff Morale

Inability to attract high-skilled staff

Readily available labour source

A pool of Graduates

Government Legislations

Government Departments support with providing Warm Bodies

Usage of ICT to automate and enhance internal processes

Inadequate systems and processes

Lack of controls and monitoring systems;

Skills shortages

Financial constraints;

Poor implementation of projects and strategies;

Inadequate organisation capacity;

Harmony between Administration, political leadership and Labour

Strong Intergovernmental Relations;

Middle-Management Appointments

MFMP Training to all finance Staff

Frequently held MANCO

INTERNAL

EXTERNAL

THREATHS

OPPORTUNITIES

WEAKNESS

STRENGTH

ENABLER

5

C4. Basic Service Delivery

### C4.1.1Water and Sanitation

Water and sanitation is one of the most basic needs in our society and a major municipal developmental mandate within the Republic of South Africa.

The Mpofana Municipality still has a major backlog in terms of water and sanitation in certain municipal areas.  Ward 2 and 4 are most affected by lack of access to suitable water and sanitation. These two wards are mostly rural in nature with a fragmented household landscape and this could be a contributing factor in the slow progress of service delivery in these areas.

In the 2008/2009 IDP, the municipality handed over the water and sanitation functions to the uMgungundlovu District Municipality which is now the Water Services Authority (WAS). The construction of the Spring Grove Dam will assist in curbing the water shortages experienced in Bruntville, A project by Umngeni Water is to be implemented which will see the construction of a pipe-linefrom Roseta to the Bruntville area Ward 1,3&5and hopefully be expanded in areas of great need in Ward 2 and Ward 4, as planned in the UMDM’s IDP for the year under review.

Figure 1: Piped Water per ward within the municipality

The majority of households in the municipality forms part of a water scheme.  However, there is still a significant amount of households that do not have access to water or use water sources that might compromise their health.

Figure 2: Water sources

The majority of households have access to piped water within their dwelling or yard.

Figure 3: Piped water

The uMgungundlovu District Municipality is the Water Service Authority

Indigent Households Receive Free Basic Water Supply and about 40% of Households in Mpofana LM receive 6 KL free water per month

The district municipality is currently conducting a water meter audit in the Mpofana LM

The next stage will be installing water leak detection systems and pressure management

Mpofana LM has a water demand of 7 -8 Ml/d

The UMDM is currently rated as having one of the highest non water revenue losses in KZN due to ageing infrastructure, lack of or inaccurate metering

The extent of water losses within Mpofana LM is unknown

There are no known water conservation strategies in the Mpofana LM

Alien Plant Control and Rainwater Harvesting are High Priority Projects in the Mpofana LM

UMDM spent R1,5 mln in 2012 to install a sludge dewatering plant to improve performance of  Mooi River Waste Water Works (WWW)

Design Capacity of Mooi River WWW – 5Ml/d

Annual Average Daily Flow of Mooi River WWW – 4.09Ml/d

Peak WWF on any day – 10 Ml/d

Effluent Quality Compliance – Poor Microbiological Compliance

DWA has approved R2,9 mln for  a planning study to be undertaken to look at condition of bulk sewer pipelines and the feasibility of upgrading or building a new Waste Water Works in Mooi River

The availability of toilet facilities has been no exception in the improvement of service delivery since 2001 within the Mpofana Municipality.  There has been an approximately 16% increase in the number of flush toilet that are connected to a sewerage system with a significant drop in the bucket system. These are mostly located in Ward 1 and Ward 3 which are the urban centers. Ward 2 with the Rosetta village also forms part of the areas with flush toilets.

Figure 4: Sanitation

### C4.2. Energy Sources

There has been a substantial improvement in the percentages of households that use electricity for lighting purposes. The majority of the households using electricity are located in the urban centers of the municipality, more especially Mooi River, Bruntville and Rosetta.  The use of candles has been proven to have hazards effects and the development of the Electricity Sector Plan within the current IDP will properly address areas that require electricity for lighting.  Within the current context of the electricity crisis in South Africa, it would be

imperative for the municipality to also promote alternative sources of electricity hence addressing the shortages.

It cannot be denied that major backlogs exist in as far as access to Electricity is concerned, that is why 5 Million Rand has been set aside for the Electrification Project which will aid in dealing with these backlogs in the affected wards (Ward 2 and 4).  The Municipality currently does not have an Energy Sector Plan but this is receiving the attention it deserves. This is to be developed soon seeing that a lot of houses will be electrified.

The Municipality services Ward 1 and 3 with Electricity, whilst Eskom services mostly rural areas Ward 2 and 4, The Municipality purchases the electricity from Eskom which in turn sells to the Community and Industries in the Mpofana Area.

Map 12: Electricity for lighting per Ward

According to the above map major backlogs are in Ward 2 and 4 with regards to electricity, An effort is being made to deal with the backlog. 380 Households are due to benefit from the Electrification Project as per the 2016/17 budget, with a total number of 70 houses already electrified.  which will go on in the 2017/18 year.  Some houses have already been electrified so the project goes on as planned.

Map 13: Electricity Network

M

The above Map shows that central to Mpofana, the Electricity network is available, but as you move away from the Centre of the town, Electricity network is lacking, that is why an electrification project which is funded by the Department of Minerals and Energy is currently being implemented. Going forward, and  in the 2016/17 financial year over 360 households will benefit from the project.

The t

There has been a substantial improvement in the percentages of households that use electricity for lighting purposes when comparing the Census 2001 against the recently conducted 2007 Community Survey (See Table Below):

Energy / Fuel for Lighting

| Energy/Fuel | Census 2001 | Census 2007 | Census 2011 |
| --- | --- | --- | --- |
| Electricity | 53,4 | 71,9 | 72.0 |
| Gas | 0.3 | - | - |
| Paraffin | 0.7 | 1.4 | 1.4 |
| Candles | 44.8 | 25.8 | 26 |
| Solar | 0.3 | 0.2 | 0.2 |
| Other | 0.5 | 0.7 | 0.6 |

The table below, shows that the majority of the households using electricity are located in the urban centers of the municipality, more especially Mooi River, Bruntville and Rosetta.  Within the current context of the electricity crisis in South Africa, it has been seen imperative for the municipality to promote alternative sources of electricity; hence solar system project has been concluded in the Town View Area, there are plans to expand the project to include Bruntville Township.

Almost 56.5% of the total households in the Municipality make use of wood for heating purposes.  The majority of these households are located in the rural part of the municipality.  This fact raises a need for more electricity supply within these areas of the municipal area.  This is an indication that natural forests are depleting, which poses downstream environmental concerns. More electricity supply is a strategy towards addressing this issue.   An application was lodged with Department of Energy for the electrification project in the 2014/2015 financial year.

T

| Ward | Electricity | Gas | Paraffin | Candles | Solar | None | Total |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ward 1 | 2833 | 6 | 2 | 162 | 4 | 18 | 3025 |
| Ward 2 | 2572 | 11 | 11 | 696 | 3 | 9 | 3302 |
| Ward 3 | 1948 | 1 | 36 | 104 | 2 | 1 | 2092 |
| Ward 4 | 165 | 1 | 6 | 1835 | 5 | 20 | 2033 |
| Total | 7519 | 19 | 55 | 2797 | 14 | 49 | 10452 |

The table above shows the Backlogs that exist in Ward 2 and 4 in so far as the Electricity is concerned. Major Backlogs exist in Ward 2 and

Ward 4. The electrification project is to decrease the numbers and thereby address the backlogs that be.  More candles are being used in Ward 4, meaning that the backlogs are much higher in Ward 4 than in Ward 2.

Figure 5: Access to electricity for lighting

The current status with regards to energy in the municipality is as follows:-

Mpofana Municipality – Holder of Electricity Distribution License for Mooi River (Ward 1 and 3)

Eskom supplies rural areas of Mpofana LM – less than 10% of HH

Electricity demand being reduced by fitting energy saving light bulbs and solar water heating

No free basic electricity is provided at the moment, but in the year that is upon us there is a plan to address this, by reviewing the Indigent Register.

The table above reflect that the municipality has a challenge to provide electricity to rural areas especially ward 4.

At the moment an Operations and Maintenance Plan is still being developed, once the funds to fund the Maintenance plan is made available this will be implemented.

Power lines are regularly checked by our Senior Electrician and where cables need to be changed; this is done with the little resources at our disposal.

There is a need to employ an electrical engineer; this has been catered for in the reviewed organogram since Mpofana is a holder of an electric licence for Ward 1 and 3 respectively.  The Energy/ Electricity Sector Plan is currently being planned and will e

### C4.2Solid Waste Management

The Municipality is responsible for waste collection. There has been a 30% increase in household refuse collection services since 2001 and an increase in household refuse since 1996. There is a Compactor Truck that was purchased in 2012. Due to the increasing number of the households, 2 new compactor trucks will be procured in the year under review.  There is a need to provide refuse collection services to areas that are 40km to 80km from Mooi River CBD. The lack of a Landfill Site in Ward 2 and 4 poses a serious threat to those communities. There is a need to develop another Landfill site.

### 4.2.2.2 SOLID WASTE STATUS

Figure 6: Waste removal

Although the majority of households have their refuse removed on a regular basis, there are still significant amounts that have their own refuse dump, which poses a health hazard to the citizenry of Mpofana.

### Waste Disposal Site 4.2.3

Mpofana has a Landfill site that is serviced by Mpofana, The Municipality’s Landfill site has been in existence for a considerable amount of time, a business plan was prepared for a new landfill site, however the land issue remains a challenge in this regard. The Municipality hires a compactor which helps in burying the dirt. It is also worth mentioning that the Municipality has looked at other options with regards to waste management and in line with its Waste Management Plan.

There has been a proposal from prospective investors, where an initiative to  convert waste to energy has been tabled, so as to better manage our waste and to deal with the energy crisis facing our country. This proposal has been well received Another proposal has come to the attention of the Municipality by a

### C.4.2.4 State of Waste Disposal site

The Waste Disposal site is has been around for over 30 years, and will reach the end of its life span in 2030. The landfill site is licenced and Mpofana holds the licence.

### C.4.2.5 IWMP ADOPTION AND IMPLEMENTATION

The Integrated Waste Management Plan (IWMP)has been tabled to Council and we are proud to announce that it was prepared in house. This was promted by the MEC’s comments in as far as the 2015/16 IDP is concerned. Mpofana has also   Through the EPWP Programme trained unemployed Graduates to lead the process of the sustenance of the Landfill Site wherein communities are taught about recycling and a better management of their waste. The Municipality has also come into partnership with Khabokhedi- Which is a Youth in Waste Programme which is in line with the Integrated Waste Management Plan (IWMP), Khobokediassists in educating the community about recycling. Another project has recently been launched a recycling project that is led by community members.

### 4.2.7 DIVERSION OF WASTE INITIATIVE(S)

The Municipality provides some assistance in the recycling center which is monitored closely by the Municipality in consultation with the Wildlands Conservation Trust.

The project was founded by Sbusiso Dladla in 1997 because there were no employment opportunities in the area, a lot of people including himself were unemployed. So rather than waiting on the government, he decided to start this project with the aim of employing a few people that were unemployed thereby play his role in alleviating poverty in the community and putting food on their table. Also it was to create employment for people that were unemployed.

Since the Project started it has created 15 jobs (2 males, 11 females and 2 Security Guards).

The community seems to ignore the call that has always been made to recycle. To the community’s advantage however, a recycling group which was founded by a Youth member of the community is in effect. The project’s location is the landfill site, where over 10 women are employed, including 2 males. The project has suffered due to theft of their recycled goods. Once the products are recycled they sell their products to different companies some are as far as Johannesburg.  One of the projects challenges is the fact they don’t have TLB, The buyers also seem to demand lower prices.

Challenges of the Project

- No  Electricity since the project started this hinders the appointment of more people due to non functional of the other equipment that are utilized in this project

- There is no TLB which is quite instrumental in transporting waste that needs to be recycled.

Achievements of the Project

Bailing machine  has been secured;

Hired a car to transport waste;

Waste is optimally diverted

Community has been made more aware of waste management

A buy back centre is being established

### C4.3. Transportation Infrastructure

The primary transport route within the municipality is the N3 Route that traverses and links Pietermaritzburg and Durban to the south and ultimately the Gauteng Highveld to the north and north-west. The Roads Network Map shows that the largest majority of households in the municipality enjoy access to roads at regional, district and local level.

The Municipality is strategically located in relation to national, provincial and regional routes. Major connector roads within the municipal area include the following:

N3 which is a national corridor.

R103 (P1-8) which adjacent the N3.

R622 (P14-2) to Greytown and beyond.

P164 to Drakensberg.

P175 to UMtshezi

There are a number of regional distributor roads spread relatively even throughout the municipal area, improving the relative accessibility of the majority of settlements and households in the municipality. Many households are also serviced through lower order, district or local, roads. The map does not indicate the condition of the roads in terms of maintenance and quality.

The Road Infrastructure Strategic Framework for South Africa (RIFSA) classifications indicates a major dependency on lower order access roads for most of the residents within. Due to the remoteness of these roads, as well as the limited funding for infrastructure maintenance, maintenance of these roads might pose a problem in future.

It is true that the conditions of the roads in the Mpofana area are bad, the roads are characterised by potholes, no drainage systems and are unmaintained due to limited funding that the Municipality has been receiving.  The Municipality seeks to address this by having 4 capital projects split between the 4 wards so as to rehabilitate the roads, namely Sthembiso Main Road, Mangaung Access Road, Tendela Access Road and Mooi-River Testing Routes. There are projects in place which are aimed at dealing with the bad road conditions that are in Mpofana. Also Heavy vehicles have been prohibited from entering certain areas of Mpofana due to their size and the inability of our roads to handle heavy vehicles.

### C.4.3.3 PROVISION OF NEW ROADS

The Municipality is responsible for new roads, the Municipality’s capital budget has made provisions for these new roads.

| WARD | NEW ROAD NAME / FACILITY |
| --- | --- |
| 1 | Mpofana Testing Route |
| 2 | Nkandla Road, Rondebosch Road |
| 3 | Sthembiso Cabazini Road |
| 4 | Mgqula Access Road |
| 5 | Mangaung Access Road |

### C.4.3.4 Operational and Maintenance Plan

A provision of new roads and facilities as indicated above has been made. There is an Operational and Maintenance Plan for existing and new roads and public transport facilities.

### C.4.3.5 Integrated Transport Plan

The Municipality is not responsible for Integrated Transport Plan

Map 14: Road Network

The Municipality is responsible for major access roads that are not maintained by Department of Transport.   Due to very bad weather conditions we have experienced over the year, some roads have dilapidated so much.  Through many years of use without maintenance or hardening, many have developed in deep dongs where storm-water continuously deepens them.  However the municipality, where it can has repaired some under very tight budgetary constraints. The Roads in Ward 2 and 4 that need attention have been identified.

The business plan has been drafted to seek for funding to resurface most of our roads especially those that surrounds our town.

### C4.5. Access To Community Facilities

The IDP has 2 authorized cemetery sites, the table below indicates where there are backlogs, needs and priorities for all community facilities over and above the cemetries.

Below the Graph shows Communities access to Facilites in the Mpofana Area, This is broken down per ward and the number of those facilities per ward.

### C.4.5.2 Status, backlogs, needs and priorities

| SERVICES | TOTAL NUMBER MPOFANA | WARD 1 | WARD2 | WARD 3 | WARD 4 | WARD 5 |
| --- | --- | --- | --- | --- | --- | --- |
| Hospital | n/a | n/a | n/a | n/a | n/a | n/a |
| Clinics | 4 | 2 | 1 | 1 | n/a | n/a |
| Mobile clinic | 1 | n/a | n/a | n/a | 1 | 1 |
| Schools | 41 | 4 | 23 | 4 | 10 | 2 |
| Libraries | 2 | 1 | n/a | 1 | n/a | n/a |
| Police station | 1 | 1 | n/a | n/a | n/a | n/a |
| Cemeteries | 2 | 1 | n/a | 1 | n/a | n/a |
| Dump site | 1 | n/a | n/a | 1 | n/a | n/a |
| Soccer fields | 3 | 2 | n/a | 1 | n/a | n/a |
| Netball fields | 1 | n/a | n/a | 1 | n/a | n/a |
| Rugby fields | n/a | n/a | n/a | n/a | n/a | n/a |
| Swimming facilities | n/a | n/a | n/a | n/a | n/a | n/a |
| Basketball facilities | 2 | 1 | n/a | 1 | n/a | n/a |
| Cricket facilities | n/a | n/a | n/a | n/a | n/a | n/a |
| Boxing facilities | n/a | n/a | n/a | n/a | n/a | n/a |
| Gymnasium facilities | n/a | n/a | n/a | n/a | n/a | n/a |
| Halls | 5 | 1 | 2 | 1 | 1 | n/a |

Map 13: Clinics in the Mpofana area

Schools in the Mpofana area, The Department have Education is looking into constructing a new Primary School due to the fact there is overcrowding in Bruntville Primary School.

The above table shows the community’s access to social amenities per ward.

The Municipality interacts with some Government Departments in providing the services, Department of Health Provides the Clinics, with the Department of Sports and recreation providing recreational facilities, this is true of the newly launched Bruntville Stadium which was constructed by the Department of Sports and Recreation.  Department of Arts and Culture which has since had a partnership with Mpofana Municipality is responsible for funding the Liibraries and servicing the Libraries by providing books, It cannot be denied that Recreational Facilities are a priority in Ward 2 and 4 as there is a need for such facilities as reflected in the table above which shows access to facilites.

### C4.6. Human Settlements

C.4.6.1 Housing Developer for Human Settlement

The Municipality is classified as a Housing Developerfor Human Settlements, in that the Municipality is a signatory on Housing Developments in the tripartite agreement that is signed between the Municipaility, Human Settlement and the Implementing Agent.

### C.4.6.2 Housing Sector Plan

The Municipality has an approved Housing Sector Plan, but seeing that a new Council has recently been installed calls for an urgent review of the Housing Sector Plan. The approved Housing Sector Plan comprises of priority Housing Projects for all the 5 wards.

Below are Projects that have been funded by Human Settlement (Housing Projects) The table depicts the number of units in each of the areas concerned. The number of Units per area are the Units to be built, Once the projects are completed this will affect settlement patterns as some families are housed in very small shelters yet with so many members.

### C.4.6.5 Existing Housing Project

| Project name | Ward | Units | 2015/16 | 2016/17 | 2017/18 | 2018/19 | 2019/20 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ekujabuleni | 3 | 120 |  | R10 300 000 |  |  |  |
| Ebuhleni | 4 | 100 | R8 000 000 |  |  |  |  |
| Phumlas | 1 | 400 | R19 200 000 |  |  |  |  |
| Bruntville | 3 | 120 |  |  |  | R3000 000 |  |
| Craigieburn | 4 | 850 |  |  |  | R6 300 000 | R6 300 000 |
| Tendele | 2 | 250 |  |  |  |  |  |
| Rosetta | 2 | 92 | R230 000 |  |  | R3 000 000 | R3 600 000 |

1932 Housing Units as per the Housing Sector Plan.

### 4.6.7 Mechanism for Co-ordination of Housing Developments with Service providers

Housing Projects are funded by Human Settlements, The co-ordination however lies with Mpofana Local Municipality. The co-ordination of all current and planned Housing Projects takes place through Think Tanks meetings which are attended by Mpofana’s Officials, Department of Human Settlement, The Implementing Agents and the Service Providers. In these Think Tank meetings, challenges are raised and amicable solutions as per the different housing projects are made. Mpofana has been pro-active in the implementation of some of Housing Projects, where upon Section 32 appointments have been made where some service providers performed badly and slowly. Mpofana is better suited to co-ordinate the Housing Developments this is also complemented by the fact that the Housing Unit has a dedicated Officer and a Director who oversees Housing as well. It is through our Housing Officer and through War-Rooms and Operation Sukuma Sakhe and IDP Consultative meetings that we have been able to identify the backlogs that exist in Mpofana Local Municipality in as far as housing is concerned. Co-ordinated and joint effort is also needed from the District Municipality which is tasked with providing Bulk Services to the funded Housing Projects and planned Housing Projects.

| Housing Needs as per Housing Sector Plan | Type of Settlement | No. Of units | WARD |
| --- | --- | --- | --- |
| Randebosch | Urban | 60 | 2 |
| Inkululeko | Rural | 60 | 4 |
| Middelrus | Rural | 650 | 4 |
| Riversdale | Urban | 82 | 1 |
| Rockydrift | Rural | 650 | 4 |
| Hidcote | Rural | 100 | 2 |
| Bruntville | Urban | 200 | 3 |
| Phofini | Rural | 100 | 1 |
| Scottfontein | Rural | 100 | 2 |
| Phumlass | Urban | 800 | 5 |

C.4.7.1TELECOMMUNICATION

Telecommunication is vital in this technological and ever evolving world. Communication proves vital in the dissemination of information to the citizenry. Mpofana realizes the need to have a well oiled telecommunication network. Things like email, website, blogs and facebook pages are means by which the Municipality is able to communicate to the public. Telephones are also vital in this regard. According to Stat SA, the Mpofana Citizenry has access to cell phones, although in some wards there are still issues with cell phone networks. MTN and Vodacom have been approached for the areas which lack bulk telecommunication network. It is for this reason that a Cell-tower has been erected in Ward 2, which will help service Summerhill Studs Farm which falls under Mpofana Local Municipality and was previously not reachable via cellphones.  Stat SA during the 2011 census has confirmed that there is a rise in relation to access to telecommunication facilities in Mpofana.

### HOUSEHOLDS WITH ACCESS TO TELECOMUNICATIONS

As stated in the aforementioned paragraph, there has been an increase in the number of households with access to telecommunicaitons in the municipality. This is evident by the number of people with access to cellphones as concluded by Stat SA. In 2001 22% percent of households had access to cell phones, while in

2011 the figure seems to have increased to 75%. Only 15% of households have access to computers and internet. That is why the Municipality has ensured that the Youth Centre has free internet for the youth. The number has not increased much from the 2001 census. The reason for this decision was based on the Census count which highlighted that over 54% of Mpofana population is youth. More applications are still being made for more Cell-towers so that a lot of people would be able to communicate. It has been noted that the fact that only a few people have access to the Computer, means that computer literacy is on a low in Mpofana, hence there is a need to make the youth centre more accessible.

### C4.8. Infrastructure Development Projects

The projects listed below respond to all the infrastructure requirements of the municipality across all of the four wards and will not only benefit the infrastructure needs but also create employment opportunities for the local communities. If these infrastructure development projects are funded, they will assist the municipality to have access to many areas which the Municipality currently has difficulty accessing due to conditions that prevail, like the road conditions which make it difficult to deliver municipal services in some ares. The projects listed below, even though not currently funded, are informed by community needs and priorities identified through the ward committee structures and through a series of community meetings in developing the IDP. The table below summarises the list of needs identified during our Community Based Planning engagements which took place in February 2017, this was followed by an IDP engagement which took place in April 2017.

| Roads, Water, Electricity and Infrastructure Projects | Ward | Length & Project Scope | Estimated Cost | Locality | Implementing Agent/Entity |
| --- | --- | --- | --- | --- | --- |
| Upgrade of CBD Roads | 1 | 8 km roads Rehabilitation of Street surface Storm water drainage system Signage, Upper Town Road (Phase 1&2). | R20M | Central business district of Mpofana LM | Mpofana LM Dept of Transport |
| Construction of Ward 2& 4 Roads | 4 | Earth works Road layer Works Storm water drainage system Signage | R 150 000 | Muden, Nyamvubu, Vovonya, Mathwanya Birdspruit, Cranham; Rocky drift; Emdubuzweni, Scotfontein Gravel Roads,Phofini Road, Nkomba Road, Tendele Road, Rondebosch Gravel Road. | Mpofana Municipality |
| Mooi River Traffic circle and Island beautification Project | 1 | Traffic circle upgrade and Land scaping | R300,000 | Central business district of Mpofana LM | Mpofana Municipality Dept of Transport and COGTA |
| Beautification of Rosetta Town | 2 | Upgrade of Infrastructure | R3M | Central business district of Rosetta | Department of Transport |
| Upgrade of Shiyabazali and Bruntville Main Road residential Roads | 3 | Earth works Road layer Works Storm water drainage system Signage | R4.5M | Shiyabazali Township | Mpofana Municipality |
| Fencing of Schools | 5 | Summerhill and Hidcote | R1M | Summerhill and Hidcote Schools | Department of Education |
| Nyamvubu and Rosetta Bus Shelter | 2,4 &5 | Construction of Bus Shelter in the Rosetta Area | R50, 000 | Roseta | Mpofana Local Municiapality |
| Upgrade of Bhumaneni Stadium | 4 | Earthworks Fencing Grassing Multi-sport facilities Grand stands Change rooms & Toilets. Parking | R4.5M | Bhumaneni | Local Municipality District Munic Dept. of sport & Recreation |
| Upgrade of Muden Stadium | 4 | Earthworks Fencing Grassing Multi-sport facilities Grand stands Change rooms & Toilets. Parking | R4.5M | Muden | Local Municipality District Munic Dept. of sport & Recreation |
| Upgrade of Rietvlei Stadium | 4 | Earthworks Fencing Grassing Multi-sport facilities Grand stands Change rooms & Toilets. Parking | R4.5M | Reitvlei | Local Municipality District Municipality Dept. of sport & Recreation |
| Upgrade of Mooi River Stadium | 1 | Earthworks Fencing Grassing Multi-sport facilities Grand stands Change rooms & Toilets. Parking | R 500 000 | Mooi River | Local Municipality District Municipality Dept. of sport & Recreation |
| Household Electrification Project | 2,4&5 | Bulk supply of electricity network Associated Infrastructure Reticulation network Household connections | R36M | Muden, Nyamvubu, Birdspruit, Cranham; Rocky drift; Emdubuzweni; Milderus; Vovonya, Hidcote, Rondeboshc | Dept of Mineral & Energy Eskom |
| Household Electrification Project | 2 | Bulk supply of electricity network Associated Infrastructure Reticulation network Household connections | R36M | Scotsfontein; Rossetta; Mngwenya ; Rondebosch farm | Dept of Mineral & Energy Eskom |
| Construction of Creche | 2,4& 5 | Construction of a Creche to house children |  | Rondebosch, Phofini, Sgubudu, Nyamvubu. | Department of Education |
| Bruntville Gardens | 1& 3 | Community Gardens | R1M | Bruntville Township | Department of Agriculture and Mpofana Local Municipality |
| Upgrade of Electricity Network Project | 1 | Upgrade of Bulk supply of electricity Associated Infrastructure upgrade Reticulation network upgrade | R50M | CBD and Townships | Dept of Mineral & Energy Eskom |
| Upgrade of Phumlaas Residential Engineering Services- Roads, Water and Sewer and Housing | 3 | 8km Road Network - Surfacing Sewer reticulation upgrade Water Reticulation upgrade | R16M | Phumlaas Township in Mooi River | Human settlement dept. Mpofana Municipality |
| Town view Early Education centre | 1 | Construction of Early Childhood Centre | R5M | Townview | Mpofana Municipality |
| Townview/Bruntville Botanic Gardens | 1&3 | Establishment of a Botanical Garden | R2M | Bruntville | Mpofana Municipality |
| Upgrade of Mooi River Tennis Court | 3 | Revamping of Tennis Court | R0.4M | Bruntville | Mpofana Municipality UMDM Sports and Recreation dept. |
| Townview Indoor sport complex centre | 5 | Completion of Townview Sport Complex | R8M | Town view | Mpofana LM Human settlement dept. |
| Scotsfontein; Rossetta; Mngwenya ; Rondebosch farm | 2&4 | Road Construction | R30M | Scotsfontein; Rossetta; Mngwenya ; Rondebosch farm | Mpofana LM |
| Cranham Water Scheme | 4 | Bulk Water Supply | R5M | Cranham; | Mpofana LM |
| Mooi-MngeniTranfer scheme | 2 | Bulk Water Supply | R50M | Rossetta, UMngeni Localities | Umgungundlovu DM Umngeni water |
| Muden Water scheme | 4 | Bulk Water Supply | R5M | Muden | Mpofana LM |
| Emdubuzweni Road Mantainance | 4 | Rehabilitation of Road | R4M | Emdubuzweni | Mpofana LM |
| Middelrus | 4 | Road Maintenance | R2M | Milderus | Mpofana LM |
| Nyamvubu | 4 | Road Maintenance | R3M | Nyamvubu | Mpofana LM |
| KwaMqenula | 4 | Road Maintenance | R2M | KwaMqenula | Mpofana LM |
| Rocky Drift | 4 | Road Maintenance | R3M | Rocky Drift | Umgungundlovu DM |
| Vovonya | 4 | Road Maintenance | R3M | Vovonya | Umgungundlovu DM |
| Milderus | 4 | Road Maintenance | R2M | Milderus | Mpofana LM |
| Nyamvubu | 4 | Road Maintenance | R3M | Nyamvubu | Mpofana LM |
| KwaMqenula | 4 | Road Mantinence | R2M | KwaMqenula | Mpofana LM |
| Vovonya | 4 | Road Mantainence | R3M | Vovonya | Mpofana LM |
| Rocky Drift | 4 | Road Mentainence | R3M | Rocky Drift | Mpofana LM |
| Rossetta | 2 | Road Mantainence | R2M | Rosetta | Mpofana LM |
| Scotsfontein | 2 | Road Maintenance | R5M | Scosfontein | Mpofana LM |
| Tendele | 2 | Road Maintenance | R5M | Tendele | Mpofana LM |
| Rondebosch | 2 | Road Maintenance | R2M | Rondebosch | Mpofana LM |
| Mngwenya | 2 | Gravel Road Construction | R8M | Mngwenya | Mpofana LM |
| Upgrade reticulation network in CBD | 5 | Upgrade of Electricity Network | R10M | Bruntville | Mpofana LM |
| Development of Integrated Waste Management Plan | All | 6 months Project A planning document | R300 000 | Mpofana | Mpofana Municipality |
| Development of waste recycling plant | 1 | Establishment of waste recycling plant to ensure an environmentally friendly area | R1M | Mpofana | Mpofana Municipality |
| Upgrade of Solid waste Management Site | 1 | Selection of suitable site Environmental Impact Assessment Design of waste disposal site Construction for waste disposal site | R3M | Mpofana | Umgungundlovu District |
| Electricity Network and street light maintenance | 1&3 | Routine maintenance of network Repairs on electricity faults | R700000 per annum | CBD and Townships | Mpofana Municipality |
| Roads and storm water operation & Maintenance | 1&3 | Pothole filling and compaction Stormwater drainage cleaning Resurfacing of Streets | R1.5M | CBD and Townships | Mpofana Municipality |
| Solid Waste Management | 1&3 | Collection of refuse and disposal Maintenance of waste disposal site Plant & Equipment maintenance Supply of refuse bags | R4M | CBD and Townships | Mpofana Municipality |
| Maintenance of Municipal Buildings & Halls | 1&3 | Repairs on electrical faults Painting Brick works Surfaces Built –ins | R 3M | All Properties in the Municipal Boundaries | Mpofana Municipality |
| Phumlass Access Roads | 1 | Upgrade of Access Roads | R 20M | Upgrade of Access Roads | Mpofana Municipality |
| Riversdale Housing Projects | 1 | 82 Housing Units |  | Riversdale | Department of Human Settlement |
| 36 Town-View Houses, access roads and Drainage. | 1 | Construction of 36 Units for the beneficiaries that did not benefit from the Town-View Housing Project |  | Townview | Department of Human Settlement |
| Bruntville Abestos Housing Rehabilitation | 3 | Re-construction of Abestos Houses in the Bruntville Area |  | Bruntville | Environmental Affairs |
| Bruntville Library | 3 | Re-construction of Bruntville Library |  | Bruntville | Departmnent of Arts and Culture |
| Reconstruction of Gwala Park | 3 | Reconstruction of Gwala Park Houses which are too small. |  | Bruntville | Department of Human Settlement |
| Lakeview Housing Projects | 1 | Implementation of Lake view Housing Projects |  | Lakeview | Department of Human Settlement |
| Change of Abestos | 3 | Change of Abestos in the Bruntville area |  | Bruntville | Department of Human Settlement |

### C.4.9 Basic Service Delivery: SWOT Analysis

| STRENGTHS | WEAKNESSES |
| --- | --- |
| Constitutional Mandate to provide Free Basic Services Location of the Municipality High levels of improvement in the delivery of basic services EPWP Staff which complements the Municipality’s effort in Service Delivery Good understanding of the needs of the community Good understanding of the Community’s needs Staff management and leadership Implementation of Housing projects Technical Director position filled | Households in Ward 2 and 4 too scattered making it costly to provide the needed services Limited MIG Funding Lack of access of social amenities in ward 2 and 4 High level of vacancies Poor access roads Dilapidated infrastructure MIG reporting One compactor for Waste Collection |
| OPPORTUNITIES | THREATS |
| Government Department Funding Proposed conversion to smart metering Planned purchasing of Grader and TLB Proposed new-land fill site Completed Business plans for funding Proposed Conversion of Waste to Energy | Bad Road infrastructure Electricity Theft Low maintenance of Infrastructure Slow implementation of Water Projects Lack of co-ordination between the UMDM and Local Municipality Slow SCM processes resulting in poor service delivery One landfill site which services more than 5000 households weekly One compactor Illegal dumping which could cause health harzards |

## C5. Local Economic & Social Development Analysis

### C5.1. Local Economic Development Analysis

#### C5.1.1. Municipal Comparative & Competitive Advantages

the LED strategy

The current LED strategy has been reviewed to respond to the socio-economic challenges facing Mpofana Municipality, the LED Strategy was adopted in 2016 and is due for review in the 2017/18 financial year, this will be culminated by the staging of the LED summit. Internal resources have been used to review Mpofana LED strategy. Consultation with key stakeholders during the LED forum led into the development of a Local Economic Development strategy. In developing the strategy the following elements were taken into account:

Assessment and identification of the gaps in the existing strategy

Socio-economic analysis which includes figures on the rate on population,HIV/AIDS, unemployment and poverty prevalenceSpatial analysis in relation to National and provincial economic development priorities.

The District Municipality has currently reviewed its District Growth and Development Plan, It has been agreed between the uMgungundlovu District Municipality  and Mpofana Local Municipality that an alignment between the LED strategy and the District’s Growth and Development Plan should exist, Meetings to this effect have been held with the Local and District Municipality.

This therefore means that all precautions are taken to ensure that the Mpofana Local Municpality’s LED strategy is aligned to the Provincial Growth and Development Plan and the District’s Growth and Development Plan.

The review of the LED strategy was not done in isolation, but careful analysis of the Provincial Growth and Development Strategy was done to ensure alignment, the goals and plans as contained in the National Development Plan (Vision 2030) was also undertaken.

Monitoring and evaluation framework

In line with the Provincial Growth and Development Strategy and National Spatial Development Plan, the revised LED strategy directs stakeholders on areas that require coordinated economic investments. Private-Public Patnership is vital in the achievement of Mpofana’s LED goals and strategies, this much was made clear during our LED summit.

| Comparative Advantages | Competitive Advantages |
| --- | --- |
| Easy access to national (N3) and provincial (R103) carriage way. | A Vibrant Agricultural Sector that is well linked to the supply chain. |
| Abundance access to natural resources such as water, scenic beauty and other input resources such as human, electricity etc. | Mooi River town and its surrounding agricultural areas fall within Bio-resource Group (Central Midlands) that is classified as having 67% arable land with 47% of this land consisting of high potential soils. |
| Proximity to the Capital City of KZN and provincial government administration. | The moist midlands belt allows the area to be ideal for forestry development. |
| Land reform beneficiaries constitute a second high percentage of land ownership after private individuals. | The area is the origin of many streams and rivers and is thus ideal for the conservation of water resources. |
| Close proximity to the Midlands Meander tourism route and the proposed Industrial corridor of uMngeni, uMsunduzi and eThekwini. | Best private schools in the midlands-which support the promotion and increases demand for tourism products. |
| Strong cultural and historic heritage. | Midlands Meander’s central point |
| Youthful population which is both an advantage and disadvantage if employment opportunities and recreational facilities are not provided | Spring Groove Dam |

C5.1.2. POLICY/ REGULATORY ENVIRONMENT

Mpofana has adopted an Informal Economy Policy, the policy was workshoped to all informal traders so as to familiarize them with the policy. The engagement was a fruitful one in that clarities were given to the informal traders on the expectation that the Municipality has on all informal traders. The engagement was well attended. The Informal Economy Policy does cover street vending, although street vending is an informal activity the Municipality through its Informal Economy Policy has brought about some level of regulatory environment. The Policy is being adhered to by all stakeholders concerned. An investment and Retention policy is also in place, the Municipality has gone an extra mile in this regard in that a formal structure namely Mooi-River Business Retention and Expansion Committe comprising of Local Business People, Department of Trade and Industry and Mpofana LED unit is in place. Mooi-River Business Retention and Expansion committee focuses on Investor attraction and retention.

EPWP

The Municipality benefits from the Department of Public Works Programme namely the EPWP, wherein impoverished members of the Public are given work opportunities which are aimed at assisting them in their plight and in turn assist the Municipality in accelerating its Service Delivery mandate. The EPWP policy is adopted and aligned with the EPWP phase 3.

A database for land ownership is available and is updated as and when required.

SMMEs and Cooperatives

The Municipality has realized a need to develop and support SMMEs as an alternative vehicle for job creation and poverty alleviation by ensuring that aspired community members are assisted to register businesses and Co-operatives through the linkage that the municipality has with CIPC. After registering a certain number of businesses the LED section co-ordinates various workshops for entrant SMME aimed at empowering them with information that will enable them to grow and to sustain their businesses. The workshops offered include business plan development, tendering and business management. In partnership with SEDA, the local Municipality has created an Enterprise Information Centre that helps provide and refer Entrepreneurs to business development support services thereby improving both the sustainability and management of SMMEs. The Municipality has even partnered with DEDT to assist SMMEs engaged in various technical sectors by providing technical skills development trainings relevant to their sectors to ensure they enhance performance by participating competitively within their respective sectors.

Some of the concerns which most businesses in Mpofana have reported  that, there is  (60%) deterioration in the business environment and attribute this to crime, HIV/AIDS, inconsistent service delivery, lack of maintenance, the lack of employment, and poor road conditions.

Woza-Woza Centre which belongs to the Municipality has thus been leased to Tourism players so as to ensure that local Tourism is transformed in that it will be the first point of entry to tourists coming into Mpofana, this will thus enable tourists to market themselves. Woza-Woza is well positioned in that it is located at the entry point of Mpofana Municipality, Some economic activites including tourist attraction activities are being seen at this recently revived centre. All SSMEs and Cooperatives are registered on the Municipal database.

C.5.1.3 PGDP and DGDP Priorities

The KPA responds to the PGD and DGPD Priorities; this is demonstrated in the table below

| PGDS | DGDP | Mpofana Strategic Goal | APPLICABILITY and ALIGNMENT MPOFANA |
| --- | --- | --- | --- |
| Job Creation | Economic Growth and Development (Job creation) | Accelerate Job Creation | Mpofana Municipality has tried by all means necessary to increase the EPWP intake thereby create Jobs, as part of the goals of PGDS, this initiative is being complemented by the CWP programme. Over 400 Jobs have been created |
| Human Resources Development | Human Resource Development Human and Economic Development | Facilitation of Skills Development | Mpofana will be implementing its Work Skills Plan so that the Officials are trained to full capacity, Mpofana has trained all its Finance Staff in the MFMP training so that they are knowledgeable in handling finances. Mpofana Youth currently benefits from ongoing Learnerships from Services Seta wherein over 125 learners are being trained at no cost on Water, Sanitation, Health, Business Administration and Hygien. This is in line with the PGDS goal of Human Resource Development |
| Spatial Equity | Spatial Equity | Spatial Equity | With the SDF being under review and in line with SPLUMA, Spatial Equity is being given the attention it deserves at Mpofana. Previously disadvantaged groups will be prioritized for development just so that spatial equity which is a national priority finds expression in Mpofana’s decision making and development. |
| Basic Services | Basic Services | Increase access to Basic Services | Mpofana has prioritized Basic Services such as Roads and Electricity, this prioritization can be attested to by the fact that the Municipality invests a lot of its MIG to rehabilitating Roads and that a lot of its operating budget goes towards the maintenance of electricity infrastructure. |
| Spatial and Environmental Management | Environmental Sustainability | Improve Spatial Planning | Provide positive environment for Industrial Development. Renewal and Regeneration of Mooi-River Small Town Rehabilitation |
| Governance and Policy | Governance and Policy | Promote Sound Governance and Policy | All IGR Forums are functional, most are co-ordinated at the District Level including the Mayor’s Forum, the Premier’s Forum and the different District Forum’s Mpofana’s Municipal Manager chairs the District Area Finance Forum DAFF. Mpofana also participates in the Planner’s Forum including the Techcinal Forum and MUNIMEC. Council meetings are held monthly as and when required. The Anti-fraud and Corruption policy has been workshoped and approved including the whistle blowing policy which allows the members of the public to report any suspcicious or corrupt behaviour by Municipal Officials. |
| Environmental Sustainability |  | Sustainable Environment | Awareness Campaigns have thus been conducted in Mpofana on how best we can sustain the environment. The Minister of Environmental Affairs is expected to conduct a visit on the 11th of April so as to host an Imbizo to this effect. As part of environmental sustainability, a recycling center has thus been established at the Landfill site so as to protect our environment; the Landfill Site has been established in partnership with the community. |
| Strategic Infrastructure |  | Upgrade and improvement of Infrastructure | Mpofana has recently completed a Weigh-Bridge which cost over R46 000 000 so as to bring about revenue and to promote Road Safety by weighing the Heavy vehicles that pass on the N3. |

C.5.1.3 ECONOMIC DRIVERS

Agriculture

The Department of Agriculture and Environmental Affairs has identified soya, dry beans and maize as products for intensive support in line with the concept of one village one product. Seven districts including uMgungundlovu were identified to be most suitable for this initiative. Mpofana municipality and its partners with its competitive advantage of vast arable land will respond to this call.

Mooi River is one of the regions that have a large percentage of farms acquired during the land restitution programme. Twenty percent of Agricultural land is now on the hands of previously disadvantaged individuals with the others yet to be transferred. While this is anticipated to create an asset base for the poor and enable them to engage in land related economic development initiatives, but due to limited resources mobilisation, financial support, training, integrated planning and support is now resulting in the sector experiencing unintended consequences viz: loss of high potential agricultural land .The net results of this is continuous prevalence of poverty and unemployment.

The issue of underutilization of agricultural land had been identified as an issue of concern and has prompted the municipality to collaborate with local farmers Association, DAERD, DRDLR and ADA to find the best possible solution to remedy this situation. As a remedial intervention a local commercial farmer from Middelrus Valley has decided to partner with six communities who acquired land restitution programme to establish a vegetable Joint Venture projects. The Communities concerned own 70% of the business and have committed small portion of their land to the joint Venture towards vegetable cultivation. The communities will reap multi benefits from this initiative to such an extent that they will get employment from the JV, receiving monthly rentals from the land they have committed whilst owning 70% of the JV. This project is now on implementation stage and over 350ha of land is cultivated with Vegetables.

The second phase of this project is the plantation of stone nuts fruits on the remaining portions of land.

The third phase of this project will be the establishment of Agro-processing facility which is the complementary project for the Joint Venture. The studies for the processing plant are currently underway which entail a feasibility study, an EIA study and preliminary designs. Due to large production to be required to sustain the processing hub the joint venture type of a project will be replicated to all underutilized farms owned by PDIs around Mpofana.

A bridging support programme between commercial and emerging farmers is being implemented. This encompasses the revitalization of potential agricultural land in order to direct required support to intensify performance of agricultural sector. The produce from these farms will be marketed to the proposed agri-processing hub.

Tourism

Mpofana municipality will utilise its comparative advantage of being close to the N3 highway to market local tourism products. A joint tourism route will be developed in partnership with Open Africa and surrounding CTOs to broaden and increase the length of stay as well as spend of tourists.

Currently the local tourism and crafts centre is in operation and even has an additional craft facility to accommodate local crafters. This tourism centre offers a restaurant, tour bus and crafts facilities. The development and erection of tourism signage will be intensified in order to encourage motorists to come-off the N3. A Municipal wide Brochure aligning the Municipal area to the Midlands Meander, Battlefields, Drakensberg (Giants Castle), Pietermaritzburg and the like is going to be produced and will effectively market the area as a gateway.

TZN has already offered to conduct training workshops for emerging tourism based enterprises and crafters. This will surely improve local products and exposure to niche markets. (E.g. development of bird-viewing sites, tour guides etc.).

With the Spring Grove Dam being under construction it is envisaged that the tourism sector is going to be intensified through the development of tourism establishments around the dam. This attraction has without doubt the potential of becoming a major tourist draw card which will incorporate a number of recreational activities that will prolong the tourists stay in the town.

#### C5.1.3.Employment and Income Levels

Figure 7: Employment status

Source: Census 2011

The figure above shows that unemployment decreased between 2001 to the year 2011. Employment status is increasing in spite of the slow pace of investors moving to Mpofana.  The establishment of Tai-yuen textile industry,construction of Spring groove dam and Spar retail has contributed to the increase in job opportunities. This could also be attributed to the recent introduction of KFC in the area which has employed a significant number. A new Mall is being constructed which will also have an impact in terms of the employment levels. These figures are showing that there is hope for people of Mpofana in terms of employment opportunities. However the employment rate is increasing at a very low rate.

The municipality has prioritise economic growth by rolling out its investment incentive policy, small town rehabilitation programme, leverage on municipal assets by disposing land for development of food retail and golf club  and establishment of industrial hub. All these initiatives will result in economic growth and unlocking of job opportunities.

Figure 8: Employment status as per 2011 Census

The unemployment levels are projected at 45% and this is due to a lack of economic activities that provide employment to the municipality. This can also be attributed to closure of textile factories in the nineties, lack of entrepreneurs, lack of infrastructure to boost investor confidence, lack of skilled labour etc. The municipality also faces a shortage in the skilled and professional pool labour as most individuals are employed in elementary occupations. The lack of skilled labour or professionals in the municipality results in other individuals outside of the municipality being employed within. There are quite a number of individuals who are self-employed through the formal and informal arts and craft sector of the economy.  This might be related to the location of the municipality within the Midlands Meander and along the N3.  This is a positive trend for the municipality to promote the tourism sector. The unemployment rate has a direct impact on the affordability of municipal services and therefore affects Municipality’s cash flow situation negatively.  The high unemployment rate also suggests that economic growth and job creation must be considered as one of the key strategic issues for the Municipality.

Figure 9: Household income levels

C5.1.3. SMME’s

SMME and co-operative development has been recognised as an alternative mechanism to address triple challenges facing the country. The municipality is continuously assisting SMME in areas of business registrations   and business plan development etc.

The municipality is working tirelessly in creating linkages between big businesses and the SMME’s during the LED Forum interactions between the Big businesses and the SMMEs took place where both sectors outlined their services, much to the advantage of the SSMEs that were able to showcase some of their services. National Government has recently established a ministry to look into SMME’s. Mpofana continues to support SMME’s that is why in the 2014/15 financial year, R100, 000 was allocated for the establishment and support of local SMME’s and Co-operatives around Mpofana Local Municipality. Mpofana monitors and supports the SMME’s. Funding mobilisation is done on behalf of the SMME’s. In all our capital projects, procurement of goods and services by our service provider should be from SMME’s but if such goods are not available from our SMME’s then they are allowed to procure elsewhere. The SCM policy has recently been reviewed so as to give preferential treatment to SMME’s. The implementation of Mpofana’s Public Realm Project also known as Small Town Rehabilitation Programme will see our local SMME’s benefit immensely including local co-operatives and local forums who are registered on our database.

C5.1.3. Agriculture

Mpofana Municipality is predominantly rural and as such there are too many agricultural activities in the area, Agriculture is the backbone of Mpofana’s economy. A lot of land belongs to the Farmers who specialise in the production of agricultural products. Mpofana receives a lot of rain during the summer season, and as such the land is fertile and good for agricultural activities.

70% of the land is agricultural, and there exist over 50 farms which contribute significantly into the development of Mpofana’s economy. As part of the Land Reform project that is going on countrywide. Some people have benefitted immensely in that, there are some farms that now owned by previously disadvantaged groups. This has further been boosted by the recent visit of the Deputy Minister of Agriculture and Fisheries, wherein some farms were visited by the Deputy Minister recently. Farms that are non-functional were visited and support was offered to them by capacitating them to better their understanding of farming for commercial purposes.

C5.1.3. Tourism

Mooi-River is strategically located as it’s the gateway to the Drakensberg and to Durban which are the most preferred tourism destinations.  Mooi-River also forms part of the Midlands Meander tourism route which is internationally recognised.

Department of Water Affairs and Forestry has completed the construction of Spring Grove Dam in Mooi-River which will augment water supply in 4 District Municipalities. This resource is believed to enhance the current economic development related initiatives e.g. Agriculture and further need and demands of prospective investments.

The location of Spring Grove Dam in Mooi-River presents enormous development opportunities in the tourism sector. This development opportunity compels the Municipality to develop the plan to optimise development opportunities around the newly built dam. The plan will seek to encourage various sporting activities. It anticipated that the dam will be able to host events.

C.5.1.4 Spatial Referencing of Programmes and Projects

C5.1.7. Strategic Programmes Responsive to the Comparative and Competitive Advantage of the Locality

The municipality has a specific programme seeking to transform the local tourism players. There is a Business Retention and Expansion Committee which seeks to assist Local Tourism players.  There are programmes that have been developed for SMMEs/ Cooperatives.

### AGRI-PARKS

MPOFANA MUNICIPALITY: AGRI-PARKS

FARMERS PRODUCTION SUPPORT UNIT (FPSU)

Background

The Agri-park concept was mentioned by the Honourable President J.Z Zuma during his State of the Nation Address, 2015/16. The strategic objectives include strengthening a system of agro-production, processing, logistics, marketing, farm infrastructure, capacity building, and production and mechanization inputs.

Agri-Park (Hub) proposed location for uMgungundlovu District is at uMngeni Municipality, the concept includes the establishment of Farmers Production Support Unit (FPSU) which will be located in each local municipality.

Mpofana Municipality`s intention is to establish a Farmers Production Support Unit (FPSU) which will respond to mechanization support (ploughing, spraying, harvesting, local logistics support and Small Business Development and Training center which will include banking. FPSU will also offer extension support & training, -a symbiotic relationship to “hold-hands” with farmers over 10 years.

Status Qou

On the 6th of May 2016 Mpofana Municipality hosted the stakeholders engagement where we invited commercial farmers, private entities, SMME`s/co-operatives, agricultural training institutions, etc in the agricultural and manufacturing sectors. The event was well attended as we have about 70 people from the different farming sectors (find attached attendance register).

The presentation of the concept where done by Mr. Kimraj from Department Rural Development and Land Reform also Mr Hlongwa from uMgungundlovu District. The municipality was given a task to develop business plan to be submitted to DAPOTT for funding and to identify a suitable land or farm for FPSU, we decided to establish Project Steering Committee (PSC) that will oversee the project also assist in drafting the business plan which was made out of the following sectors.

MPOFANA MUNICIPALITY (AGRI-PARK-FPSU PSC)

| NAME | ORGANIZATION/ FORMATION | CONTACT NUMBER |
| --- | --- | --- |
| James Kean | Commercial Famers | 0828020973 |
| Mlungisi Xulu | Emerging Farmers | 0724202065 |
| Bheki Nene Ndoda Khumalo | CPI’s | 0718485341 |
| Nkosinathi Mathunjwa | LIMA | 0793053429 |
| Gram Armstrong | UMATI | 0828545746 |
| Zodwa Khoza | Mchunu Tribal Authority | 0837859684 |
| Mhlengi Sithole Mrs. BM Mchunu | Mpofana Municipality | 0764115869 0828886276 |
| Ross Phipson | TechnoServe | 0829274911 |
| K.S Mendu M.M Mthembu | DARD | 0828761387 033 3476268 |
| Sbongiseni Madlala | YARD | 0729457462 |
| Thando Sokhela | UMDM DAMC | 0828059461 |
| Gcino Shabala | Land Activist | 0834733522 |

Progress

We delegated (Upper Midlands Agricultural Transformation Initiative) UMATI to assist the PSC and the municipality in developing business plan, first option was to develop this plan without any huge costs. UMATI promise to use services of Mr James Martin who is currently working with company called Just Trading which is willing relocated to Mooi River with their animals feed business and establish abattoir. We decided to collaborate with them in their business venture to avoid duplicate and unnecessary competition.  The PSC had their first meeting on 17th of June 2016 on that particular meeting Mr James Martin presented a draft business plan, the resolution taken was that Just Trading shall come and do full presentation on the PSC about their offer and also the committee should give us a formal structure which consist of Chairperson, Deputy Chairperson, secretary, deputy secretary, treasury and coordinator. The meeting was schedule for the 21st June 2016, in that meeting we engaged and agreed that Just Trading should give us the proposal in writing, which they did (find the document attached). The PSC presented a structure as follows:

Mpofana PSC Structure

| Name | Designation |
| --- | --- |
| Mr. Xulu | Chairperson |
| WARD Representative | Deputy Chairperson |
| Mhlengi Sithole | Secretary |
| YARD Representative | Deputy Secretary |
| Bheki Nene | Treasury |
| Gcino Shabala Ross Phipson | Organizer |
| UMATI Representative | Additional |

The committee PSC together with Just Trading was also tasked to do a presentation and give a progress report to the Mpofana Municipality council and management, before they take it to DAPOTT. That has since taken place, wherein at a Special Council Meeting, The Council adopted the Farmers Production Support Unit (FPSU).

Expected outputs of AGRI-PARKS @ Mpofana

Revival of farms that are underutilised

Food Security

Job Creation

A boost of the Mpofana economy

The Municipality has identified the manufacturing sector in particular industrial development as the key intervention to address the LED challenges. We believe that industries have potential of absorbing enormous employment and to enhance revenue generation.   In pursuing this desire the Municipality has undertaken a feasibly study to assess the viability of the proposed intervention. The study entails the feasibility study EIA and preliminary design. The land identified is already zoned as an industrial (zone). The study has revealed that the proposed project will be of high viability.

The rationale behind studies was to assist in making an informed decision whether to make provision of necessary infrastructure (Road, Storm Water Pipes and Electricity). The Municipality has an understanding that investors would come flooding to invest in places set up with infrastructure. The Municipality seeks amongst other things to attract the green project as a response to climate change.

Manufacturing is one sector that will unlock job opportunities for locals and thereby turn around Mpofana’s economic situation.

C.5.1.8JOB CREATION

Some jobs have been created as a result of the LED Unit. Herein the ensuing table shows the number of jobs that have been created and the table further shows which programme has assisted in the creation of those jobs. All wards have benefited from the jobs that have been created.

| Programme name | Number of jobs created |
| --- | --- |
| Extended Public Work Programme (EPWP) | 65 |
| Community Works Programme (CWP) | 359 |
| Khabokhedi PTY LTD | 16 |
| Labour Intensive Jobs | 67 |
| Small Town Rehabilitation | 20 |
| Side Walk Construction | 45 |

The Municipality therefore boasts over the creation of over 700 jobs created, as part of its Local Economic Development. This is exclusive of the SMME and CO-ops that had benefited a great deal from Mpofana’s LED initiatives.  Mpofana is committed to job creation.

The Municipality has been sure to report on its integrated grant spending for the 2016/17 financial year.

The following projects/programmes were undertaken under the EPWP programme

| Project Name | Ward |
| --- | --- |
| Maintenance of Mpofana Roads and Storm System | All Wards |
| Maintenance of Mpofana buildings | Ward 5 |
| Grass-Cutting | All Wards |
| Parks and Gardens | 1,2&3 |
| Out-door Gym | 3 |

C5.1.8. Mining

The Municipality has no Mining Industry.

C.5.1.9 EPWP INDICATORS

| Programme name | Number of jobs created |
| --- | --- |
| Extended Public Work Programme (EPWP) | 65 |

The Municipality has over the past 3 years received R 300 000 for the Extended Public Works Programme. Annually the Municipality receives R1000 000 from the Department of Public Works and the community has benefited from this. The Municipality has done well in this regard in terms of grant spending, having spent the entire funding of 100%.

Hereunder are projects that have been submitted to the National Department of Public Works (NDPW) under the EPWP programme.

| PROJECT LIST FOR: |  |  |
| --- | --- | --- |
| Name: |  |  |  |  |  |  |  |
| Sector | Focus Area | Project Name |  | Project Number | System Generated ID | Project Budget in 2017/18 | Funding from EPWP Grant |  | Number of WOs |
| Infrastructure Sector | Road and Stormwater System Development and Maintenance | Maintenance of Mpofana Roads and Storm System. |  | Roads 17/18 | 56301 | R 424 360 | R 424 360 |  | 22 |
| Infrastructure Sector | Development and Maintenance of Buildings | Maintenance of Mpofana Buildings |  | Maintenance of buildings 17/18 | 56302 | R 182 520 | R 182 520 |  | 13 |
| Environment and Culture Sector | Parks and Beautification | Mpofana Grass Cutting |  | Grass Cutting 17/18 | 56303 | R 182 520 | R 182 520 |  | 13 |
| Environment and Culture Sector | Parks and Beautification | Mpofana Parks and Gardens |  | Parks and Gardens 17/18 | 56304 | R 168 480 | R 168 480 |  | 12 |
| Social Sector | Social Services | Out Door Gym |  | Out Door Gym17/18 | 56305 | R 42 120 | R 42 120 |  | 3 |

C.5.1.10 SKILLS DEVELOPMENT

Skills development is at the heart of any developing community, The Municipality has quantified the number of people involved in skills development programmes, this has been through the support of Mpofana’s WSP and Services SETA. Inclusive growth means training community members including those from rural areas. The Municipality boast training over 350 of its youth, women and men from rural areas on different skills. At the moment there are 8 skills development opportunities for rural development initiatives, Mpofana Youth in Agriculture (MYAD) has been instrumental in identifying much needed skills for the youth. 5 out of 55 registered SMMES are being supported with training. Through the AGRI-Parks programme, there have been 20 emerging farmers trained by well experienced farmers on finance management and crop rotation.  There have been 2 programmes that have been implemented in support of tourism.

C.5.1.11 AGRIGRIAN TRANSFORMATION

There is one project that has been developed which seeks to support the revitalisation of irrigation schemes, the programme came about as a result of an initiative by the Minister of Agriculture and Rural Development working closely with Mpofana Farmers Association. There is a programme called Sengani Irritation in the Mpofana area that seeks to revitalise an irrigation scheme through the safekeeping of dams and safeguarding dams which are vital in the irrigation of some farms. A plan has thus been developed to also promote smallholder producers, as it stands 5 smallholder producers are receiving the support. The approved AGRI-PARKS plan aims at expanding employment opportunities in the agriculture sector. There is one Agri-Parks infrastructure project that is currently under design stage which will see the development of infrastructure which will in turn assist in positioning Mpofana as the Hub of Agriculture in the province. Five agricultural enterprises are supported, namely Oranges, Beef, Peaches, Milk and Potatoes. There are over 2000 hectors under irrigation that are used by smallerholder producers.

C.5.1.12 INCLUSIVE RURAL ECONOMY

Agro-processing has been widely perceived as one of the key economic drivers in Mpofana, it is for this reason that the Mpofana Project Steering Committee on AGRI-Parks has seen it as one of its priorities. 3 new enterprises have been supported in the rural areas and more stand to benefit out of this initiative. There are only 2 investors participating in rural investment schemes. As mentioned in the aforementioned paragraphs there are skills development programmes that have been carried out in the rural areas.  The Tourism Sector thrives in Mpofana and has been accepted as one of the biggest employers within the community. There are over 5 Game Reserves in Mpofana, 15 B&Bs, 12 Hotels and 10 Tourist Attraction Sites and this has in total employed over 500 people.

MINING INDUSTRY

Mpofana has no mining industry

C.5.1.13 GREEN ECONOMY INITIATIVES

Green economy initiatives, is designed government in greening the economies by reshaping and  refocusing policies, investment and speing towards a range of sectors such as clean technologies, renewable energies, water services and green transportation, waste management, green buildings and sustainable agriculture and forests. Some green Buildingshave since emerged in Mpofana. This has also been supported by waste management in that a recycling project has since been established which aims to manage waste by having a recycling centre. The project on waste management is supported by the Municipality and the Co-operative itself is registered on the Municipality’s database.

C.5.1.14 CAPACITY OF THE MUNICIPALITY

There is an established LED unit within the Municipality, there are capacity constrains in the unit in terms of human resources. But the EPWP programme minimizes the challenge. The filling of the post for LED and Tourism Manager will also help deal with the staff shortage. There is a Mooi-River LED Team that champions LED programmes and initiatives. In the 2016/17 financial year 5 collaborative agreements were signed including one co-funding agreement; indeed there is capacity for formulating collaborative and co-funding agreements. In the 2017/18 financial year more will be signed if they will be advantageous to the development of Mpofana. A budget of R500 000 has been set aside for the effective implementation of the LED programmes. A plan to monitor and evaluate the effectiveness of the progress made is being developed, but at a departmental level monitoring and evaluation does take place. No budget has been set aside for Research and Development, however such a budget will be considered in future so as to fully explore the economic development of Mpofana.

C.5.1.15 PRIVATE SECTOR RESOURCES

This is simply answered by the fact that the Municipality managed to sign a Public Private Partnership in the amount of R 46 000 000 with SANRAL for the construction of a Weigh Bridge in the 2016/17 financial year. The plan is developed that looks into tapping on private sector resources. The Municipality has thus been able to leverage on private sector funding and resources which has assisted greatly in the realization of LED projects.

#### C5.2.9 Local Economic Development: SWOT Analysis

| STRENGTHS | WEAKNESSES |
| --- | --- |
| Mpofana Municipality is strategically located along N3 and an agro-industrial corridor stretching from Pietermaritzburg to Escort. Strong institutional arrangements to promote economic growth, retention and expansion of local business, promoting dialogue between business and the municipality LED Strategy in place Business Retention and Expansion Policy | Poor infrastructure development. Lack of investment incentives to attract new investors. Lack of capacity to enforce street trading by laws Lack of investment incentive policy Capacity constraints, LED Manager has been advertised and is to be filled |
| OPPORTUNITIES | THREATS |
| Accessing grant funding for small town rehabilitation. Public private partnerships Business support and development. Form partnership with Trade and Investment KZN to promote Mpofana as an investment destination. Increase job opportunities through agro-processing industry and agricultural development. Identify more land for industrial and commercial development. Establishment of a Farmer Production Support Unit | Competition for investors from other neighboring municipalities. High staff turnover within the LED unit Slow Economic Growth Some farms are underutilised Toll tariff is too high |

### 5.2  Social Development Analysis

C.5.2.1 The Municipality is in the process of developing a Poverty Eradication Master Plan (PEMP)

#### C5.2.1. Broad Based Community Analysis

The table below outlines the broad based community needs which have been gathered as part of this IDP’s review process. It is clear that a lot of needs are infrastructural in nature. This is also based on the CBP programme.

| Ranking | Ward 1 | Ward 2 | Ward 3 | Ward 4 | Ward 5 |
| --- | --- | --- | --- | --- | --- |
| 1 | Mpofana Testing Routes | Highover Road | Sthembiso to Cabazini Road (Phase 1&2) | Mgqula Road | Mangaung Access Road (Phase 1 &2) |
| 2 | Small Town Rehabilitation | Rosetta Slums Clearance | Gwala Park ratification | Vovonya Road | Mangaung Electrification |
| 3 | Phofini Road | Scotsfontein Electrification | Bruntville Internal Roads | Cwaka Road | Phumlaas Internal Roads |

C5.2.1. Education

Education is another factor that is hindering people from overcoming poverty. There are no institutions for Mpofana youth to acquire skills and knowledge to earn decent living. There is a need to establish the FET in Mpofana so that young people can be encouraged to finish matric and move to tertiary level. Young people have to attend the Mnambithi or Msunduzi FET College to get access to higher education.

| Indicators | 1996 | 2001 | 2011 |
| --- | --- | --- | --- |
| No schooling | 3 246 | 5 584 | 3 438 |
| Some primary | 2 867 | 4 571 | 3 598 |
| Complete primary | 1 025 | 1 449 | 1 116 |
| Some secondary | 3 375 | 5 375 | 7 327 |
| Std 10/Grade 12 | 1 603 | 3 095 | 5 813 |
| Higher | 1 062 | 1 075 | 1 261 |

The above table shows that there is a discrepancy between the number of people who complete Matric and those who get the opportunity to get higher education. According to 2011 stats SA data 5 813 people managed to get their matric and on the other hand only 1 261 managed to get higher education.Education plays a pivotal role on community development.  It provides a set of basic skills for development, creativity and innovative abilities within individuals. The South African Constitution provides that everyone has a right to education, which includes Adult Basic Education. There is a significant number in the population who have not obtained any schooling especially females. A number of factors could be attributed to this section of the population not having any schooling, amongst others stereotypical thinking that women should not obtain education or perhaps lack of interest thereof.  It is assumed that the majority of women who have not obtained any schooling form part of the older generation of the population.  The municipality in partnership with Gender Machinery structures has embarked on various programmes addressing gender issues and advocating for women empowerment.

There has been over the years a significant decline in the number of people who continue to tertiary education after completing the matriculation. This can be attributed to the lack of financial resources and lack of knowledge of financial aid available to prospective tertiary students. The poverty levels might also be a contributing factors where there’s a significant need to get a job than continue to tertiary education. The lack of knowledge about the availability of financial resources is being addressed through the Youth Advisory Centre and has seen a significant number of the youth having access to bursary institutions and financial aids. The

C5.2.2.Health

The Mpofana Municipality is currently serviced by two clinics located in Mooi River and Bruntville respectively. There is also a satellite clinic located in Rosetta that’s opens once a week. The Bruntville Community Health Centre Clinic is managed by the Department of Health. There is however a need to conduct a feasibility study in order to address the need of clinics in other areas of the municipality especially in wards 2 and 4 where there’s a dependency on mobile clinics. The Mooi River Clinic has been transferred to the Department of Health.

MAP13: Clinics

The above map shows the location of the Clinic (including Mobile Clinics)

The population of Mpofana has increased since the death rate as a result of HIV/AIDs has declined. The Local Aids council chaired by the Mayor has implemented awareness campaigns; male medical circumcisions through it ward based aids councils. The Department of Health is engaged in negotiations with the Municipality with the view of adding a clinic. Council has proposed that an additional Clinic be located in Ward 4.

C5.2.3Safety & Security

The municipality is currently serviced by 2 police stations located in Ward 1 and 4 respectively, Ward 2 and 3 are serviced by these 2 Police Stations. There is however a high prevalence of criminal activities in other wards which has resulted in the communities from different wards requiring mobile police stations. The municipality is committed to intensify campaigns against Substance abuse and crime by having open dialogues about substance abuse and crime, Some dialogues have already taken place with the communities around the issue of substance abuse. Traffic control and compliance with the bylaws is one of the key priorities of the municipality. A weigh bridge has recently been completed are plans to build the weigh bridge to monitor the overloads by truck fleets passing on the N3, The project is currently being implemented with funding totalling R46, 000 000. This will ensure the safety of the people who live within a close proximity of the N3, more Traffic Officers will be deployed at various points so that the community’s safety is maximized. This project will assist in enhancing the municipal revenue and ensure compliance with roads regulations.

Due to the prevalence of Crime in the area, the SAPS has come on board in partnership with Government Departments, to educate communities about the adverse effects of crime and drug abuse. The CPF (Community Policing Forum is in full effect and works closely with the Municipality and the SAPS. Suspicious behaviours are reported to the SAPS.  An awareness campaign was recently held to discourage crime, the attendance was good and the participation by the community was satisfactory. SAPS were also involved and the CPF played a vital role in the awareness campaign. The people now feel safer, the Municipality is also in a process of procuring Street lights where crime is most prevelant.

C5.2.4 Community Development with particular Focus on vulnerable

The Municipality is centred around the development of the community at large and with a special focus on vulnerable groups. Programmes are planned in the Service Delivery and Budget Implementation Plan (SDBIP) and are implemented annually which focus on the vulnerable groups.

C.5.2.5 Youth Plans Development

Young people are faced with numerous social and economic challenges that prevent them from being active participants in the reconstruction and development of South Africa. Poverty and unemployment are some of the major challenges facing young people of Mpofana municipality.

A fully fledged youth centre with two dedicated Youth Development Officers is responsible for coordinating specific interventions such as education, health and well-being, economic participation and social cohesion. The role of this office will be even more once there is an integrated youth development strategy in place.

The youth summit was convened in April  2013 involving the Provincial Departments, District Municipality, NYDA and other stakeholders working with young people. The main aim of this summit was to interact with young people and listen to their aspirations. The output of the summit is thatthere has been alignment of plans and establishment of the Youth Council. The role of the Youth Council which was elected during the Youth Summit is to monitor and evaluate the interventions on the needs of young people from various stakeholders. The Youth Council meets quarterly to look into Youth issues, representatively in terms of Ward, Age; Gender was taken into cognizance when the Youth Council was elected.

Youth Day is held annually on June 16, and is funded internally.

Youth Development is also complemented by some programmes that have since been introduced at Mpofana like Youth in Agricultrure wherein young upcoming farmers are assisted and capacitated.  The Forum is established which deals with Agriculture, since Mpofana is mainly agricultural in nature. The aim of the Forum is to develop the Youth agriculturally.

C.5.2.5 Development of the People with Disabilities

We are members of the KZN joint machinery which is a forum established in the office of the Premier. The main aim of this structure is to monitor government departments and other sectors in mainstreaming of gender, children s’ rights and disability into all their programmes. This will help government to respond to issues of these target groups in an integrated and coherent manner.

The Mpofana municipality has formed partnerships with government department and NGOs to respond to the needs of the children, women, elderly and disabled. The Department of Social development has registered more than ten non-profit organizations to bring services closer to the communities.

Tholimpilo Centre, which was utilized as a Clinic is now being used for disabled children. Mpofana Municipality has prioritized the development of this centre since the number of disabled children has increased to 30 this is due to the development of new housing projects which has seen an increase in the population figure. The caregivers havesince undergone formal training to look after children with disabilities. Theare plans to registerthe centre in order to get funding and be managed properly. Tendele NIP in ward 2 provides care to the orphans and there is a need to establish one in ward 4.

Elderly and Disabled committees have been established in all four wards. The emphasis will be on developing and implementing programmes targeting the elderly and the disabled. The elderly people will continue to participate in District and Provincial sports to promote healthy living.

There are programmes that have been put in place so as to promote the development of the people with disabilities. A budget totalling R200 000 has been set aside to this effect.

C.5.2.5Development of the Elderly

Mpofana Muncipality has formed partnership with Government Departments so as to respond to the needs of the Elderly, This has been evident by the number of Elderly events that have taken place in the Mpofana Area. The function of the development of Elderly falls directly under our Social Services Office, which has been tasked with establishing Community Structures, of which one of those structures is a structure for the Elderly. The Elderly will continue to participate in the District and Provincial Sports to promote Healthy living. The Elderly structures have been established in all 4 Wards, SASSA has been very instrumental in supporting Mpofana in this cause.  The Municipality has recently hosted games for the elderly and the turnout was good. A project for the elderly is also running called Mbizimbele, where the elderly come together and plant. The project was established through joint partnership between Mpofana Local Municipality and SASSA. One of the projects objectives above planting is providing meals for the elderly who are either overly burdened with too many dependants. Skills relating to sewing and gardening are taught to all the elderly. There are currently Luncheon clubs that have been established in Mpofana that are in existence.

C.5.2.5 Development of Women

Mpofana Municipality is committed to the Development of Women, It cannot be denied that National Trends in this regard are not showing a desired picture, however it should be taken into account that strides are made in the right direction to fix the marginalization of women even at national level. Mpoana Municiplaity has also made tremendous strides in addressing issues surrounding women exlusion, We have therefore made it a priority that the emancipation of women takes centre stage in the Municipality, It is no surprise that a number of women SMEs have been established trough the Municipal Local Economic Development Office, where women are encouraged to be participants in the development of the local economy by registering SME’s. Mpofana has many women-headed households, During women’s month (August) An annual event is held where all women come together have an open dialogue with the Local Mayor who is a woman herself, where issues affecting women at large are tabled, This is also used as an opportunity to honour women for their contribution in the wellness of the community and their role in their households, especially women-headed households.

C.5.2.5 People affected by Crime, HIV/Aids, Drugs, etc.

HIV/AIDS continues to pose a threat to the residents of Mpofana. Although the death rate has declined, fight against HIV/AIDS must continue. The municipality has the existing functional structures responsible for coordination of integrated responses to HIV/AIDS and poverty. For example the municipality has established the Local Aids Council chaired by the Mayor and the Ward Aids Councils chaired by the Councillors. Operation Sukuma Sakhe is generating positive results since there is Local Task Team comprises of all government Departments and Non-Governmental Organisations. All the four wards have the war rooms dealing with monitoring of interventions to profiled community needs. Each war room is allocated a Councillor as the Champion and the Manager from the Municipality for technical support.

Drug and substance abuse is threatening young people who are the fabric of the society. The municipality has to work hard together with the government department and other stakeholders to combat the problem of substance and drug abuse. The Drug Aids Council is functional and Chaired by the Mayor.

The municipality is unable to absorb a high number of unemployed people, especially the youth. The municipality has to stimulate manufacturing and industrial development to create more jobs. As a result communities are more dependent on social grants.

Mpofana Municipality in partnership with other stakeholders has aligned itself by identifying infrastructure development as one of the key strategic tool to unlock job creation and address poverty. The construction of the Spring Groove Dam in Ward 2 has created jobs for the community. It is also envisaged that the roll out of small town rehabilitation programme and housing development will create more job opportunities within Mpofana.

C.5.2.6 Disability summit

The Municipality does hold a disability summit annually, wherein the disabled are invited and given life-skills. The disabled are further supported by an established Disability Forum which assists the disabled.

C.5.2.7 Nation Building & Social Cohesion

The Department of Art and Culture, Sport and Recreation and Social Development in partnership with the municipality has implemented various programmes aimed at building the nation and reviving our cultural heritage. Many of our young girls attend the Reeds ceremony and undergo virginity testing by trained maidens on a regular basis. The municipality has recently hosted an event for young people in partnership with Department of Arts and Culture which saw a Mpofana Group win an award in a competition which was very competitive. The Municipality has dedicated individuals who attend to Social Cohesion issues. Mayoral Cup is an example of one of Social Cohesion initiatives that the Municipality has undertaken and this is done on an annual basis. Of late during the Month of June a month which has nationally been categorized as Youth Month, A fun Walk/Run is held and is attended by all youth from across the Mpofana Wards.

### C.5.2.9.Social Development: SWOT Analysis

| STRENGTHS | WEAKNESSES |
| --- | --- |
| Strong institutional Arrangements in place(Local Task Team and war room are functional) Local Aids Council, Sport Council Council for the Disabled in place. | Lack of consistency in terms of people attending from other departments Availability of water an issue on food security |
| OPPORTUNITIES | THREATS |
| Strong Stake-Holder Relations Reduction in HIV/AIDs District Aids Council Provincial Aids Council Strong institutional arrangements Constitutional Mandate Knowledge | Prevalence of HIV/AIDs Departments are not fully supporting the programme. Government Departments perceive the programme as additional work. Profiling has not been completed. Lack of proper monitoring and evaluation system. Lack of adequate water, electricity and sanitation. Lack of sport infrastructure affecting youth participation in sport. One garden per household sustainability affected by change in season and lack of adequate water. Slow delivery of houses for qualifying vulnerable individuals. Lack of support from senior managers Lack of transport for the cadres Slow response by Departments to needs identified through surveys |

5.3 FOOD SECURITY

### C.5.3.2 FOOD Security and Nutrition

There are over 2000 people are benefiting from Food Security and Nutrition initiatives,

### C.5.3.3 HOUSEHOLDS SUPPORTED

Through the EPWP programme some homes have been supported with food supporting initiatives. They are estimated at 50 with 10 in each ward. The Department of Agriculture provides seeds to the households concerned and the community members employed in the EPWP and CWP assist in developing those food initiative programmes for those impoverished households.

### C.5.3.4 GARDENS ESTABLISHED

There are only 2 Community and Institutional Gardens established. Ward 2 through a co-operative has established one community garden and the Municipality has successfully established 1 in Ward 3. There are plans to establish more gardens in other wards.

### C.5.3.5 National School Nutrition Programme

Mpofana Local Municipality Schools do benefit from the national School Nutrition Programme and with most schools being rural and in impoverished communities. 11 out of the 15 Mpofana Schools benefit from the National School and Nutrition Programme.

### C.5.3.6.Number of hectares and projects under-utilised land

It is not known at the moment how many hectares are under-utilized. But this has been estimated at 10 farms which lie dormant and under-utilized. Most of these farms are those that are procured on behalf of previously disadvantaged communities.

C6. Municipal Financial Viability & Management

### C.6.1 CAPITAL FUNDING AND EXPENDITURE TO ADDRESS SERVICE DELIVERY

Financial viability and management remains is at the backbone of Service Delivery in that projects need to be funded. Below is a 3 year synopsis of funds received, spent, unspent source of funding, variance tables and contingency plans to address challenges which are mainly due to delays.

| Year | Funds Received | Funds Spent | Unspent | Variance | Source of Funding | Contingency Plans |
| --- | --- | --- | --- | --- | --- | --- |
| 2014/15 | R11 600 000 R5 000 000 | R 9 830 398 R4 000 000 | R1 769 602 R1 000 000 | 15% 5% | MIG DOE | Fast track the appointment of Service Providers |
| 2015/16 | R16 295 00 R6 000 000 | R16 295 00 R5 600 000 | R0 R400 000 | 0% 4% | MIG DOE | Fast track the appointment of Service Providers |
| 2016/17 | R11 680 000 R5 000 000 | R 11 680 000 R5 000 000 | R0 R0 | 0% O% | MIG DOE | Fast track the appointment of Service Providers |

The table above shows that the Municipality has not always been in a position to spend all its funding, but the variances in terms of spending on the receieved grants has never exceeded 15%, some is as low as 4-5%. The only reason that could account for these variances is the timely appointment of Service Providers that have been entrusted with the completion of these projects.

Capital Budget

CAPACITY TO DELIVER ON CAPITAL PROJECTS

Mpofana Local Municipality is well suited to deliver on its capital projects, this is due to the reason that the Technical Director post is filled, which means that all infrastructure related issues and projects are dealt with and given the attention they need, since they are our core-function. The Technical Director is also complemented by a Manager that deals with Roads. All our MIG has gone into Road Rehabilitation and Upgrade, it therefore is vital that a Roads Manager stays employed and receives the necessary training. The Municipality has also made a decision that a Project Manager be employed in this financial year, Interviews have been scheduled to this effect. This will assist Mpofana by having a dedicated official looking at projects and constantly reporting on all progress and closely supervise the Service Providers.

Below are projects that are listed in order of prioritization and duration of each project including the responsible departmentand the donor or grant.

| Project Name | Ward | (Estimated Amount) | Duration | Responsible Department | Fund | New/ Ongoing |
| --- | --- | --- | --- | --- | --- | --- |
| Mooi-River Testing Route | 1 | R 3 000 000 | 2017-2018 | Technical Services | Small Town Rehabilitatino | New |
| Mangaung Access Road (Phase 2) | 5 | R 2 432 800 | 2017-2018 | Technical Services | MIG | Ongoing |
| Ward 2&4 Electrification Project | 1,2&4 | R 5 000 000 | 2017/2018 | Technical Services | Department of Energy | Ongoing |
| Highover Gravel Road | 2 | R2 432 800 | 2017/2018 | Technical Services | MIG | New |
| Sthembiso Cabazini Road (Phase 2) | 3 | R2 432 800 | 2017/2018 | Technical Services | MIG | Ongoing |
| Mgqula Gravel Road | 4 | R2 432 800 | 2017/2018 | Technical Services | MIG | New |
| Upper-Town Road | 1 | R2 432 800 | 2017/2018 | Technical Services | MIG | Ongoing |
| Energy Efficiency | 1,3 &5 | R6 000 000 | 2017/2018 | Technical Services | Department of Energy | New |

### C6.1. Capital funding and expenditure to address service delivery

The projected capital outlay to be funded by the council for capital additions are as following until June 2017:

Ultimately, the implementation of the capital budget is based on the availability of funds. The need to develop services, especially to the poor and for economic development, is vital for the future, but this will not be possible should the collection rate not improve. It would then be prudent to stress that the implementation of this projects is reliant on the cash flow position of the municipality.

The above projections reflect an increase in the municipal contributions towards the capital budget. There are various measurements that management has put in place to try and increase the financial viability of the municipality so that significant contributions can be made towards the capital budget and indirectly to service delivery capacity of the municipality; such as submissions and lobbing to the Municipal Infrastructure Grant decision makers to increase the allocation made to the municipality.

The Municipality is in the process of establishing a Project Management Unit, and as such will be in a position to execute capital projects, as that has always been missing in the Municipality.A Project Manager is to be appointed who will see to it that all Capital Projects are implemented within the given time-frames. A post has been advertised, The Municipality will be short-listing soon for the mentioned post.

### C6.2. Social and Economic Redress Via Indigent Management

The municipality provides Free Refuse Removal to indigent customers who are mostly located in the Townview and Bruntville area.

During the 2016/17 Financial Year the Muncipality was engaged in compiling its indigent register through the involvement of Councillors and Ward Committees. This was a thorough exercise, which the Municipality concluded. In the 2017/18 financial year, the Municipality has set aside a budget which will go towards free basic services and the indigent support.The introduction of the Free Basic Services including the indigent support has been prompted by legislation and the MEC’s assessment of the 2016/17 submitted IDP. This further addresses the MEC comments. This will be funded by the Equitable Share. The Indigent customers have increased, in the previous submitted IDP; the MEC commented that there is no reason given for the growth in terms of indigent customers. It has been investigated and concluded that this growth is attributed to the growing number of unemployment in Mpofana; this thus sees a number of people being indigent. Another reason for this growth in the number of indigent customers is attributed to the influx that has been experienced, wherein people leave rural areas in search of better jobs and services, only to realize that there are no jobs even in the urban areas. These people thus become a cost to Council in that they apply for indigent aid; this in turn increases our indigent customers. This explanation as provided seeks to address the MEC’s comment about no justification being given for the growth in indigent customers. Mpofana has an approved indigent register. As it stands there are 3200 registered households on the indigent register. In terms of monetary value, there is R350 000 allocated for indigent support. The table below shows an indication in the increase of indigent support over the last three years.

| YEAR | NUMBER REGISTERED | COMMENT(S) |
| --- | --- | --- |
| 2015/16 | 1358 | It appears that over the last 3 years the indigent support is growing in terms of numbers. The reason for this increase has been explained in the afore-mentioned paragraphs. |
| 2016/17 | 2500 |  |
| 2017/18 | 3200 |  |

It can be seen from the above table that there is an indication of the increase of indigent support over the last three years.  People with disabilities have undoubtedly benefitted from the Municipality in that there is a budget that has been set aside to that effect. It is also worth mentioning that a Disability Forumis in place and enjoys the full support of the Municipality.

### C.6.3. Revenue Raising Strategies

We have based our expenditure estimates on the presumption that more effort will be made to enforce Councils credit control policy. The municipality will be commissioning the vehicle testing centre in the future as well as the weight bridge. What will be pursued is ensuring that Mooi River is the next destination for all government services departments.

The main goal of Mpofana municipality is to create an economic environment in which investment can grow and jobs can be created.  Increase in employment opportunities will result in empowered citizens who take full responsibility to pay for basic services and improved municipal revenue. We want to attract big corporations to establish their industries in Mpofana. We want to encourage those sectors where we have a competitive advantage, like the agro-processing, tourism retail and the golf estate, to expand in the municipality.

These are some of the actions that have been taken to maximise revenue collection:

Disconnection of all illegal connections

Sending out notices and letters of demands to all our debtors

Liasing with  bulk customers based on the age analysis to prevent the accumulation of debt

Liasing with the Farmers association and Resident’s association in locating and identifying customers owing the Municipality

Employment of a pool of debt collectors to recover monies owed to the Municipality for rates

The Municipal Manager takes full responsibility for the collection of all debt and meets them for payment plans

All Municipal employees pay for their rates, electricity and refuse

Notices accompanying pay-slips to all employees warning them of consequences for non-payment of services

Debt Collectors are now appointed which is a strategic appointment; this will go a long in addressing revenue generating challenges.

- The above strategies are assisting the Municipality in terms of revenue collection, although the Municipality is still pursuing other means of revenue generation. .

Expenditure Reduction

The following have thus been done so as to reduce expenditure

The Municipality has drastically cut its budget for the 2017/18 financial year through the support of the Provincial Treasury.

It has been ensured that employees function optimally during normal working hours to limit expenditure on overtime

Load shedding for households has since been introduced

Introduction of energy efficiency lighting and ensuring that air conditioners and office lights are switched off after hours

Reduction of overtime, No overtime is paid unless it was pre approved by the relevant Head of Department

Usage of Municpal Vehicles is closely monitored to ensure that there is no abuse

Cash-Flows monitored to ensure that it is in line with available funds

A financial recovery committee is thus in place and is attended by both COGTA and Provincial Treasury.

### C6.4. Debt Management

Ideally the municipality should have the cash and cash equivalent on hand to meet at least the current liabilities, however, if the Municipality under collects its revenue this will lead to serious financial challenges for the Municipality. As part of the long term financial planning objectives the Municipality’s liquidity ratio (ability to utilize cash and cash equivalents to extinguish its current liabilities immediately) needs to be set at a minimum of 1.

.

### C6.5. Financial Management

### C.6.5.1 SCM FUNCTIONALITY OF THE SCM

SCM is functional with the Bid Committees all functional, there are some delays that take place in terms of appointing service providers. It is true that some Appointments don’t always take place within 90 days as per legislation. The Municipality has however developed a tender policy implementation plan as an internal control to avoid any delays in terms of meeting timelines.

### Alignment of Procurement Plan with SDBIP

At the beginning of the 2016/17 financial year, a Procurement Plan (Demand Management Plan) was developed. The basis of the Procurement Plan was the SDBIP, which was used for extracting projects. Every care was taken to ensure that there is alignment between the SDBIP and the Procurement Plan.

### Challenges with the SCM Unit

There are no major challenges with SCM, except the timely appointment of Service Providers to undertake project, but as mentioned in the preceding paragraphs, a tender policy implementation plan has been developed which addresses the aforesaid challenge.

### BID COMMITTEES

The table below indicates the Bid Committees namely the Specification Committee, The Evaluation Committee and the Adjudication Committee. The current Bid Committees are in effect

BID SPECIFICATION COMMITTEE

| NAME | ID NO: | POSITION | DEPARTMENT |
| --- | --- | --- | --- |
| Terrence Subriman | 520807 5124 085 | Chairperson | Budget and Treasury |
| Thandi G Cele | 840123 0310 080 | Member | Budget and Treasury |
| Cyril L Ndlovu | 850228 5119 084 | Member | Infrastructure |
| Mhlengi Sithole |  | Member | Social and Economic Services |
| Walter Sithole |  | Member | Technical Services |

BID EVALUAITON COMMITTEE

| NAME | ID NO: | POSITION | DEPARTMENT |
| --- | --- | --- | --- |
| Mtshezi Mkhize | 861116 5947 082 | Chairperson | Office of the MM |
| Prudence Maharaj | 870319 9546 087 | Member | Budget and Treasury |
| Sanele S Sithole | 90030 6597 085 | Member | Budget and Treasury |
| Khethiwe M Buthelezi | 82121 4047 8085 | Member | Budget and Treasury |
| Cyril L Ndlovu | 850228 5119 084 | Member | Infrastructure |

BID ADJUDICATION COMMITTEE

| NAME | ID NO: | POSITION | DEPARTMENT |
| --- | --- | --- | --- |
| Pitso Molefe | 871125 6099 080 | Chairperson | Budget and Treasury |
| Patrick PS Zamisa | 771001 5449 082 | Member | Technical Services |
| Bongiwe B Mchunu | 710519 0369 082 | Member | Community Services |
| Stanely B Ngubane | 751020 5424 089 | Member | Corporate Services |

Government grants have been recognized as income over the periods necessary to match them with the related costs.The following grants will be received from national government over the next three years.

| Grant Description | Budget 2017/18 | Budget 2018/19 | Budget 2019/20 |
| --- | --- | --- | --- |
| Equitable Share | 29 225 000 | 31 700 000 | 32 472800 |
| Finance Management Grant | 1 800 000 | 1 950 000 | 2 074 800 |
| Municipal systems Improvement grant | 934 000 | 967 000 | 1 028 000 |
| Provincial Library | 735 000 | 778 000 | 819 000 |
| Museum | 299 000 | 314 000 | 331 000 |
| Community library services | 126 000 | 132 000 | 359 000 |
| Total Operating grants | 28 752 000 | 31 841 000 | 34 085 488 |
| INEP | 5 000 000 | R6 000 000 | R 5000 000 |

Other Grants that will be allocated to the municipality are: MIG R 12 164 000, Small Town Rehabilitation Which is R3 000, 000.

THE 2017/2018 PROJECTED EXPENDITURE

| ITEM | BUDGET | SOURCE OF FUNDING |
| --- | --- | --- |
| REPAIRS AND MAINTENANCE | R1, 869, 000 | INTERNAL BUDGET |
| ROAD MAINTENANCE | R1, 200, 000 | INTERNAL BUDGET |
| STHEMBISO TO CABAZINI (WARD 3) Phase 2 | R2 432 000 | MIG |
| UPPER TOWN REHABILITATION Phase 3 | R2 432 000 |  |
| MANGAUNG ACCESS ROAD (WARD 1) Phase 2 | R 2 432 000 | MIG |
| MGQULA GRAVEL ROAD | R 2 432 800 | MIG |
| HIGHOVER (WARD 2) | R2 432 800 | MIG |
| MOOI-RIVER TESTING ROUTE | R 3 000 000 |  |
| REFUSE COLLECTION | R1 250 000 | INTERNAL BUDGET |
| PARKS | R150, 000 | INTERNAL BUDGET |
| LIBRARY SERVICES | R 808, 000 | DEPT. OF ARTS AND CULTURE |
| LED | R 300 000 | INTERNAL BUDGET |
| MUSEUM | R 300 000 | DEPT. OF ARTS AND CULTURE |
| SOCIAL SERVICES | R 600 000 | INTERNAL BUDGET |
| PUBLIC PARTICIPATION | R 70 000 | COGTA |
| REAL ESTATE | R 50 000 | INTERNAL BUDGET |

Salaries and wages account represents 25% of the total 2017/2018 operating expenditure. Our projections were based on an increase in the staff complement together with an estimate of annual increases.

In projecting future increases in salaries, we have used the following percentages:

| 2017/2018 | 8.48% for all employees |
| --- | --- |
| 2018/2019 | 6.2% for all employees |
| 2019/2020 | 5.9% for all employees |
| 2020/21 | 6,00 for all employees |

Council bargains directly with the Unions regarding the salary increases. We have assumed that there will most probablY be an element of salary equalization between management and the other employees in the future. Actual result in comparison to prior years will show a dramatic increase due to the implementation of the new wage curves and task grades.

### C.6.5.2 Budget and Treasury OFFICE

There are 25 people that are employed in the Budget and Treasury Office, all of which have undergone the MFMP training and certified as competent. The use of financial consultants has been avoided including the compilation of financial statements. In the 2016/16 financial year COGTA did provide support in the compilation of Financial Statement for auditing. The are vacancies that are to be filled in the 2017/18 financial year for middle managers in the Finance section. These are the Budget Manager, the SCM Manager and the Expenditure and Income Manager. In terms of separation of duties the Municipality has had challenges. Financial consultants have not been used.

### C.6.5.3 TECHNICAL SERVICES

The post of Technical Services is filled and this has been the case for the past 2 years, the Municipality is better positioned to drive service delivery. The Technical Services department does have vacancies but the vacancies that exist are not critical ones and have no impact on the department’s ability to carry out projects and drive service delivery. There is no impact that is caused as a result of the vacancies in the achievement of projects. The Municipality has benefited from additional grant funding based on it spending patterns.  Communication between Technical Services and the Budget and Treasury Office is ongoing in terms of projects. No payments are made without Technical Services having not seen progress on the actual work carried out. In that way communication between the 2 departments is there and a synergy does exist.

### C.6.5.4 ASSETS AND INFRASTRUCTURE

If assets are managed correctly, it ensures that costs are saved and longer life spans of the assets. With the position of the Asset Control Officer, the Municipality ensures that the implementation of an integrated asset management system and management of the system is current and accurate. The Asset Control Officer ensures that proper investigations, identification and implementation of a suitable integrated asset management system. It also includes the capture of all assets onto the system, the maintenance of this system and the production of a complete asset register in terms of the GRAP requirements. Currently the financial interns are assisting in checking the asset register and ensuring that it is properly maintained

### C.6.5.5 REPAIRS AND MAINTENANCE

1 606 000/ 152 177 X 100= 1%

The 1% as calculated indicates that Mpofana has not met the norm which is 8%. It is a challenge. When the Municipality is engaged on its s72 Report in January 2018 this will be looked into, and the percentage allocated on repairs and maintenance will likely be increased.

An asset Register is in place and an Asset Management Policy is in place. The policy sets out the implementation of repairs and mantainance, acquisitions, disposals and depreciation. An asset renewal plan is indeed supported with an operations and maintenance plan and is feasible. The plan is budget bound and has a budget towards repairs and maintenance. The budget as it stands has forecast that1% as per the norm has been set aside. There is a budget of Repairs and Maintenance that has been set aside, this has been placed at 1%.

### C.6.5.6 FINANCIAL RATIO’S

|  | FINANCIAL CONTROL DASHBOARD OVER A PERIOD OF THREE YEARS |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Financial Ratios | Formula | Norm | FY 2015 | FY 2016 | FY 2017 | Comments |  |  |  |  |
| 1. Capital Expenditure to Operating Expenditure | Total Capital Expenditure/Total Expenditure *100 | 10%-20% | 6% | 8% | 10% |  |  |  |  |  |
| 2. Repairs and Maintenance as a percentage of PPE | Total R&M /PPEand Investment Property *100 | 8% | 1% | 1% | 1% |  |  |  |  |  |
| 3. Debtors Collection rate | Gross debtors Opening balance +Billed Revenue -Gross Debtors Closing balance -Bad debts written off/ billed revenue *100 | 95% | 40% | 55% | 69% |  |  |  |  |  |
| 4. Net Debtors Days | ((Gross debtors -Bad Debt Provision)/billed revenue)) *365 | 30 days | 200 days | 550 days | 642 | High amount of old debt that is irrecoverable and prescribed debts |  |  |  |  |
| 5. Cash/Cost coverage (Months) | ((Cash and Cash equivalent- Unspent grants - Overdraft) + Short term investment/Monthly fixed operational expenditure excluding Depreciation, amortisation and provisional for bad debts, Impairments loss on disposal of assets | 1-3 Months | -3 | -3 | -3 | Unauthorised expenditure |  |  |  |  |
| 6.Current Ratio | Current Assets /Current Liabilities | 1.5 -2.1 | 0.25 | 0.62 | 0.78 | Non payment of outstanding creditors within legislated timeframe due to cash flow problems |  |  |  |  |
| 7. Capital costas % of Operating Expenditure | Capital Cost (Interest paid and redemption) /Total Operating Expenditure *100 | 6%-8% | 1% | 1.2% | 1.17% |  |  |  |  |  |
| 8.Total borrowings as % of Revenue | Debt (Short term Borrowing + Bank overdraft +Short term lease +Long term Lease)/Total operating revenue -Operating conditional grants | 45% | 1.2% | 1.32% | 1.38% |  |  |  |  |  |
| 9. Net operating Surplus margin | (Total operating revenue -Total operating expenditure)/Total operating revenue *100 | = or > 0% | 2% | 5% | 6% |  |  |  |  |  |
| 10. Revenue Growth (%) | Period under review's Total Revenue -Previous Period total Revenue/Previous Period Total Revenue)*100 Excluding Capital Grants | CPI | -13 | -15 | -18% | High rate of electricity theft and lack of credit controls. Comparison is for 12months versus 9 months |  |  |  |  |
| 11.Creditors payment period (Trade creditors) | Trade Creditors/Credit Purchases (operating and Capital) *365 | 30 days | 90 days | 158 days | 186 | Non payment of outstanding creditors within legislated timeframe due to cash flow problems |  |  |  |  |
| 12. Irregular, fruitless and wasteful & Unauthorised expenditure /Total Operating expenditure | Irregular, fruitless and wasteful & Unauthorised expenditure /Total Operating expenditure *100 | 0% | 1% | 1% | 1% |  |  |  |  |  |
| 13. Remuneration as % of Total operating expenditure | Remuneration (Employee related + Councillors remuneration) /Total expenditure *100 | 25%-40% | 15% | 25% | 27% |  |  |  |  |  |
| 14.Contracted Service % of Total expenditure | Contracted services/Total operating Expenditure | 2%-5% | 2% | 3% | 4% |  |  |  |  |  |
| Net Surplus/Deficit Electricity | Total Electricity Revenue Less Total Electricity expenditure/Total Electricity Revenue*100 | 0% - 15% | -20% | -27% | -25.90% | High level of electricity theft, Ageing infrastructure |  |  |  |  |
| Net Surplus/Deficit Refuse | Total Refuse revenue Less Total Refuse Expenditure /Total Refuse Revenue *100 | '= or > 0% |  |  | 0 | 2296+ 2347978,68 |  |  |  |  |
| Electricity Distribution Losses (%) | (Number of Electricity Units Purchased and/or Generated - Number of Electricity Sold)/ Number of Electricity Units purchased and/ or generated | 7% - 10% | 18% | 25% | 27.72% | High level of electricity theft, Ageing infrastructure |  |  |  |  |

### C6.6. Loans/  Borrowings and Grant Dependency

The Municipality has not budgeted for any borrowings for the current financial year and will not consider any loans. The Municipality is in no position to afford frontloading. The Municipality heavily relies on grants in meeting its service delivery mandate.  All Capital Projects are funded by Grants, hence the dependency on grants by the Municipality is at maximum. It is worth mentioning that without grants, the Municipality will not be able to meet its service delivery mandate.

### C6.7. Expenditure Management

The Salaries and wages account represents 31% of the total 2017/2018 operating expenditure. Our projections were based on an increase in the staff complement together with an estimate of annual increases.

In projecting future increases in salaries, we have used the following percentages:

| 2017/2018 | 7,4% for all employees |
| --- | --- |
| 2018/2019 | 7,4% for all employees |
| 2019/2020 | 7,4 for all employees |

Council bargains directly with the Unions regarding the salary increases. We have assumed that there will most probably be an element of salary equalization between management and the other employees in the future.

Based on these projected increases in salaries, the Municipality is in a position to meet its operational expenses over the next year.

### C.6.8 AUDITOR-GENERAL’S OPINION

The table below depicts the Auditor General’s Opinion over the last 3 years. It should be said that the Municipality has not fared well in as far the Auditor General’s opinion is concerned.

| AUDITOR GENERAL’S OPINION |  |  |
| --- | --- | --- |
| 2013/14 | 2014/15 | 2015/16 |
| Annual Financial Statements-Unqualified Audit Opinion Annual Performance Report – Unqualified Audit Opinion | Annual Financial Statements-Qualified Audit Opinion Annual Performance Report – Unqualified Audit Opinion | Annual Financial Statements-Disclaimer Annual Performance Report – Unqualified Audit Opinion |
| MEASURES TO ADDRESS THE NEGATIVE AUDIT OPINION 2015/16 |  |  |
| An Audit Action Plan has been developed, submitted to the Auditor General, Audit Committee, Council and MPAC (The oversight structure to the Council. An Audit Steering Team which the Mayor is a part of is functional. There are dedicated teams that look at each item which led to a disclaimer and are reporting on progress monthly. Audit Committee meetings are being held on a regular basis to keep the Audit Committee abreast with progress being made in dealing with the issues that led to the disclaimer in the 2015/16 financial year. An audit Improvement plan has been developed and is attached to this IDP. As a norm the Audit Committee meets to monitor progress with the implementation of the Audit Improvement Plan. |  |  |

### C6.9. Supply Chain Management (SCM)

The municipality applies strict supply chain management principles in advertising and awarding tenders. Strict controls in place ensures that the MFMA is adhered to and to prevent any fraudulent activities from occurring. The Municipality will ensure that we do not do business with entities owned by people working in the public sector this will be in contravention of the MFMA. The Mpofana Municipality has an SCM policy in place. There is a great need for staff outside of the Finance department to be educated on the policy and procedures of the the MFMA. It should also be mentioned that the Municipality does have a bid committee that is functional and ensures that the Municipality complies with all legislative frameworks in awarding tenders and in the selection process.

The Bid Committees have been established and are all functional and as per our SCM policy they have been delegated with the authority of ensuring that SCM processes move smoothly by the Municipal Manager.

uMgungundlovu District Projects

2017/18 UMGUNGUNDLOVU WATER AND SANITATION PROJECTS IN MPOFANA

| PROJECT NAME | WARD | BUDGET |
| --- | --- | --- |
| Upgrading of Rosetta water supply | 2 | R 29 239 079.00 |
| Upgrading of Thendele Water supply scheme | 2 | R 13 923 000.00 |
| Upgrading of Phumlas Water Reticulation scheme | 1 | R 26 757 949.80 |
| Upgrading of Mooi River bulk mains | 1 | R 5 440 503.10 |
| AC Pipe Replacement and Upgrading in Mooi River | 1 | R 44 795 155.09 |
| Ebuhleni Water Scheme (Project has since been suspended due to an unresolved issue with a community member) | 4 | R 3 404 380.00 |
| Mpofana Bulk Supply | 1 | (No expenditure to Date) |
| Muden Water Supply | 4 | Approx R512 ,910,784,32 |
| Construction of a bulk sewer pipeline including a waste water treatment works. | ALL | R 12 333 516.91 |
| Construction of VIP sanitation | 4 | R 20 573 328 |

uMngeni Water Projects IN MPOFANA 2017/18 FINANCIAL YEAR

Table 1	Progress on the projects Umgeni Water is implementing for the Umgungundlovu family of municipalities (9 May 2016).

| Strategic Integrated Project (SIP) | PGDS GOALS | KZN PGDP Strategic Objective | Umgeni Water Projects in Mpofan | Progress to Date (as of April 2016) | BUDGET (subject to review) | LOCALITY |
| --- | --- | --- | --- | --- | --- | --- |
| SIP 18 - Water and Sanitation | Goal 4: Strategic Infrastructure | Strategic Objective 4.5: Improve Water Resource Management and Supply | Greater Mpofana Bulk Water Supply Scheme Sustained housing development and tourism related activities are increasing the water demands at several nodes along the Mooi River – Lions River corridor. This growth is beginning to stress local water resources and water supply infrastructure in the area. It has been identified that a regional bulk water supply scheme is required to ensure that the area has a reliable water supply that will sustain this growth into the future. | In construction/tender. Anticipated date of completion is Jan 2019. | Total Project Cost for Phase 1: R615,487,000 (subject to review). Budget (subject to review): 2016/2017 - R191,115,000 2017/2018 - R186,329,000 2018/2019 - R46,446,000 2019/2020 - R12,570,000 2020/2021 - R73,140,000 | Wards 2 and 3 of Mpofana Municipality and Ward 3 of uMngeni Municipality. |

It should also be mentioned that uMgungundlovu has now handed over the Mooi-Mpofana Water Treatment Plant over to uMngeni Water, the treatment and purification of Water is now the responsibility of uMngeni Water which was previously being handled by uMgungundlovu District Municipality.

### C6.9Financial Viability & Management: SWOT Analysis

| STRENGTHS | WEAKNESSES |
| --- | --- |
| Electricity distributor SCM Policy in place Credit control and debt collection policy in place MFMP Training complete by all Finance Staff Revenue Raising Strategies in Place | Some inexperienced staff in the Finance Department Vacancies in the Finance Department Creditors payment period Billing of Creditors on time |
| OPPORTUNITIES | THREATS |
| Implementation of strategies for the attraction of investors to increase rate base. Support of Treasury in providing Warm Bodies Established Oversight Committees within the Municipality (MPAC and Internal Audit Unit) | Electricity distribution losses Unemployment Cash flow fluctuations Non-payment of rates and services charges Illegal Connections Electricity Theft |

The Swot analysis compares to financial management in this reviewed IDP. It must be pointed out that the crippling factor for this KPA as can be seen in the SWOT analysis is the non-payment of services by the community, illegal connections and electricity theft. All these challenges have been pinpointed and going forward Management and Council should look at unlocking these weaknesses. Internally a lot still needs to be done in terms of billing the customers on time and billing them correctly. Some level of support has been enjoyed from Treasury and COGTA by the Finance Department. The post of the CFO having been vacant for over a year is one of the challenges that has faced the Munipality, but there has been an acting appointment in the position.

## C7. Good Governance & Public Participation

### C7.1. Good Governance Analysis

The Municipality does have a Batho Pele Policy that is enforceable and a Procedure Manual. A Service Delivery 	Charter and Standards has also been developed. A Service Delivery and Budget Implementation Plan has also been developed, presented by the Mayor as a draft in Marh and approved by the Council at the end of May. The Plan is attached under section G of this Plan. The Municipality has identified the services that are to be improved in the 2017/18 financial year. The table below outlines the services that are to be improved.

| Service to be improved | How to improve |
| --- | --- |
| Delivery of Houses | Engage Human Settlement about the slow implementation of Housing Projects including the District Municipality who are responsible for Bulk Water Supply |
| Improved Roads | A realistic budget for Repairs and Maintenance has been set aside so that our existing roads will be well maintained. |
| Customer Services | A more open and accountable Public Institute is a commitment that the Municipal Council and Management including Staff has agreed on and daily that is the goal that all stakeholders of Mpofana are seeking to achieve. |

In general, corporate governance is perceived as a normative principle of administrative law, which obliges any institution to perform its functions in a manner that promotes the values of efficiency, non-corruptibility, and responsiveness to civil society.   In the Mpofana Municipality, The principle of good governance has also been espoused in the context of the internal operations of both the public and private sector organisations. In this way, corporate decision-making strategies integrate the principle of good governance and ensure that public interests and employees are taken into account.

#### C7.2 National & Provincial Programmes

Operation Sukuma Sakhe which is a Provincial Programme has been well received in Mpofana, All section 56 Managers have been deployed to all the Wards, so as to attend to Sukumasakhe, This is where Government Departments are invited so they provide the needed interventions, as per community needs. War Rooms are also functional with each Head of Department dedicated to one War Rooms. Interventions by the relevant Government Departments are being rolled out.

C7.1.3.1 INTER-Governmental Relations (IGR) in the District

The Office of the Municipal Manager has been tasked to deal with the Intergovernmental Relations and to mantain the already existing relations. The Municipality enjoys good relations with Human Settlement, Department of Social Development, SASSA, IEC and Home Affairs. Mpofana Municipality participatesintheProvincialandDistrictMIGforum.Theseforums provide a platform forengagement on the approval of projects and for coordination and monitoringof expenditureon projects which were previously funded under  Municipal Infrastructure Grant projects.

uMgungundlovu District has adopted a Cluster Model  to share best practices amongst its Local Municipalities.  These clusters are chaired by the Municipal Managers of all participating Municipalities.

Mpofana’s Accounting Officer has been tasked with chairing the District Area Finance Forum (DAAF)

The Municipality also has entered into shared services on the following functions: Internal Audit, Development and Planning Services and Geographic Information System (GIS).

TheMunicipalityalsoparticipatesintheProvincialHousingCoordinatingforumwherepartieslookinto the HumanSettlement Grantfunded projects, basedontheallocationgrantedfortheprovince.

UMgungundlovu District Cluster

The Cluster Model has led to the establishment of shared services in the District, which also lead to better utilisation of resources. Shared services are now used in the fields of Internal Audit, Performance Management, Integrated Development Planning and Information and Communications Technology. This approach is having the effect that the families of Municipalities in the District are all benefiting from the scarce resources and expertise available within the District. Each cluster is chaired by municipal Managers as indicated below:

Figure 10: IGR Structure

C.7.3.2 Participation at Provincial Forums

The Municipality does participate in Provincial Forums like the Premier’s Co-ordinating Forum and Munimec. The Municipality further participates in the Public Participation Practitioners Forum and many other forums. The Mayor participates in the Munimec and the MM participates as well an the attendance has been satisfactory.

C.7.3.3 igr official

The Municipality does not have a dedicated IGR Official but the function rests with the Office of the Municipal Manager.

C.7.4Municipal Structures COUNCIL, MPAC AND WARD COMMITTEES

C.7.4 Council

Mpofana has a council that meets as per legislation and whenever necessary, The Mayor is a chairperson of the Council, for full council meetings and special council meetings.

C.7.4 MPAC

The Municipality has a Municipal Public Accounts Committee that plays an oversight role to Council, besides playing the oversight role, one of their duties include facilitating the Public Hearing for the Annual Report. It meets and reports to Council, One of the Councillors is chairperson of the MPAC.  Mpofana’s MPAC consists of 3 Councillors and 2 outsiders who have been co-opted in this committee owing to their knowledge on financial issues and governance issues.

c.7.4 Ward Committees

In terms of the Municipal Structures Act, the objective of Ward Committees is to enhance participatory democracy within the local government sphere.

The Mpofana Municipality consists of five wards, (Athough the fifth ward has recently been added to the four as per the demarcation’s decision) each represented by ten ward

committee members. This IDP was approached through a Ward based participation process. Each ward was represented by ward committee members whereupon different needs for each constituency were noted and included in this document. These input formed the basis for the development of this document. Cogta Public Participation Unit has been instrumental in ensuring that our Ward Committees were revived, the respective Ward Councillors are Chairpersons of the established Ward Committees.

The Ward Committees are therefore functional and this has been confirmed by the COGTA Public Participation Unit, that verifies the submitted information by Municipalities in as far as their Ward Committees are concerned.

IDP Rep Forum

This forum deals with Sector alignment forum was conducted at the municipality whereupon departments made their presentation to the municipality of their programmes and projects for the next financial years. The 2017/2018 IDP programmes by the sector departments have been incorporated into the IDP. The IDP Rep Forum consists of our stakeholders namely, Government Departments, Ward Committees, NGO and NPOs. Our IDP Rep Forum has also seen the involvement of iNkosi Mchunu the Traditional leader, who in turn participates in Council Meetings.

C.7.6 IDP Steering Committee Team

The IDP Task Team recommended that a simplified and implementable IDP be developed in line with the COGTA Framework Guide in order to achieve an effective IDP which engages community needs from a grass root level.

It is headed by the Municipal Manager and the role of the IDP Manager like in the IDP Rep Forum is to provide secretariat services to the committee. The HODs are participants to the IDP Steering Committee.

c.7.7 management Structures MANCO AND PORTFOLIO COMMITTEES

The Municipality hasMANCO bi-weekly that meets to discuss strategic issues per department, once resolved these are then escalated to Portfolio Committees. The Municipal Manager chairs management meetings, sometimes there are extended MANCO Meetings wherein line managers are invited to these meetings. Mpofana also has functional portfolio committees, namely the Infrastructure Portfolio Committee, The Finance Portfolio Committee, The Community Portfolio Committee and the Governance Portfolio Committee. The Committees are responsible for deliberating on issues before they are brought to council and make recommendations to Council, Councillors serve as Chairperson of the Portfolio committees, the respective Managers are also part of the Portfolio Committees.

C.7.8 COMMUNICATION PLAN OR STRATEGY

The Municipality has an adopted Communication plan and Strategy

The Municipality does have an adopted Communication Strategy in place for public Participation. The plan will further be reviewed in the 2017/18 financial year.

C.7.9.1 Internal AUDIT UNIT

The Municpiality has definetly boosted its middle management Staff Complement, this is evidenced by the recent appointment of the Internal Audit Manager and the Internal Audit Clerk. The Internal Audit Unit reports to the Audit Committee quarterly.

C.7.9.2 THE AUDIT COMMITTEE

The Audit Committee is an independent body which is tasked with advising Council on Performance and Financial matters of the Municipality. The municipality has a functional audit committee, with three external members. They perform the tasks of an audit committee as per Section 166 of the Municipal Finance Management Act no. 56 of 2003. The Audit Committee also serves as a Performance Audit Committee, it reports to Council at least twice a year, but given the recent audit outcome, the audit committee has had to report to Council on more than 2 occasions.

### C7.10.1 Municipal Risk Management

The municipality has conducted a municipal risk management exercise whereabouts all the risks at different levels were identified and through that exercise, the municipality will be able to develop a clear strategy (IDP) that responds to the current situation.

Section 62 (i) of the MFMA requires that the municipality has and maintains an effective, efficient and transparent system of risk management.     The Municipality undertook to implement and comply with this section and this resulted in the development of the Risk Action Plan through a workshop which was held near the end of the 2016/17 financial year with the assistance of Internal Audit Activity.  A risk register was compiled and approved by the Audit and Performance Management Committee. Furthermore a Risk Management Strategy was developed which has since been approved by Council and is monitored quarterly.

### C.7.10.2 ANTI-FRAUD AND ANTI-CORRUPTION STRATEGY

The Municipality has an anti Fraud and Anti Corruption Strategy that is enforceable and is approved by Council. The Municipality has further established the Whistle Blowing Policy.

### C.7.10.3 Risk Management Committee

The Risk Management Committee is established and functional, the below table shows the members and the Departments they are working under.

| Risk Management Member name | Department |
| --- | --- |
| Mr Max Moyo | Office of the Municipal Manager |
| Mr Steady Zamisa | Technical Services |
| Mr Bongani Ngubane | Corporate Services |
| Mrs B Mchunu | Social Services |
| Mr P Molefe | Budget and Treasury Office |
| Mr Mtshezi Mkhize | Office of the Municipal Manager |
| Mr Mfanafuthi Mkhize | Internal Audit |

### C.7.11 Council adopted Municipal Policies

#### C7.1.5. Status of Municipal Policies

Municipal Policies

| Policies | Developed (Yes/No) | Adopted (Yes/No) | Reviewed (Yes/No) |
| --- | --- | --- | --- |
| Street Naming Policy | Yes | Yes | Yes |
| Credit Control & Debt Collection Policy | Yes | Yes | YES |
| Tarrif Policy and Notices | Yes | Yes | Yes |
| Whistle Blowing Policy | Yes | Yes | Yes |
| Compliants Management Policy | Yes | Yes | Yes |
| Communication Strategy Policy | Yes | YES | YES |
| Overtime Policy | Yes | Ye s | No |
| Fraud Prevention Strategy | Yes | Yes | YES |
| Human Resource Strategy | Yes | Yes | Yes |

### C.7.12Municipal By-laws

The municipality has By-laws that have been adopted by council but areyet to be gazetted.

Table 15 Municipal By-Laws

| Name of Bylaw | Reviewed | Approved | By- Law Gazetted (Yes/No) |
| --- | --- | --- | --- |
| Encroachment | No | Yes | No |
| Credit Control | Yes | Yes | No |
| Tariffs | Yes | Yes | No |
| Keeping of Animals | No | Yes | No |
| Advertisement | No | Yes | No |
| Street Trading | No | Yes | No |

The Municipality has set aside a budget which will be used to gazette some of the approved by-laws. Animal Keeping Bylaw is a priority one, which will see the Municipality working hand in hand with SPCA to safe-guard against stray animals that seem to be loafing around the town area.

### C.7.14 MUNICIPAL PUBLIC ACCOUNTS COMMITTEE

BID SPECIFICATION COMMITTEE

| NAME | ID NO: | POSITION | DEPARTMENT |
| --- | --- | --- | --- |
| Terrence Subriman | 520807 5124 085 | Chairperson | Budget and Treasury |
| Thandi G Cele | 840123 0310 080 | Member | Budget and Treasury |
| Cyril L Ndlovu | 850228 5119 084 | Member | Infrastructure |
| Mhlengi Sithole |  | Member | Social and Economic Services |
| Walter Sithole |  | Member | Technical Services |

BID EVALUAITON COMMITTEE

| NAME | ID NO: | POSITION | DEPARTMENT |
| --- | --- | --- | --- |
| Mtshezi Mkhize | 861116 5947 082 | Chairperson | Office of the MM |
| Prudence Maharaj | 870319 9546 087 | Member | Budget and Treasury |
| Sanele S Sithole | 90030 6597 085 | Member | Budget and Treasury |
| Khethiwe M Buthelezi | 82121 4047 8085 | Member | Budget and Treasury |
| Cyril L Ndlovu | 850228 5119 084 | Member | Infrastructure |

BID ADJUDICATION COMMITTEE

| NAME | ID NO: | POSITION | DEPARTMENT |
| --- | --- | --- | --- |
| Pitso Molefe | 871125 6099 080 | Chairperson | Budget and Treasury |
| Patrick PS Zamisa | 771001 5449 082 | Member | Technical Services |
| Bongiwe B Mchunu | 710519 0369 082 | Member | Community Services |
| Stanely B Ngubane | 751020 5424 089 | Member | Corporate Services |

### C.7.14 MPAC

MPAC continues to play an oversight role on behalf of Council, MPAC has through the COGTA’s support received extensive training so as to be fully equipped to deal with their oversight role. They are responsible for tabling the annual report to the Council and for providing comments and making recommendations to the Council. They are also empowered to look closely on public affairs in the Municipality under the authority of Council.

### C.7.15 PORTFOLIO COMMITTEES

Council Portfolio Committees are structured as per national guidelines and meet once a month. Issues requiring Council resolution are raised for deliberation at portfolio committee meetings. Recommendations are then made to the full Council.

The following are the Mpofana Council Portfolio Committees:

Youth, Economic and Social Services Directorate

Infrastructure and Maintenance Directorate

Budget and Treasury Directorate

Corporate Services Directorate

### Public Participation Analysis

The Muncipality is committed to public participation this is done through a series of community meetings in the different WARDS; operation sukuma sakhe is also used AS A MECHANISM to get the public to participate in the municipal affairs. The Municipality has recently revived its ward committees through cogta’s support. The Service Delivery Protests that have long entangled this Municipality are now a thing of the past. all EFFort is made that all information that needs to be communicated to the Communities is indeed communicated to the community timely. The iNkosi’s participation in council matters has been received warmly and it assists in maximising public participation. idp imbizo meetings which took place prior the adoption of this document saw democracy being deepened in mpofana through the participation and involvement of the community.

### C7.16. Good Governance & Public Participation: SWOT Analysis

| STRENGTHS | WEAKNESSES |
| --- | --- |
| IDP inclusive of the input from all the stakeholders. Risk management strategy in place Committees established A vibrant Community Established Audit Committee Municipal Public Accounts Committee in place | Poor attendance by ward committees Budget Constraints Lack of team spirit Risk, management plan not monitored on a regular basis. |
| OPPORTUNITIES | THREATS |
| IDP reviewed annually and guide decision making and resource allocations Participation of Inkosi in Council Meetings | By-laws not gazette Mis-information being given to the Community |

### C.7.17 DISTRICT Rural Development Plan

The uMgungundlovu District Municipality has undertaken the District Rural Development Plan and has since adopted it

### C.7.18 WARD BASED PLANS

In compiling this plan the Municipality undertook ward based planning across the 5 Wards and each ward has developed its own Ward Based Plans. The priorities as outlined in the Ward Based Plans has been caterd for in the IDP projects, There is a clear alignment between the Ward Based Plans the IDP.

### C.7.19 LAND USE MANAGEMENT

The Municipality has established a Municipal Planing Tribunal and the Town planner sits in the District Municipal Planning Tribunal. The MPT meets monthly. This has been done in keeping with SPLUMA Regulation 14. THE Municipality has indeed appointed a Municipla Planning Authorised Officer. The Municipality has further resolved on the Appeal Authority. Through the COGTA fund the Municipality will amend the delegations from KZNPDA to SPLUMA bylaws, since The Municipality is in line to receive funding. All applications are categorized, the Municipality has further adopted SPLUMA bylaws, the only outstanding task is to gazette the bylaws.

### C.8.1 KEY CHALLENGES PER KPA AND EXPLANATION

### Municipal Transformation &INSTITUTIONAL DEVELOPMENT

The municipality also faces a high rate of staff turnover, which impacts negatively on the ability of the municipality to meet its objectives and targets on time. The downtime during the departure of one employee and recruitment and filling in of the post impacts negatively on service delivery. This has been worsened by the Municipal cash flow situation, which makes it difficult to fill posts including critical ones.

### Basic Service Delivery

It’s a reality that cannot be ignored that there has been slow progress in the delivery of essential services to our community over the last five years and as such this plan serves as a realistic strategy to realising our objectives. The implementation of projects is hindered by the lack of funding available or the planning process where funds are available especially in the area of housing. As a strategy, closer working relations with the different government sectors will be essential, moving forward and COGTA will have to play a major role in formulating closer working relations. The plan has been formulated with the national, provincial, and regional objectives in mind. It is noted with great concern that the backlogs in terms of basic services exist.

### Local Economic & Social Development

There has been a very slow Economic Development Progress and investors shy away from Mpofana due to many inhibiting factors that the municipality currently endeavours to address. Degenerating town characterised by crumbling and dilapidated infrastructure and poorly maintained buildings have contributed to the inability to attract new investors to boost Mpofana economy and create job opportunities and jobs.

### Municipal Financial Viability & Management

Debt collection problems, electrical distribution losses were very high due to electricity theft and unpaid services. The electricity losses have exacerbated cash-flow challenges shortage and financial distress resulting in the municipality not being able to meet its short and long term goals.

### Good Governance & Public Participation

The following are the challenges impacting negatively on good governance:

Poor systems, processes and procedure

Poor monitoring and evaluation of municipal decisions

Poor implementation of municipal by-laws and policies

It is worth mentioning that in comparison to the previous IDP Ward Committee functionality and community participation has improved immensely. Although there is still a need to capacitate Ward Committees in terms of their roles and responsibilities, A training has been scheduled which would assist Ward Committees in executing their duties and responsibilities.

### Cross Cutting

The following are cross-cutting challenges facing the municipality:

Poor land use management systems (LUMS)

Lack of prioritisation of environmental matters (The Municipality has not employed an Environmental management Officer)

### C.8.2 EXPLANATION OF EACH KEY CHALLENGE (SEE THE ABOVE)

### C.8.4 PREVIOUS YEAR PERFORMANCE

This IDP Review has taken into account the performance from the previous year, which the Auditor General found to be credible and verifiable (Performance Report). As a norm the corrective measures have been included where there was no achievement. A column was further added for improved performance.

## C8. Combined Swot Analysis

| STRENGTHS | WEAKNESSES |
| --- | --- |
| Development of the SDF Good commercial agricultural land Clear nodes Electricity distributor Policies in place SCM Policy in place Support from Government Departments. Strong institutional Arrangements in place(Local Task Team and war room are functional) Local Aids Council, Sport Council and Council for the Disabled in place. Mpofana Municipality is strategically located along N3 and an agro-industrial corridor stretching from Pietermaritzburg to Escort. Strong institutional arrangements to promote economic growth, retention and expansion of local business, promoting dialogue between business and the municipality | Poor attendance by ward committees Budget Constraints Lack of team spirit Weak cellphone coverage in some areas Lack of recreational facilities Lack of mobile police stations Poor road infrastructure Lack of access to community facilities Electricity shortages Lack of adequate staff to render service delivery Eskom supply of electricity in rural areas Agricultural viable land not being fully utilised Lack of agricultural skills by farm owners Poor infrastructure development. Lack of capacity to enforce street trading by laws |
| OPPORTUNITIES | THREATS |
| N3 corridor Vacant land Reduction in HIV/AIDs Strong institutional arrangements Accessing grant funding for small town rehabilitation. Public private partnerships Business support and development. Draft investment incentive policy in place. Form partnership with Trade and Investment KZN to promote Mpofana as an investment destination. Increase job opportunities through agro-processing industry and agricultural development. Identify more land for industrial and commercial development. Recruitment for the LED manager is underway. | By-laws not gazetted Crime Prevalence of HIV/AIDs Departments are not fully supporting the programme. Government Departments perceive the programme as additional work. Profiling has not been completed. Lack of proper monitoring and evaluation system. Lack of adequate water, electricity and sanitation. Lack of sport infrastructure affecting youth participation in sport. One garden per household sustainability affected by change in season and lack of adequate water. Slow delivery of houses for vulnerable individuals. Lack of transport for the cadres Slow response by Departments to needs identified through surveys Competition for investors from other neighboring municipalities. High staff turnover within the LED unit |

Key Challenges and how we can address them?

Please see page 13-14 of this document for Key challenges as identified, Please further find the proposals of how we can go about addressing the identified challenges on page16-17 for the opportunities that be which we need to take into cognizance. The challenges, have been derived from the status quo and the solutions respond to the identified challenges.

# Section D: Vision, Goals, Objectives And Strategies

## D1. Long Term Vision

LONG TERM VISION

“By the year 2020, Mpofana will be a sustainable, socially and economically developed municipality, that encourages community participation and whose residents live in a safe and healthy environment. Mpofana will, in addition have substantially increased its contribution to its districts gross domestic product whilst also having realized substantially decreased its share of poverty.”

## D2. Mission Statement

MISSION

“.Mpofana Municipality is to be a pro-active, accountable and financially viable municipality that is continually striving to provide efficient, affordable, sustainable and customer-orientated services - committed to participation principles in the social and economic development of our community”

## D.2.-D4 Goals, Objectives & Strategies

| Ref No. | NKPA | GOAL | Objective | Ref No. | STRATEGY |
| --- | --- | --- | --- | --- | --- |
| A | Municipal Transformation & Institutional Development | To increase organisation capacity | To improve functionality of Municipal Performance Management System | A1 | Implementation of Municipal PMS Policy & Framework |
|  |  |  | Reengineer Organisation to enhance strategic needs. | A2 | Conduct and Implement Organisational design |
|  |  |  |  |  | Implementation of adopted WSP |
|  |  |  | To improve administrative systems and processes | A3 | Development / Reviewal and implementation organisational policies |
|  |  |  |  |  | Develop required administrative system and structures. |
| B | Basic Service Delivery | To increase access to Municipal Basic Services | To improve access to basic services | B1 | Improve access to electricity |
|  |  |  |  | B2 | Improve access to refuse removal |
|  |  |  |  | B3 | Improve access to Roads |
|  |  |  |  | B4 | Improve access to adequate shelter |
|  |  |  |  | B5 | Provision of free basic water sanitation and refuse removal |
|  |  |  |  | B6 | Develop and Implement Infrastructure Maintenance plan |
| C | Local Economic Development | To boost the LocalEconomy | To strengthen the economic environment. | C1 | Develop and Implement strategies to Improve LED. |
|  |  |  |  | C2 | Establishment of partnerships with other stakeholders |
|  |  |  |  | C3 | To promote sustainability of SMMEs and Co-operatives entrepreneurship |
|  |  |  |  | C4 | Creation of Employment opportunities |

| Ref No. | NKPA | GOAL | Objective | Ref No. | STRATEGY |
| --- | --- | --- | --- | --- | --- |
| D | Municipal Financial Management | To increase own revenue | Increase funding and revenue generation | D1 | Financial viability debt recovery ratio |
|  |  |  |  |  | % of Municipal operations funded |
|  |  |  | Improve expenditure and maximise the economies of scale. | D2 | Financial viability cost recovery ratio |
|  |  |  |  |  | SCM performance rating |
|  |  |  | Optimise budgeting and accountability of finances | D3 | % compliance with MFMA calendar |
| E | Good Governance & Public Participation | To achieve a clean audit | To Improve compliance and audit opinion | E1 | Establish and maintain effective audit structures. Resolve AG Audit queries |
|  |  |  | To Improve Municipal Governance | E2 | Development / Reviewal and implementation organisational By-Laws |
|  |  |  | To Improve public participation and awareness | E3 | Ensure Functional community participation structures |
|  |  |  | Improve municipal internal and external communication | E4 | Training and implementation of Batho Pele Principles |
|  |  |  |  |  | Develop/Implement and review communication strategy |
| F | Cross Cutting Issues/Interventions | To increase environmental and community safety and Spatial Equity | To Strengthen Governance and IGR | F1 | Develop partnership with relevant stakeholders |
|  |  |  | To prevent and mitigate the occurrence of disasters. | F2 | Establish Disaster Management Unit. |
|  |  |  |  |  | Facilitation of Disaster Management Awareness campaigns |
|  |  |  |  |  | Improve response to disasters in collaboration with the District Municipality. |
|  |  |  | To promote credible, Strategic and spatial municipal planning | F3 | Develop a Credible IDP |
|  |  |  |  |  | Improved SDF Planning |
|  |  |  | To promote and develop support programmes for Youth and vulnerable groups within the community. | F4 | Support the implementation campaigns directed to Youth and vulnerable groups. |
|  |  |  |  |  | Co-ordinate the implementation of HIV & AIDS Strategy |

### D.5 ALIGNMENT WITH KZN PGDS

The table below shows the alignment between the KZN PGDS and Mpofana Goals

| KZN PGDS Strategic GOALS | Mpofana Goals |
| --- | --- |
| Job Creation | To boos the local economy |
| Human Resource Development | To increase the organization capacity |
| Human and Community Development | To increase organization capacity |
| Strategic Infrastructure | To increase access to Basic Service |
| Environmental Sustainability | To increase Environmental and Community Safety |
| Governance and Policy | To achieve Clean Audit |
| Spatial Equity | To achieve Spatial Equity |

### D.6 GOALS, OBJECTIVES AND KPAs (ALSO SEE TABLE ON D2)

| Mpofana GOALS | Mpofana OBJECTIVES | National KPAs |
| --- | --- | --- |
| To Boost the local economy | Strengthen the Local Environment | Local Economic Development |
| To Increase the organization capacity | Re-engineer Organization to achieve Strategic Goals | Municipal Transformation and Organizational Development |
| To Increase own revenue | Increase funding and revenue generation | Municipal Finance Management |
| To Increase access to Basic Service | Improved Access to Basic Services | Basic Service Delivery |
| To Achieve Clean Audit | Improved Audit opinion | Good Governance and Public Participation |
| To Achieve Spatial Equity | Achieve Spatial Equity | Cross-Cutting Issues |

# Section E: STRATEGIC Mapping & Implementation Plan

## E2. Five (5) Year Implementation Plan

Land Designations

Economic Nodes and Corridors

### E.2 IMPLEMENTATION PLAN

| NKPA 1. |  | Municipal Transformation & Institutional Development |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Outcome 9 Output |  | Differentiated approach to Municipal financing planning and support |  |  |  |  |  |  |  |  |
| Ref No. | Objective | Strategies | Performance Indicator | 2017/18 Target | 2018/19 Target | (2019/20 Target | 2020/21 Target | 2021/22 Target | Funding | Responsibility |
| A1 | To improve functionality of Municipal Performance Management System | Develop Municipal PMS Policy & Framework | Date PMS Policy and Framework Approved | N/A | 31 July | 31 Oct | 31 July | 31 July | Internal | OMM |
|  |  | Implementation of Municipal PMS Policy & Framework | Number of Performance Agreements for Section 56/57 Managers signed | 5 | 5 | 4 | 5 | 5 | Internal | OMM |
|  |  |  | Number of OPMS Quarterly Reports | 4 | 4 | 2 | 4 | 4 | Internal | OMM |
| A2 | Reengineer Organisation to enhance strategic needs. | Conduct and Implement Organisational design | Date Organogram Approved | 31 July | 31 July | N/A | 31 July | 31 July | Internal | Corporate Service |
|  |  |  | Number of signed section 56 contracts | 5 | 5 | 4 | 5 | 5 | Internal | Corporate Service |
|  |  |  | Number of women appointed in Section 54/56 Posts | 2 | 2 | 2 | 2 | 3 | Internal | Corporate Service |
|  |  |  | Number of people from Employment Equity target groups employed in the 3 Highest levels on Management in compliance with approved EE plan | 5 | 5 | 4 | 5 | 5 | Internal | Co-operate Service |
|  |  | Implementation of adopted WSP | Date of completion of skills audit | 30 Jun 2017 | 30 Jun 2018 | 30 Jun 2019 | 30 Jun 2020 | 30 Jun 2021 | Internal | Corporate Service |
|  |  |  | % of Budget spent on implementation of WSP | 100% | 100% |  | 100% | 100% | Internal | Corporate Service |
| A3 | To improve administrative systems and processes | Development / Reviewal and implementation organisational policies | Number of identified policiesdeveloped (new) and approved | 5 | 5 |  | 5 | 5 | Internal | Corporate Service |
|  |  |  | Number of existing policies reviewed and approved | 25 | 30 |  | 35 | 40 | Internal | Corporate Service |
|  |  |  | Number of Policies Implemented | 25 | 30 |  | 35 | 40 | Internal | Corporate Service |
|  |  | Develop required administrative system and structures. | Number of required systems in place | 20 | 22 |  | 24 | 26 | Internal |  |

| NKPA 2. |  | Basic Service Delivery |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Outcome 9 Output |  | Improved access to basic services |  |  |  |  |  |  |  |  |
| Ref No. | Objective | Strategies | Performance Indicator | 2017/18 Target | 2018/19 Target | 2019/20 Target | 2020/21 Target | 2021/22 Target | Funding | Responsibility |
| B1 | To improve access to basic services | Improve access to electricity | Number of Existing consumer units with access to Electricity | 4000 | 4200 | 4400 | 4500 | 4600 | N/A | Tech. Service |
|  |  |  | Number of new consumer units with access to electricity | 13 | 25 | 41 | 49 | 52 | Dept of Energy | Tech. Service |
| B2 |  | Improve access to refuse removal | Number of Existing consumer units with access to refuse removal | 4000 | 4200 | 4400 | 4500 | 4600 | Internal | Tech. Service |
|  |  |  | Number of new consumer units with access to refuse removal | 13 | 25 | 41 | 49 | 52 | Internal | Tech. Service |
| B3 |  | Improve access to Roads | Km’s of Municipal roads maintained in terms of approved Maintenance Plan | 55 | 50 | 75 | 100 | 100 | Internal | Tech. Service |
|  |  |  | Km’s of rural roads re-gravelled | 13 | 25 | 41 | 49 | 52 | Internal | Tech. Service |
|  |  |  | Km’s of new access roads (Gravel or Tarred) constructed | 2 | 2 | 2 | 2 | 2 | Internal | Tech. Service |
| B4 |  | Improve access to adequate shelter | Date of approval housing sector plan | 30 Jun | 30 Jun | 30 Jun | 30 Jun | 30 Jun | Internal | Tech. Service |
|  |  |  | Number of new housing units constructed | 100 | 100 | 130 | 320 | 400 | Internal | Tech. Service |
| B5 |  | Provision of free basic water sanitation and refuse removal | Number of existing households with access to free basic services in terms of the indigent register | 0 | 0 | 0 | 0 | 0 | 0 | Tech. Services |
|  |  |  | Number of new household with access to free basic services in terms of the indigent register | 0 | 0 | 0 | 0 | 0 | Internal | Tech. Services |
| B6 |  | Develop and Implement Infrastructure Maintenance plan | Date Infrastructure maintenance plan approved | 30 Jun | 30 Jun | 30 Jun | 30 Jun | 30 Jun | Internal | Tech Services |
|  |  |  | Number of Municipal Infrastructure maintained timeously. | 3 | 3 | 3 | 3 | 3 | 3 | Tech Services |

| NKPA 3. |  | Local Economic Development |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Outcome 9 Output |  | Differentiated approach to Municipal financing planning and support |  |  |  |  |  |  |  |  |
| Ref No. | Objective | Strategies | Performance Indicator | 2017/18Target | 2018/19 Target | 2019/20 Target | 2020/2021 Target | 2021/22 Target | Funding | Responsibility |
| C1 | To strengthen the economic environment. | Develop and Implement strategies to Improve LED. | Number of LED strategy projects and programmes implemented | 4 | 4 | 4 | 4 | 4 | Internal | SOCIAL |
|  |  |  | Number of tourism strategy projects implemented | 2 | 2 | 2 | 4 | 3 | Internal | SOCIAL |
| C2 |  | Establishment of partnerships with other stakeholders | No of LED Fora Established and functional | 1 | 1 | 1 | 1 | 1 | Internal | SOCIAL |
| C3 |  | To promote sustainability of SMMEs and Co-operatives entrepreneurship | Number of SMME’s and Co-operatives supported and capacitated | 10 | 10 | 10 | 10 | 10 | Internal | SOCIAL |
| C4 |  | Creation of Employment opportunities | Number of jobs created through LED, EPWP and CWP programmes | 65 | 265 | 265 | 265 | 265 | Internal | SOCIAL |
|  |  |  | % of Youth women and disabled employed in LED EPWP and CWP programmes | 5% | 5% | 5% | 5% | 5% | Internal | SOCIAL |

| NKPA 4. |  | Municipal Financial Viability & Management |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Outcome 9 Output |  | Differentiated approach to Municipal financing planning and support |  |  |  |  |  |  |  |  |
| Ref No. | Objective | Strategies | Performance Indicator | 2016/17 Target | 2017/18 Target | (2018/19Target | 2019/20 Target | 2020/21 Target | Funding | Responsibility |
| D1 | Increase funding and revenue generation |  | % Increase in Financial viability debt recovery ratio | 100% | 100% | 100% | 100% | 100% | Internal | BTO |
|  |  |  | % of Municipal operations funded | 100% | 100% | 100% | 100% | 100% | Internal | BTO |
| D2 | Improve expenditure and maximise the economies of scale. |  | % Increase Financial viability cost recovery ratio | 100% | 100% | 100% | 100% | 100% | Internal | BTO |
|  |  |  | % Increase in SCM performance rating | 100% | 100% | 100% | 100% | 100% | Internal | BTO |
| D3 | Optimise budgeting and accountability of finances |  | % compliance with MFMA calendar | 100% | 100% | 100% | 100% | 100% | Internal | BTO |

| NKPA5. |  | Good Governance & Public participation |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Outcome 9 Output |  |  |  |  |  |  |  |  |  |  |
| Ref No. | Objective | Strategies | Performance Indicator | 2016/17 Target | 2017/18 Target | (2018/19Target | 2019/20 Target | 2020/21 Target | Funding | Responsibility |
| E1 | To Improve compliance and audit opinion | Establish and maintain effective audit structures. Resolve AG Audit queries | Number of Audit Committee Meetings held and reports submitted to council | 4 | 4 | 4 | 4 | 4 | Internal | OMM |
|  |  |  | Number of Internal Audit reports submitted | 4 | 4 | 4 | 4 | 4 | N/A | OMM |
|  |  |  | Number of AG Audit queries resolved as per AG Action Plan | 100% | 100% | 100% | 100% | 100% | N/A | OMM |
| E2 | To Improve Municipal Governance | Development / Reviewal and implementation organisational By-Laws | Number of identified By-Laws developed (new) and approved | 4 | 4 | 4 | 4 | 4 | Internal | Corporate Services |
|  |  |  | Number of existing By-Laws reviewed and approved | 4 | 4 | 4 | 4 | 4 | Internal | Corporate Services |
| E3 | To Improve public participation and awareness | Ensure Functional community participation structures | Number of By-Laws Implemented | 4 | 4 | 4 | 4 | 4 | Internal | Corporate Services |
|  |  |  | Number of Community and Ward Committee meetings held | 10 | 10 | 10 | 10 | 10 | Internal | SOCIAL |
|  |  |  | % of attendance by members per ward | 100% | 100% | 100% | 100% | 100% | Internal | SOCIAL |
| E4 | Improve municipal internal and external communication | Training and implementation of Batho Pele Principles | Number of Functional Ward committees | 5 | 5 | 5 | 5 | 5 | Internal | SOCIAL |
|  |  |  | Number of customer satisfaction surveys conducted | 1 | 1 | 1 | 1 | 1 | Internal | Corporate Services |
|  |  | Develop/Implement and review communication strategy | Date Communication Strategy Adopted | 30 June | 30 June | 30 June | 30 June | 30 June | Internal |  |
|  |  |  | Number of Municipal publications | Quarterly | Quarterly | Quarterly | Quarterly | Quarterly | Internal |  |

| NKPA 2. |  | Cross Cutting Issues/Interventions |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Outcome 9 Output |  |  |  |  |  |  |  |  |  |  |
| Ref No. | Objective | Strategies | Performance Indicator | 2016/17 Target | 2017/18 Target | (2018/19Target | 2019/20 Target | 2020/21 Target | Funding | Responsibility |
| F1 | To Strengthen Governance and IGR | Develop partnership with relevant stakeholders | Number of Meetings held / attended | 4 | 4 | 4 | 4 | 4 | Internal | OMM |
|  | To prevent and mitigate the occurrence of disasters. | Establish Disaster Management Unit. | Number of Disaster Management meetings held | 4 | 4 | 4 | 4 | 4 | Internal | OMM |
|  |  |  | Number of Disaster management for a established | 1 | 1 | 1 | 1 | 1 | Internal | OMM |
|  |  | Facilitation of Disaster Management Awareness campaigns | Number of Awareness Campaigns held | 1 | 1 | 1 | 1 | 1 | Internal | OMM |
|  |  | Improve response to disasters in collaboration with the District Municipality. | % of disasters responded to within the stipulated time frames as per Disaster Management Plan | 10 | 10 | 10 | 10 | 10 | Internal | OMM |
| F3 | To promote credible, Strategic and spatial municipal planning | Develop a Credible IDP | Improvement in credibility rating |  |  |  |  |  | Internal | OMM |
|  |  | Improved SDF Planning | Date reviewed SDF Framework | 30 Jun | 30 Jun | 30 Jun | 30 Jun | 30 Jun | Internal | OMM |
|  |  |  | Number of Identified Spatial Development priorities/ Interventions | 3 | 3 | 4 | 4 | 4 | Internal | OMM |
| F4 | To promote and develop support programmes for Youth and vulnerable groups within the community. | Support the implementation campaigns directed to Youth and vulnerable groups. | Number of people benefiting from special programmes. | 54 | 54 | 54 | 54 | 46 | Internal | Social |
|  |  |  | Number of programmes conducted. | 4 | 4 | 4 | 4 | 4 | Internal | Social |
|  |  | Co-ordinate the implementation of HIV & AIDS Strategy | Number of effectively functioning structures | 2 | 2 | 2 | 2 | 2 | Internal | Social |

# Section F: Financial Plan

## F1. Overview

The implementation of the Integrated Development Plan is largely reliant on the efficiency of the financial management system, and a strategy to enhance this capacity is necessary.

The principles, Strategic Financial Framework, the Medium Term Expenditure and Revenue Framework (for the next three years) and Capital Investment Programme, are outlined in this section. The emphasis for the initial year, i.e. 2014/15, is on projects receiving committed funding, and priority projects. It is important for the Municipality to ensure that they source funding for projects in an aggressive way in order to ensure that the implementation process is sustained.

Since the Mpofana Municipality is characterised by a substantial lack of basic services (for the major portion of the Municipality), the emphasis will fall on basic service provision, which could be funded, by all levels of government and service providers. Local economic development should be encouraged as it could have a spill over effect, which would be beneficial to the municipality as a whole, triggering more investment.

Mpofana Local Municipality’s financial plan is compliant to the MFMA, and such its implementation is legal in nature. It does remain a challenge that the Municipality’s financial cries far outweigh the needs that be at Mpofana. This has not prevented the Municipality from coming up with a comprehensive Plan to address the financial challenges. This has been as result of a Revenue Enhancement Strategic Workshop which was held over a 2 day period where some of the financial challenges were identified, and solutions to address the challenges identified were brought to the foe.

The following will be quite important in the implementation of Mpofana’s financial plan.

- It is of vital importance that the municipality has adequate sources of revenue, from both its own operations and intergovernmental transfers, to enable it to carry out its own functions.

- It is important to track the respective sources of revenue received by the municipality as they can be different and vary depending on the period within the financial year. Knowledge of the resources of funds will illustrate the Municipality‟s position more accurately.

- Cash management is crucial for the short and long-term survival and good management of the organization. To assess the financial standing of the municipality, a current ratio will be used which expresses the current assets as a proportion to current liabilities. A current ratio of more than 2:1 is considered to be healthy.

- The Municipality should ensure that the budget is balanced – revenue is greater than the expenditure. Services provided at all levels should be affordable. However, subsidies need to be made available to the indigent who cannot even pay for a quarter of their service costs so that they can have access to at least basic services. That is why one of the outcomes of the Revenue Enhancement Strategic Session was that the Providence of Free Basic Services should commence soon.

- The municipality is responsible to the people who provide the resources, for what they do with those resources. The budget process and other financial decisions should be open to the public`s participation. Also, it is crucial that the accurate information is produced within acceptable time-frames.

- Mpofana Local Municipality must treat people fairly and justly when it comes to the provision of services. In the same way that Mpofana Municipality should be treated equitably by the national and provincial government when it comes to the inter-governmental transfers.

The Municipality has over the years experienced too many electrical illegal connections, hence, a strategy has been put in place so as to audit all the pre-paid meters in areas under Mpofana’s license. If people are found to have tempered with the electricity, they will be fined, this fine will depend on their kind of settlement.

The Municipality has also made a decision to check on all local businesses to determine whether or not tempering occurs in the local businesses.

All major industries around town, will be exempt from paying the special rate, but will be charged the normal price. This has already taken place, however this point has been emphasized that the special rate rule should be dealt away with for large consumers.

The process will also be culminated by some cost-cutting issues which will be further discussed under

## F2. Municipal 3 to 5 Year Budget

### F2.Capital & Operational Budget

#### F2.1.1. Operating Budget

The following table summarises the Operating Budget.

| Description | Budget 2017/18 | Budget 2018/19 | Budget 2019/20 |
| --- | --- | --- | --- |
| Revenue by source |  |  |  |
| Property rates | 12 778 972 | 13 174 391 | 13 846 392 |
| Penalties | 2 639 028 | 2 807 925 | 2 987 633 |
| Service charges | 54 055 076 | 56 847 080 | 59 783 709 |
| Rental facilities | 4 409 876 | 4 692 108 | 4 992 403 |
| Interest on Investments | 1 281 600 | 1 363 622 | 1 450 894 |
| Interest on debtors | 1 602 000 | 1 704 528 | 1 813 617 |
| Fines | 320 000 | 340 905 | 362 723 |
| Licence and Permits | 2 242 800 | 2 386 338 | 2 539 063 |
| Operating grants | 28 752 000 | 31 841 000 | 34 085 488 |
| Capital grants | 12 164 000 | 12 557 000 | 13 360 000 |
| Other revenue | 138 840 | 147 725 | 157 180 |
| Total Revenue | 120 116 592 | 127 862 627 | 135 379 754 |
| Expenditure by type |  |  |  |
| Employee cost | 28 844 613 | 30 158 677 | 32 089 835 |
| Remuneration of councillors | 2 006 838 | 2 108 829 | 2 217 033 |
| Asset Impairment | 14 122 164 | 15 025 982 | 15 987 645 |
| Depreciation | 5 612 340 | 5 971 529 | 6 353 707 |
| Finance cost | 267 000 | 284 088 | 302 269 |
| Bulk electricity | 49 674 816 | 52 854 004 | 56 236 660 |
| Contracted service | 5 514 259 | 5 867 172 | 6 242 670 |
| Repairs and maintenance | 1 869 000 | 1 988 616 | 2 115 887 |
| Other expenditure | 9 118 180 | 8 731 376 | 9 290 184 |
| Total Expenses | 117 168 061 | 123 138 000 | 130 992 074 |
| Surplus/(Deficit) | 2 938 530 | 4 724 626 | 4 387 679 |

#### F2.1.2. Capital Budget

The following table summarises the 2017/18 Capital Budget.

| Name of the Grant | Ward | Budget 2017/18 | Budget 2018/19 | Budget 2019/20 |
| --- | --- | --- | --- | --- |
| Mangaung Access Road (MIG) Phase 2 | 5 | R2 432 800 |  |  |
| Highover Access Road | 2 | R2 432 800 |  |  |
| Sthembiso to Cabazini Road MIG Phase 2 | 3 | R2 432 800 |  |  |
| Mgqula Gravel Road (MIG) | 4 | R2 432 800 |  |  |
| Upper Town Road- Phase 3 | 1 | R2 432 800 |  |  |
| Mooi-River Testing Route | 1 | R3 000 000 |  |  |

The Mooi-River Testing Route is a 2016/17 project which is in process of being awarded, It is however anticipated that the Project will carried over to the 2017/18 Financial Year.

#### F2.1.3. Costs Of Providing Free- Basic Services

Due to financial constraints in the 2011/16 IDP, the municipality was unable to budget for free basic services. The Municipality is however pleased to announce that it has considered those that are indigent, this process needs to identify those that are indigent and the actual cost to the Municipality to subsidise those that are indigent. The Municipality looked into ward 1, 3 and 5 for the Indigent Register; there has however been a directive that the Municipality should also include Ward 2 and 4 in its indigent Register for the 2017/2018financial year. The distribution losses of the past have also contributed to the Municipality not being able to implement the Free Basic Service for Electricity. Once the process is concluded, the eligible members for the indigent aid will recieve free 500 k/w worth of electricity monthly.

### F.3Operational And Maintenance Costs

|  | Budget 2017/18 | Budget 2018/19 |
| --- | --- | --- |
| R&M Buildings | 284 088 | 302 269 |
| R&M Electricity reticulation | 227 270 | 241 815 |
| R&M Service Connections | 45 454 | 48 363 |
| R&M Machinery and Equipment | 113 635 | 120 907 |
| R&M Roads and Storm water | 1 136 352 | 1 209 078 |
| R&M Street lights | 68 181 | 72 544 |
| R&M Vehicle Maintenance | 113 635 | 120 907 |
| Bursaries | 110 000 | 130 000 |
| Total R&M | 1 988 616 | 2 115 887 |

### F4 Debt Collection

The implementation of the procedures in terms of the Credit control and Debt collection Policy will facilitate the management of cash flow, and place Council in a position to finance operation expenses. This will have to be combined with a strategy to cleanse debtor s data.

The table below depicts the current payment trends on what is raised and what is received by consumers as a whole. The collection rate for the Bruntville area only makes up 3% of the 48% collection rate. The Municipality is in the process of updating its system so that the Bruntville Community can be billed for rates and services.

| Month | % Recovery Rate |
| --- | --- |
| JUL 16 | 51% |
| AUG 16 | 39% |
| SEP 16 | 35% |
| OCT 16 | 40% |
| NOV 16 | 50% |
| DEC 16 | 30% |
| JAN 17 | 45% |
| Total | 48% |

### F4. Revenue Generation

The Municipality generates most of its revenue from the sale of electricity and is largely dependent on consumers purchasing electricity and making payment for this service. The Municipality also relies on rate payers to ensure that their rates are paid as this also is a contributing factor to whether the Municipality can improve the Town. The other contributing factor to revenue generation is the issuing of fines by the Traffic Department which was previously stopped due to change in service provider. Other factors are building plan fees, rates clearance fees, driver’s license and registrations, cemetery fees, refuse removal and electricity connection as well as hall hires. It has been suggested that the Municipality should consider the hiring of the sports fields as an added method of revenue generation as well as leasing out Municipal Properties for additional income.

At a Revenue Strategic Planning Session, these were the issues that were raised which range from:

Updated Customer Details- Which the Municipality is currently updating

There is no enquiries Clerk- A dedicated official has been assigned the duty of Enquiries Clerk

Incomplete billing- The Municipality is currently checking its billing method and verifying if there could be people who might be owing the Municipality but are not billed.

F2.4. EXPENDITURE MANAGEMENT

Whilst the Municipality wishes to collect all the money owed to it, it is equally important that the spending patterns are monitored closely so as to avoid unnecessary expenditure. It must be recalled that Mpofana Local Municipality was under intervention Section 139 (c), The intervention introduced a committee called the IFC, The Interim Finance Committee, which assists the CFO and all other relevant officials in guiding them on issues that are a priority to the Municipality and where money is to be spent. The presence of the IFC has seen an improved expenditure management, as items that need to be bought are condoned by the IFC. Treasury has also supported the Municipality in this regard by providing a warm body who helps out at Finance.

It is equally important to mention that the Finance Staff are currently being trained on MFMP (Municipal Finance Management Programme), the course farmiliarizes the staff dealing with financial issues with sound financial practises and norms. This in turn assists the Municipality by having peple who are well vested in the MFMP.

Council through its delegated oversight committee the MPAC closely monitors the Municipal’s spending patterns.

### F2.4. Asset Management

If assets are managed correctly, it ensures that costs are saved and longer life spans of the assets. With the position of the Asset Control Officer, the Municipality will ensure that the implementation of an integrated asset management system and management of the system is current and accurate. The Asset Control Officer will ensure that proper investigations, identification and implementation of a suitable integrated asset management system. It also includes the capture of all assets onto the system, the maintenance of this system and the production of a complete asset register in terms of the GRAP requirements. Currently the financial interns are assisting in checking the asset register and ensuring that it is properly maintain Revenue Protection Unit to ensure the municipality’s revenues is collected to its maximum ability. The following are some of the more significant programmes that have been identified.

### Budget

National Treasury published draft budget regulations in accordance with the relevant provisions of the MFMA. This informs the organogram, especially on the finance directorate in order to effectively deal with these budget regulations. A municipality should comply with the National Treasury Budget and Regulation format on its budget.

### Financial Statements

A municipal financial year has to fully comply with the standards of GRAP. In order to show effective compliance with these and other standards will also necessitate an amendment to the finance organogram. A municipal Finance department should appoint well experienced financial personnel (CFO) to allow full compliance to GRAP standards.

### Borrowing Costs

This should indicate the maximum average borrowings ratio inclusive of projects for the next three years. The list of projects the fund is earmarked for should also be indicated. It must also show the total amount of external loans for a certain period of years

# Section G.1 (Annual Operational Plan)

FINAL

2017/18

SERVICE DELIVERY & BUDGET IMPLEMENTATION PLAN

10 Claughton Terrace

Mooi-River

3300

“Ikusasa lisezandleni zethu, Masakhe”

CONTENTS

Foreword by the Mayor

Introduction

Legislation

Components

Vision, Mission and Values

Strategic Objectives

Votes and Operational Objectives

Monthly Revenue

Monthly Expenditure

Service Delivery and Perfomance Indicators and Targets

Budget and Treasury Office

Office of the Municipal Manager

Corporate Services

Social and Economic Development Service

Technical Services Department

Detailed Capital Works Plan

Conclusion

Foreword by the Executive Mayor

I am honored and humbled to submit to you, in terms of Municipal Systems Act of 2000, the 2017/18 Service Delivery and Budget Implementation Plan. The SDBIP will inform decision making on resource allocation and service delivery. We are proud to inform you that this SDBIP emanates from the IDP which is the key document, also which was compiled through extensive public consultation and participation process. This shows that Mpofana Municipality fully understands the importance of democracy and that no development of people can take place without their involvement.

We have made enormous strides in fulfilling our constitutional obligation by implementing five strategic programmes embedded in our vision: economically viable and developmental municipality, creating job opportunities, affordable place to inhabit, promote environmental sustainability and a strong competitor for economic and tourism investment municipality.

We will continue to put more effort to achieve our vision and forge intergovernmental relations. The existing partnerships formed with private, public and civil society has contributed to positive business environment .The benefit of these partnerships has already started to generate fruits in reviving economic growth within Mpofana Municipality.

We have prioritized economic growth and development to address unemployment and poverty. Industrial Development and Agro-processing is one of the strategic priorities to stimulate economic growth and job creation.

The Municipality has better positioned itself in meeting the needs and priorities of the community by re-aligning its organizational structure and embarked on an effort of filling in the critical posts. This will ensure that we strengthen management of resources and accelerate service delivery. Therefore this SDBIP is inclusive of the programmes, projects and financial investments from other government departments and other key stakeholders.

As the Executive Authority of Mpofana Municipality, I wish to say we are committed to explore all the avenues and mobilise financial and human resources to ensure the successful implementation of this SDBIP. Better is not good enough the best is yet to come for Mpofana citizens.

Approved by the Executive Mayor

Councillor X DUMA

INTRODUCTION

The development, implementation of the Service Delivery and Budget implementation Plan (SDBIP) is required by the Municipal Finance Management Act (MFMA). In terms of Circular 13 of National Treasury, “The SDBIP gives effect to the Integrated Development Plan  (IDP) and budget of the Municipality and will be possible if the IDP and the budget are fully aligned with each other, as required by the MFMA

As the budget gives effect to the strategic priorites of the municipality, it is important to supplement the budget and the IDP with a management and the implementation plan. The SDBIP serves as a commitment by the Mpofana Municiplaity, which includes the administration, council and community, whereby the intended objectives and projected achievements are expressed in order to ensure that desired outcomes over the long term are achieved and these are implemented by the administration in the 201/17 financial year.

The SDBIP provides the basis for measuring performance in service delivery against quarterly targets and implementing the budget based on monthly projections. Circular 13 further suggests that “the SDBIP provides the vital link between the Mayor and the Administration , and facilitate the process for holding management accountable for its performance . The SDBIP is a management, implementation and monitoring tool that will assist the Mayor, the Municipal Manager, Senior Managers and community”

The purpose of the SDBIP is to monitor the excecution of the budget, performance of senior management and achievement  of the strategice objectives set by the Council, It enables the Municipal Manager to monitor the performance of senior managers, The Mayor to monitor the performance of the Municipal Manager, and the community  to monitor the performance of the municipality. In the interest of good governance and better accountability, the SDBIP should therefore determine and be aligned with the performance agreements by the Municipal Manager and senior Managers.

LEGISLATION

According to the Municipal Finance Management Act (MFMA) the definition of the SDBIP is:

“Service Delivery and Budget Implementation Plan”means a detailed plan approved by the Mayor of a Municipality in terms of section 53 (1) (c) (ii) for implementing the municipality’s delivery of municipal services and its annual budget, and which must indicate-

Projections for each month of-

Revenue to be collected, by source, and

Operational and capital expenditure, by vote;

b) Service Delivery targets and performance indicators for each quarter

Section 53 of the MFMA stipulates that the Mayor should approve the SDBIP within 28 days after the approval of the budget. The Mayor must also ensure that the revenue and expenditure projections for each month and the service delivery targets and performance indicators as set out in the Service Delivery and Budget Implementation Plan are made public within 14days after the approval.

Section 1 of the MFMA defines a “vote”as:

One of the main segments into which  a budget of municipality is divided for the appropriation of money for the different departments or functional areas of the Municipality; and

Which specifies the total amount that is appropriated for the purposes of the department or functional area concerned

COMPONENTS

National Treasury directives are quite clear on the contents and methodology to derive at the SDBIP. As a first step, the IDP objectives need to be quantified and related into key performance indicators. The budget is aligned to the objectives, projects and milestones to enable the SDBIP to serve as monitoring tool for service delivery. What gets measured, gets done, therefore it should be noted, that in order to improve on certain processes and co-operation within the municipality, process indicators have been developed for the measurement purposes during the 2014/15 financial year.

The Mpofana Municipality has incorporated the following relevant components into their SDBIP, but has used the initiative to derive it as follows:

Monthly projections of Revenue by Source

Monthly projections of Revenue and Expenditure by Vote

Monthly projections of Capital Expenditure by Vote

Quarterly projections of service delivery targets and performance indicators for each vote

Capital Works Plan over three years

In the development of Mpofana Municipality’s SDBIP cognizance was taken of the IDP priorities, Objectives and Strategies as well as the Turn Around Strategy contained in the IDP ensuring progress towards the achievement thereof. The SDBIP of Mpofana Local Municipality is aligned to the Key Performance Areas (KPAs) as the prescribed by Regulations 805 of 2006 and the IDP guidelines by COGTA for purposes of alignment to the Perfomance Agreements of the Municipal Manager and the Managers directly accountable to the Municipal Manager.

The Institutional indicators will form part of the Performance Agreements and Plans of the  Municipal Manager and the Managers directly accountable to the Municipal Manager. Indicators are assigned quarterly targets and responsibilities to monitor performance.

The SDBIP serves as a management, implementation and monitoring and that will assist the Mayor, Councillors, Municipal Manager and Senior Managers in delivering services to the community. The SDBIP is described as a layered plan. The top layer deals with consolidated service delivery targets and time frames as indicated on this plan. Top Management is held accountable for the implementation of the consolidated projects and Key Performance Indicators.

5. VISION, MISSION AND VALUES

In line with the National Development Plan, the strategic vision of the Mpofana Local Municipality is in existence, although there has been a call to revise it, this process however should be subject to Public Participation.  The Vision of Mpofana Local Municipality is

LONG TERM VISION

“By Year 2030, Mpofana will be an economically vibrant and developmental municipality, able to generate employment for all its economically active residents, be affordable place to inhabit, and with its environmental endowment, be strong competitor for tourist trade and investment.”

The Strategic Mission speaks about what the purpose of the Mpofana Local Municiality . The Mission is:

MISSION

“Mpofana Municipality is a pro-active, democratic and accountable municipality committed to social and economic development, provision of efficient, affordable, sustainable and customer-oriented services to its community whilst striving to sustain financial viability. Mpofana Municipality is a pro-active, democratic and accountable municipality committed to social and economic development, provision of efficient, affordable, sustainable and customer-oriented services to its community whilst striving to sustain financial viability.”

STRATEGIC OBJECTIVES

| KEY PERFORMANCE AREA | STRATEGIC OBJECTIVE |  | RESPONSIBLE DEPARTMENT |
| --- | --- | --- | --- |
| Municipal Transformation and Organizational Development | To improve functionality of Municipal Performance Management System |  | Corporate Services |
|  | Reengineer Organisation to enhance strategic needs |  |  |
|  | To improve administrative systems and processes |  |  |
| Basic Service Delivery | To increase access to Basic Services |  | Technical Services |
| Local Economic and Social Development | To strengthen the economic environment. |  | Social and Economic Development Services |
| Municipal Financial Viability and Management | Increase funding and revenue generation |  | Corporate Services |
|  | Improve expenditure and maximise the economies of scale. |  |  |
|  | Optimise budgeting and accountability of finances |  |  |
| Good Governance and Public Participation | To Improve compliance and audit opinion |  | Office of the Municipal Manager and Social and Economic Development Services |
|  | To Improve Municipal Governance |  |  |
|  | To Improve public participation and awareness |  |  |
|  | Improve municipal internal and external communication |  |  |
| Cross Cutting Issues | To Strengthen Governance and IGR |  | Office of the MM, Social and Economic Development Services |
|  | Establish Disaster Management Unit. |  |  |
|  | Facilitation of Disaster Management Awareness campaigns |  |  |
|  | Improve response to disasters in collaboration with the District Municipality |  |  |
|  | Develop a Credible IDP |  |  |
|  | Improved SDF Planning |  |  |
|  | Support the implementation campaigns directed to Youth and vulnerable groups. |  |  |
|  | Co-ordinate the implementation of HIV & AIDS Strategy |  |  |

VOTES AND OPERATIONAL OBJECTIVES

| Operational Objectives | Office of the Municipal Manager | Risk |
| --- | --- | --- |
|  | Budget and Treasury Office | Revenue Collection |
|  | Corporate Services Department | Organizational Engineering |
|  | Technical Department Services | Increased access to Basic Services |

### G.2 ALIGNMENT of the SDBIP with Goals and associated Objectives and the Municipal Budget

The SDBIP IS fully aligned with the Goals and associated Objectives and the Municipal Budget. This is made possible by the fact that the SDBIP rests in the Office of the MM and is co-ordinated in that office. This is also made possible by the fact that the Budget and Treasury Office works closely with the PMS office. Objectives are therefore aligned with the budget.

### G.3 PERFORMANCE INDICATORS

The SDBIP does have performance indicators that explain how it will be measured. In the 2017/18 financial year, 68 performanceindicators have been set, they are smart, time bound and measurable. See attached SDBIP on Section G.

### SECTION H. ORGANISATIONAL AND INDIVIDUAL PERFORMANCE MANAGEMENT SYSTEM

The municipality is currently developing a comprehensive Performance Management System based on this five year plan in accordance with Chapter 6 of the Municipal Systems Act No. 32 of 2000, Municipal Finance Management Act No. 56 of 2003 and the Municipal Planning and Performance Management Regulations. In order to address the concerns raised in the MEC letter, the PMS indicators and objectives will be linked to the objectives and strategies.

### H1 ORGANISATION KEY PERFORMANCE INDICATORS LINKED TO DEPARTMENTAL INDICATORS

Progress will be measured through organisational key performance indicators linked to departmental indicators. In the SDBIP organisational key performance indicators are presented at an annual and quarterly level. Departmental indicators are broken down into monthly indicators, which are monitored and reported on a monthly basis at the meetings of the operational management committee.

### H2 DEPARTMENTAL INDICATORS LINKED TO OUTPUTS IN THE PERFORMANCE AGREEMENTS

Managers must enter into a performance agreement annually. Theseperformance agreements are directly linked to the approved SDBIP and departmental indicators, through thedevelopment of individual work plans. Indicators in the work plans also include indicators that are not necessarilyincluded in the SDBIP and/or departmental indicators, but are relevant to the operational functionality of anyparticular post. The indicators contained within the work plan are agreed upon and signed off by both thesupervisor and the incumbent.

### H.3 Alignment of OPMS (Departmental and Individual Indicators)

The OPMS is aligned to the Departmental and Individual Performance Management System. The OPMS form the basis of the quarterly performance assessments that are conducted. Assessments that take place during the first and third quarter are conducted on an informal basis between the supervisor and the incumbent, and are more informal, as opposed to the mid-year and annual assessments, which are formal in nature and documented accordingly. The work plan is the document that links to the operational plans and indicators.

### H4. BACK TO BASICS

The OPMS (Departmental and Individual Indicators) are aligned to the Back to Basics Pillars. The SDBIP further aligns to the Back to Basics Support Plan. The Mpofana has council has adopted the support plan in its full council dated the 31st of March 2017.

### SECTION I.1 ANNEXURES

| Sector Plan | Status | Adopted by Council | Comment |
| --- | --- | --- | --- |
| Disaster Management Framework | Complete | Draft Stage | District lead process |
| Environmental Management Framework (EMF) | Underway | Yes | The EMF is currently being prepared by the uMgungundlovu District Municipality and is due to |
| Infrastructure Plan | None | Draft Stage | Not in place at the moment |
| Skills Development Plan | Complete | Yes | In place |
| Credit Control and Debt Collection Plan | Complete | Yes | In place |
| Integrated Transport Plan | None | No | District to lead the process |
| Land Use Management Scheme | Underway – 95% complete | No | In place |
| 10. LED Strategy | Complete | Yes | In place |
| 11. Comprehensive Infrastructure Plan | Underway | No | Currently being prepared- subject to availability of funding |
| 12. Youth Development Plan | Underway | Yes | In place |
| 13. Gender Policy | Complete | Yes | In place |
| 14. HIV/AIDS Strategy | Complete | Yes | In place |
| 15. Housing Sector Plan | Complete | Yes | Still needs to be reviewed |
| 16. Indigent Policy | Complete | Yes | In place |
| 17. Workplace Skills Plan | Underway | Yes | In place |
| 19. Waste Management Plan | None | Yes | In place |
| 20. Environmental Health By-Law | None | No | Not in place |
| 21. Indigent Support Policy | Complete | Yes | In place |
| 22. Land Alienation Policy & Strategy | Complete | Yes | In place |
| 23. Library Services Policy | Complete | Yes | In place |
| 24. Property Encroachment By-Law | Complete | Yes | In place |
| 25. Street Trading By-Law | Complete | Yes | In place |
| 26. KZN PDA Delegations | Complete | Yes | In place |

### 1.3 SDF ( Attached separately) Disaster Management Plan

MPOFANA LOCAL MUNICIPALITY INTERGRATED WASTE MANAGEMENT PLAN

The plan is being submitted in term of Chapter 5 of the Municipal Systems Act which propels Municipalities to Include the approved integrated waste management plan in its integrated development plan contemplated in

BACKGROUND

Impofana Municipality is required to develop an Integrated Waste Management Plan (ele) in terms of its statutory obligation to provide for competent waste management to protect human and environmental health within the local municipal area. (The Mpofana Municipality is hereafter ‘the Municipality’ unless otherwise specified.)

This statutory obligation is framed by Section 24 and Section 156 (in conjunction with Schedule 5B) of the Constitution of South Africa (Act 108 of 1996), which respectively declares the right to human and environmental health; and waste management as a local government competence.

Furthermore, the Department of Environmental Affairs Integrated Waste Management Strategy (1999/2000; IWMS) covers the relevant national principles and strategy as well as local government participation in implementing the strategy; the White Paper on Integrated Pollution Prevention and Waste Management (2000) provides for integrated waste management/pollution prevention initiatives; while the Local Government Municipal Systems Act (Act 32 of 2000; MSA) contains both broad and specific provisions relating to municipal service delivery.

However, since the National Environmental Management: Waste Act, Act 59 of2008, (Waste Act) was promulgated on 10 March 2009 and came into effect on1 July 2009, it now constitutes South Africa’s overarching primary waste legislation. As such the Waste Act provides legal standing for government to fulfil its obligation of compiling and implementing IWMPs. Section 11 of the Waste Act concerns the development of municipal IWMP:

“(4) (a) each municipality must –

(ii) Submit its integrated waste management plan to the Member of Executive Council (MEC) for approval; and

(ii) Include the approved integrated waste management plan in its integrated development plan contemplated in Chapter 5 of the Municipal Systems Act.”

Impofana Local Municipality (ILM) is one of six local municipalities that constitute the Umgungundlovu District Municipality.

Impofana Local Municipality is situated in the Midlands part of the KwaZulu- Natal Province.

The Impofana LM consists of 5 wards with a total geographical area of 181 000 Ha, with the population of 38 103 000 people living in 9244 households with a population growth of 2%. The Municipality is experiencing a continuous influx of people into the municipal area due to residential and business development in the Municipality.

The status quo study will assess the municipal area with consideration to the various services categories as well as evaluate the service delivery in each of the towns in the Municipality. The service categories that are taken into consideration can be summarised as follows:

Refuse Removal: Residential, Commercial, Industrial, Garden Refuse, Builders’ Rubble and Medical Waste

Street and ablution cleaning

Landfill Sites, Transfer Stations and Bulk Containers

The main goal of the Municipality with regards to waste management is summarised as follows:

Optimise waste management within the Impofana Municipal Area for the protection of human health and wellbeing by maximising the effective use of available resources and promoting sustainable environment.

In addition the Impofana Municipal IWMP aims to:

Ensure that the Municipality implements all existing legislation requirements in terms of waste management. The Municipality acknowledges that the Constitution of the Republic of South Africa is the supreme law of the land and that as such waste management principles must pre-eminently comply with the Constitution and any amendments thereto.

Provide a basis for a system of integrated solid waste management by-laws that will be used to regulate waste generation and waste management services within the Municipality’s jurisdiction, as well as serve as a disincentive for poor waste management practices.

Service Area and refuse collection

The Municipality currently service a total number of 12 457 properties in Impofana. Approximately 9244 households receive a communal waste collection service. A regular waste removal service is provided to all households and businesses within the major towns (Mooi River, Rosetta, and Brunt Ville) of the Municipal area, except to the households in rural areas. The majority of the population in rural areas either bury or burn their waste. The provision of such a service is at the moment not envisaged by the Municipality.

INTRODUCTION

In a situation with small rural towns that lack financial resources it is always beneficial to look at systems which are simple and easy to manage, as well as being cost effective. These systems should also address the ongoing problem of unemployment. This is what we have envisaged for this Municipality. The follow system has been proposed:-

I. Establish recycling centre at each of the identified site within Impofana Municipality

II. Identify competent contractor in to collect all the solid waste and deliver it to the recycling centre.

III. Separate the waste into recyclable, organic and non-recyclable waste.

IV. The recyclable waste is separated further and bailed or bagged for resale to recycling business.

V. Organic waste is removed by the gardening group who will then compost the waste for the use in their gardens or for resale if there is sufficient quantity. (Used in Larger towns only) In the case of garden waste a mobile shredder will be used on a weekly basis to shred this waste. It can then be used for compost.

VI. Conduct Community awareness on waste management and in schools

PROJECT GOAL

The establishment of an integrated waste management system that benefits the local community and the environment through job creation, recycling, producing crafts from waste, composting and food production from organic waste all of which will lead to a cleaner and healthier environment for all.

PROJECT OBJECTIVES

_To address the huge problem of irresponsible waste management;

_To create a clean and healthy environment free of litters;

_To look at waste as a resource which can be used by the community;

_To create jobs;

_To utilise waste to its fullest in as many ways as possible; and

_To minimise the quantity of waste that must be land-filled thus reducing costs.

_To raise awareness on waste management

BENEFICIARIES

The local community will be the ultimate beneficiaries both due to jobs created and the improvement of the local environment. It is the express intention of the implementing agency and all associates to ensure that the program is sustainable and can be managed by the municipality in partnership with the community after implementation.

Community members will be identified and trained in all aspects of the waste management system. In addition there will be opportunities for the establishment of SMME initiatives such as market gardening using organic waste, crafts from waste (linkages with existing and potential markets exist in the tourist centre, which enables local crafters and manufacturers to benefit from marketing, information and management synergies). Signage will also ensure local attention is created.

MONITORING AND EVALUATION

All stakeholders will be constantly updated and the monthly reporting format will ensure that the project is closely monitored. Appropriate measures will be taken by the Project Managers for the achievement of milestones and other deliverables.

The evaluation processes that will be followed are:

_ Close day to day management of the project by contractor;

_ Monthly reports to all stakeholders;

_An internal review process through steering committee will be strictly adhered to at all times;

SUSTAINABILITY

The following will increase the financial sustainability of the programme:

_Advertising on waste collection trailers and adopt a pole campaign.

_Sale of recyclable waste.

_Producing crafts from waste for resale.

_ Market garden using organic waste can generate income for entrepreneurs.

_ Collecting rates from the communities.

FINANCIAL DETAILS

The following budget indicates the cost of establishing a complete integrated waste management system including infrastructure, tools, training and mentoring/management and wages for Impofana Municipality.

| ITEM DESCRIPTION | AMOUNT |
| --- | --- |
| Development of recycling centre | R 550 000.00 |
| Equipment (weigh bridge) and furniture | R 400 000.00 |
| Tools and protective clothing | R 30 000.00 |
| Training of recyclers | R20 000.00 |
| Fence for the site | R 50 000.00 |
| Market garden establishment and crafter tools | R 70 000.00 |
| Signage | R 6 000.00 |
| Awareness campaigns promotional material | R 100 000.00 |
| TOTAL | R1 226 000.00 |

INFRASTRUCTURE DELIVERABLES AND EQUIPMENT

Level site and fence with razor wire, with double vehicle gate

Store room, change room, toilets and shower

I-beam and IBR roofing recycling shed with concrete flooring.

Weigh bridge

Bailing Machine

Separation tables and bag trolleys

Skip bin bay

Hand tools

Protective clothing

Hand drawn trailers

Garden implements, tools and seeds

Craft furniture and tools

OPPORTUNITIES TO BE CREATED

The integrated waste recycling centre will create opportunities not only for recyclers at Ward level but also for the staff that will be working at the recycling centre. The staff will compliment as follows:

1 x Supervisor at recycling centre

6 x Waste Separators

2 x Recycle bailing staff

1 x Trolley operator

4 x Crafters from waste

4 x Market Gardeners / composters

### I.3 DISASTER Management Plan

Mpofana Local Municipality

Disaster Management Plan (JUNE2017) [Draft]

10 Claughton Terrace, Mooi River, 3300

Tel (+27) 33 263 1221; Fax (+27) 33 263 1127

Web: www.mpofana.gov.za

Disaster Management is everybody’s Business

DOCUMENT CONTROL PLAN

DOCUMENT HISTORY

| Name of the Project |  |
| --- | --- |
| Project Team |  |

QUALITY ASSURANCE

| VERSION | STATUS | DATE |
| --- | --- | --- |
| Version 0.1 | Draft | March 2017 |

APPROVAL

| APPROVED BY THE MPOFANA LOCAL MUNICIPALITY |  |  |  |
| --- | --- | --- | --- |
| Name | Designation | Signature | Date |
|  |  |  | /June / 2017 |

Table of content

Foreword

Acknowledgements

Executive Summary

Acronyms

- Introduction

  - Purpose of the Disaster Management Plan

The purpose of this plan is to ensure the implementation of an integrated and coordinated disaster management that focuses on prevention, reduction of disaster risk, emergency preparedness, rapid and effective response to incidents/disasters and post-disaster recovery within the area of the Mpofana Local Municipality.

  - Requirements in terms of Disaster Management Legislation and Policy

Section 53 (1) of the Disaster Management, Act No. 57 of 2002 stipulates that each municipality must, withinthe applicable municipal disaster managementFramework:

- Prepare a disaster management plan for its area according to the circumstancesprevailing in the area;

- Co-ordinate and align the implementationof its plan with thoseof other organsof state and institutional role-players;

- Regularly review and update its plan; and

- Through appropriate mechanisms, processes and procedures established in terms of Chapter 4 of the Local Government: Municipal Systems Act, 2000(Act No. 32 of 2000), consult the local community on the preparation oramendment of its plan.

Section 53 (2) of the Disaster Management, Act No. 57 of 2002 states that A disaster management plan for a municipal areamust:

- Forman integral part of the municipality’s integrated development plan;

- Anticipate the types of disaster that are likely to occur in the municipal areaand their possible effects;

- Place emphasis on measures that reduce the vulnerability of disaster-proneareas, communities and households;

- Seek to develop a systemof incentives that will promote disaster managementin the municipality;

- Identify the areas, communities or households at risk;

- Take into account indigenous knowledge relating to disaster management;

- Promote disaster management research;

- Identify and address weaknesses in capacity to deal with possible disasters;

- Provide for appropriate prevention and mitigation strategies:

- Facilitate maximum emergency preparedness; and

- Contain contingency plans and emergency procedures in the event of adisaster, providing for-

- The allocation of responsibilities to the various role-players and co-ordination in the carrying out of these responsibilities;

- Prompt disaster response and relief;

- The procurement of essential goods and services;

- The establishment of strategic communication links;

- The dissemination of information; and

- Other matters that may be prescribed

Section 53 (3) of the Disaster Management, Act No. 57 of 2002 states that a district municipality and the local municipalities within the area of the districtmunicipality must prepare their disaster management plans after consulting each other.

Section 53 (4) of the Disaster Management, Act No. 57 of 2002 states that a municipality must submit a copy of its disaster management plan,andof anyamendment to the plan, to the National Disaster Management Centre (NDMC), the Provincial Disaster Management Centre (PDMC), and, if it is a district municipality or a local municipality, to everymunicipal disaster management centre within the area of the district municipality concerned.

    - Guiding Policy framework and Approach of Developing this Plan

The National, Provincial and District Disaster Management Policy Framework formed a solid basis of developing this plan. The Key Performance Areas (KPAs) and Enablers of the disaster management policy frameworks of all spheres of government are a fundamental pillars of South African approach to disaster management. Hence, the structure and content of this plan are greatly influenced or is in line with the disaster management policy framework KPAs and Enablers (Figure 1).

Figure 1: Disaster Management Policy Framework’s Key Performance Areas and Enablers.

  - Paradigm Shift in Global and South African Approach to Disaster Management

Globally, over the years the impact of disasters on humans including all those killed,injured, or made homeless has beenestimated to have affected millions of people (Disaster Management White Paper, 1999). The economic and infrastructuredamages are huge in industrialised countriesas compared to developing countries, moreoverdeveloping countries tend to experience more fatalities and injuries then developing countries (Disaster Management White Paper, 1999).These enormous losses underscore the urgent need for improved disasterreduction, especially when one considers the negative impact disasters have onthe lives of those affected.

Disaster Management White paper (1999) acknowledges that disaster management has become increasinglycomplex, compared to previous limited responses to natural and human-madeevents. The field of disasters, emergencies and risks is a rapidly changing one.Today, the field of disaster management raises many questions of morality andprinciple. It entails operations of greatly varying scale and diversity.Disaster management has become a focus area for scientific endeavours toachieve a better understanding of the hazards that shape the natural and builtenvironments and to set standards to bring about a safer world.

As described by the Disaster Management White paper (1999) disaster management encompasses, for example, interpreting the early warning signals of naturalphenomena, such as too little or too much rainfall. Similarly, it involvescontingency planning and response to emergency events triggered by bothnatural and non-natural (including technological) forces.Disaster management seeks to reduce the vulnerability of communities most atrisk through improved access to services, development opportunities,information, education and empowerment.It embraces the body of knowledge, policy and practice associated withhumanitarian responses to both natural and technological disasters.

    - New  International Approach: Disaster Risk reduction

Over the past 30 years,there has been a continuous evolution in thepractice of crisis or disaster management (UNISDR, 2004). Thesebodies of practice have been known, variously, ascivil defence, emergency assistance, disasterresponse and relief, humanitarian assistance,emergency management, civil protection, disastermitigation and prevention, and total disaster riskmanagement.

The subject of disaster risk reduction in themodern era draws its relevance largely from earliercontributions and previous practices in the field ofcivil defence and later disaster management (UNISDR, 2004). In thisrespect, the traditional focus has been on thepreparation and improved operational capacities formore timely and effective response to animpending event, or the provision of urgentservices to restore basic requirements of the publicif a disastrous event has already occurred.

In manyplaces political commitment and the allocation ofresources to address hazardous conditions havebeen concentrated overwhelmingly on short-termemergency contingencies.There is no doubt that the role of relief assistanceduring the acute phase of a crisis will remainimportant and needs to be enhanced at all levels.However, the question must be asked: canmodern societies afford to value their social andmaterial assets only after they have been lost in adisaster?

By contrast, in more recent years and perhapsmotivated at least partially by the frequency andseverity of major disasters during the past decade,those people associated most closely with affectedpopulations such as the local political authorities, a broadrange of professional and commercial interests,public organizations, educational institutions andcommunity leaders – are progressively recognizingthe essential public value of sustained efforts toreduce the social, economic and environmentalcosts of natural hazards.

This translates into the need for much greaterattention on implementation of protectivestrategies which can contribute to saving lives andprotecting property and resources before they arelost. It is for this reason that a more holisticapproach that emphasizes vulnerability and riskfactors has coalesced around the concept of riskreduction, or disaster risk management.

    - The South African Context:

Since 1994 the South African government’s approach to dealing with disasters haschanged significantly. The change in old political regime legislation governing disasters wasdriven by several factors. One of the main reasons was the need to bring the law intothe modern era so that it would be in line with international best practice in the fieldof disaster risk management (NDMC Handbook, 2008). In addition, the government intended to systematically mainstream disaster risk reduction into developmental initiatives at national, provincial and municipal levels.

One of the main reasons for South Africa’s Disaster Management Act No. 57 of 2002 being recognised internationallyas a model for disaster risk management best practice is that it gives effect to theconcept of mainstreaming disaster risk reduction into development throughlegislation (NDMC Handbook, 2008). The DM Act places statutory responsibilities for disaster risk reduction onevery organ of state in each of the three spheres of government and gives a mandatefor the establishment of disaster risk management centres in all the spheres.

  - Definitions of Key Terms and Concepts

This section defines the core key terms, concepts and variables that are technically used in this plan. The definitions of these concepts and variables are directly extracted from the South African National Disaster Management Policy Framework of 2005.

### Disaster

Disaster is a“natural or human-caused event, occurring with or without warning, causing widespread human, material, economic or environmental losses which exceed the ability of the affected community or society to cope with its effects using only their own resources. A disaster is a function of the risk process. It results from the combination of hazards, conditions of vulnerability and insufficient capacity or measures to reduce the potential negative consequences of the disaster risk”(NDMPF, 2005).

### Disaster Risk Management

Disaster risk management “is the systematic process of using administrative decisions, organisation, operational skills and capacities to implement policies, strategies and coping capacities of the society and communities to lessen the impacts of natural hazards and related environmental and technological disasters. This comprises all forms of activities, including structural and non-structural measures to prevent or to limit (mitigation and preparedness) adverse effects of hazards”(NDMPF, 2005).

### Disaster Risk Reduction

Disaster Risk Reduction is the “conceptual framework of elements considered with the possibilities to minimise vulnerabilities and disaster risks throughout a society, to avoid (prevention) or to limit (mitigation and preparedness) the adverse impacts of hazards, within the broad context of sustainable development”(NDMPF, 2005).

### Mitigation

Mitigation refers to “structural and non-structural measures undertaken to limit the adverse impact of natural hazards, environmental degradation and technological hazards on vulnerable areas, communities and households” (NDMPF, 2005).

### Response

Response refers to “measures taken during or immediately after a disaster in order to provide assistance and meet the life preservation and basic subsistence needs of those people and communities affected by the disaster. These measures can be of immediate, short-term or protracted duration” (NDMPF, 2005).

### Recovery

Refers to “decisions and actions taken immediately after a disaster with a view to restoring or improving the pre-disaster living conditions of the stricken community, while encouraging and facilitating necessary adjustments to reduce disaster risk” Recovery (rehabilitation and reconstruction) affords an opportunity to develop and apply disaster risk reduction measures” (NDMPF, 2005).

### Relief

Relief refers to “the provision of assistance or intervention during or immediately after a disaster to meet the life preservation and basic subsistence needs of those people affected. It can include the provision of shelter, food, medicine, clothing, water, etc.”(NDMPF, 2005)

### Disaster Risk

Disaster risk is a “probability of harmful consequences or expected losses (deaths, injuries, property, livelihoods, disrupted economic activity or environmental damage) resulting from interactions between natural or human-induced hazards and vulnerable conditions. Conventionally risk is expressed as follows: Risk = Hazards x Vulnerability. Some disciplines also include the concept of exposure to refer particularly to the physical aspects of vulnerability” (NDMPF, 2005).

### Disaster Risk Assessment

Disaster Risk Assessment (DRA) “is a process to determine the nature and extent of risk by analysing potential hazards and evaluating existing conditions of vulnerability that could pose a potential threat or harm to people, property, livelihoods and the environment on which they depend as well as the evaluation of the effectiveness of prevailing and alternative coping capacities in respect to likely risk scenarios” (NDMPF, 2005).

### Human-Made Hazards

Human-Made Hazards are “potentially damaging physical event or occurrences that are caused directly or indirectly by identifiable human actions, deliberate or otherwise” (NDMPF, 2005).

### Natural Hazards

Natural Hazards are “natural processes or phenomena, such as extreme climatological, hydrological or geological processes, that may constitute a damaging event. Hazardous events can vary in magnitude or intensity, frequency, duration, area of extent, speed of onset, spatial dispersion and temporal spacing” (NDMPF, 2005).

### Vulnerability

Vulnerability is the “degree to which an individual, a household, a school, a community, an area or a development may be adversely affected by the impact of a hazard. Conditions of vulnerability and susceptibility to the impact of hazards are determined by physical, social, economic and environmental factors or processes” (NDMPF, 2005).

### Capacity

Capacity is a “combination of all the strengths and resources available within a community, society or organization that can reduce the level of risk, or the effects of a disaster. Capacity may include physical, institutional, social or economic means as well as skilled personnel or collective attributes such as leadership and management” (NDMPF, 2005).

- Description of the Mpofana Local Municipality

  - Geography, History and Economy

Mpofana Local Municipality is one of (7) Seven local municipalities that constitute the uMgungundlovu District Municipality.The municipality is a municipality located approximately 40km west of Pietermaritzburg. It is bounded by three municipalities: uMngeni in the south, uMshwathi in the east, and Impendle in the west.

The municipality benefits from its strategic position as it has easy access to rail, KZN provincial roads and the N3 National Road. Almost 50% of the land in Mpofana has the potential for rural farming, with products set for the international market.

Mooi River is a small town that germinated from a small farm and then, later, became the principal node of the Mpofana Municipality when a railway line linking Durban with Johannesburg, as well as the Drakensberg Mountains, was established in order to cater for the needs of the farmers in the area. This suggests that Mpofana has great potential for development through tourism.

Figure 2: Map of the KwaZulu-Natal Province highlighting the location of the Mpofana Local Municipality

  - Demographics

    - Population Dynamics

TheMpofana Local Municipalitypopulation sits at 37 391, within the population there is 34% of people who are under the age of 15 years. Within the population 62.3% of the people are between the ages of 15 to 64 and 2.9% of the population is over the age of 65 years. The growth population of Mpofana sits at 1.56% per annum. Mpofana education statistics are as follows: Persons aged 20 years and above who have no schooling is at 8.0%, those who only have matricis at 31.8% and those with higher education is at 9.7%. Household Dynamics: the municipality has 10 927 households the average household size is 3.4 persons per household. Female headed households are at 48.1%, formal dwellings are at 83.7% and housing owned is at 68.4%. Household services; Flushable toilets connected to sewerage is at 59.7%, weekly refuse removal is at 59.5%, piped water inside dwelling is at 53.6% and electricity for lighting is at 85.5%.

| Mpofana Municipality | 2016 | 2011 |
| --- | --- | --- |
| Population | 37 391 | 34 913 |
| Age Structure |  |  |
| Population under 15 | 34.8% | 29.2% |
| Population 15 to 64 | 62.3% | 66.8% |
| Population over 65 | 2.9% | 4.0% |
| Dependency Ratio |  |  |
| Per 100 (15-64) | 60.6 | 49.6 |
| Sex Ratio |  |  |
| Males per 100 females | 89.3 | 95.8 |
| Population Growth |  |  |
| Per annum | 1.56% | n/a |
| Labour Market |  |  |
| Unemployment rate (official) | n/a | n/a |
| Youth unemployment rate (official) 15-34 | n/a | n/a |
| Education (aged 20 +) |  |  |
| No schooling | 8.0% | 12.1% |
| Matric | 31.8% | 26.5% |
| Higher education | 9.7% | 5.8% |
| Household Dynamics |  |  |
| Households | 10 927 | 9 843 |
| Average household size | 3.4 | 3.3 |
| Female headed households | 48.1% | 43.0% |
| Formal dwellings | 83.7% | 80.0% |
| Housing owned | 68.4% | 43.7% |
| Household Services |  |  |
| Flush toilet connected to sewerage | 59.7% | 56.4% |
| Weekly refuse removal | 59.5% | 51.0% |
| Piped water inside dwelling | 53.6% | 41.9% |
| Electricity for lighting | 85.5% | 76.2% |

- Integrated Institutional Capacity for Disaster Risk Management in the Mpofana Local Municipality

The status of the integrated capacity for disaster risk management of the Mpofana Local Municipality will be discussed based on the Key Performance Indicators (KPIs) of the Key Performance Area (KPA) number 1 of the National Disaster Management Policy Framework (NDMPF) of 2005. Number 0, 1 and 2 have been used to rate the level of compliance with the requirements of the NDMPF of 2005 whereas 0 is no compliance, 1 is moderate compliance and 2 is full compliance.

Table 1: Integrated Institutional Capacity for Disaster Management in the Mpofana Local Municipality.

| Imperatives | Key Performance Indicators | Status |
| --- | --- | --- |
| - Establish arrangementsfor the development andadoption of an integrateddisaster risk managementpolicy. | - The municipal Inter-departmental Committee on Disaster Management has been established and is operating effectively. | 0 |
|  | - Mechanisms for developing and adopting disaster risk management policy have beenestablished and put into operation. | 1 |
| - Establish arrangements for integrated direction and implementation of disasterrisk management policy. | - The job description and key performance indicators for the position of the municipal disaster management officer have been developed. | 1 |
|  | - The municipal disaster management officer has been appointed. | 1 |
|  | - The municipal disaster management, fire and rescue unit has been established and is fully operational. | 1 |
|  | - Disaster risk management focal/nodal points have been identified by each municipal departments/entity and responsibilities for disaster risk management have been assigned. | 1 |
|  | - Roles and responsibilities of municipal departments and entities involved in disaster risk management have been identified, assigned and included in the job descriptions of key personnel and are being applied effectively. | 1 |
| - Establish arrangements for stakeholder participation and the engagement of technical advice in disaster risk management planningand operations. | - The Municipal Disaster Management Advisory Forum or similar representative consultative forums have been established and are operating effectively. | 2 |
|  | - Entities playing a supportive role in facilitating and co-ordinating disaster risk management planning and implementation have been identified and assigned secondary responsibilities. | 1 |
|  | - Disaster management officials have full participation in integrated development planningprocesses and structures. | 1 |
|  | - Ward structures have been identified and tasked with responsibility for disaster risk management. | 2 |
|  | - A current register of disaster risk management stakeholders and volunteers has beenestablished and is maintained. | 1 |
| - Establish arrangements for co-operationfordisaster risk management. | - Guidelines have been developed and disseminated for entering into partnerships and concluding mutual assistance agreements and memoranda of understanding. | 0 |
|  |  | 13/26*100 = 50% |

In terms of the above assessment criteria (Table 1), the Mpofana Local Municipality is 50% compliant with the requirements of the Key Performance Indicators (KPIs) of the Key Performance Area (KPA) number 1 of the National Disaster Management Policy Framework of 2005 which deals with the issues of integrated institutional capacity for disaster risk management. The lack of compliance has negative implications in the ability of the municipality to comprehensively implement integrated disaster risk management.

4.2. Mpofana Local Municipality Disaster Management Organogram

Mpofana Local Municipality Disaster Management currently has the following staffing: 1x Municipal Manager, 1xManager (Support, IDP &PMS), 1x Disaster Management Officer.

5. Standard Operating Procedure

Section 54 of the Disaster Management Act No. 57 of 2002 provides clear direction in terms of what is expected from the municipality in the event threatening, occurring or actual disaster. In the effort of proper coordination of response the municipality will organize the following activities.

- The release of any available resources of the municipality, including stores,     equipment, vehicles and facilities.

- The release of personnel of the municipality for the rendering of emergency services.

-The implementation of all or any of the provision of a municipal disaster management plan applicable in a particular circumstance.

-The evacuation to temporary shelters of all or part of the population from the disaster-stricken or threatened area if such action is necessary for the preservation of life.

-The regulation of traffic to, from or within the disaster-stricken or threatened area.

-The regulation of the movement of persons and goods to, from or within the disaster-stricken or threatened area.

-The control and occupancy of premises in the disaster-stricken or threatened area.

-The provision, control or use of temporary emergency accommodation.

-The dissemination of information required for dealing with the disaster.

- Emergency procurement procedures.

- The facilitation of response and post-disaster recovery and rehabilitation; or

- Other steps that may be necessary to prevent an escalation of the disaster, or to alleviate, contain and minimize the effects of the disaster.

6. Communication Plan

Disasters are generally followed by chaos. Effectively, both confusion and rumours start to emerge from everywhere, which can ultimately lead to uncontrollable panic. Casualties of disasters need to be provided with consistent, plain, precise, and timely information in order to find assistance and resources, avert dangers, and reduce as much as possible the risk of sustaining additional impact. A precise and successful communication plan has the ability to save the lives and the property of many individuals. Effective communication guarantees prompt response thus ensuring both credibility and public trust.

Organizational Means of Communication

In order to respond rapidly during a crisis, an emergency communication strategy will be put in place. This District Disaster Management Centre will be designated as a centre for crisis operations; the centre is equipped with telephone line as well as other necessary equipment tools such as television, computers, backup power source, a fax machine and camera.

7. Stakeholders Roles and Responsibilities

The stakeholders applicable to this disaster risk, with their primary roles and responsibilities include, but are not limited to the followingStakeholder Primary Roles and ResponsibilitiesThe Municipal Council The Municipal Council declares a state of disaster and receives and considers reports with regard to disaster risk management.The Municipality Municipal Manager	The Municipal Manager is overall responsible for governance in the Municipality, including effective disaster risk management.The Municipality Disaster Management Function Coordinate disaster management function in line with the disaster management legislation and policies.

Fire and Emergency Rescue Services Assist with disaster risk reduction, implementation and co-operation.The Disaster Management Volunteers The disaster management volunteers will assist with coordination of disaster management activities at a local level. The communities Assist with disaster risk reduction and cooperation.The Ward Councillors	The Ward Councillors assist with community liaison and coordination.

The Community Leaders assist with community liaison. Non-Governmental Organisations (NGOs) and Community Based Organisations (CBOs) The\ NGOs and CBOs assists with disaster risk reduction and effective response to incidents.

8. Dis Risk Assessment Design and Methodology

8.1 Disaster Risk Assessment Design

The disaster risk assessment equation was used to calculate disaster risk of a particular hazard in each ward of the Mpofana Local municipality. The following disaster risk assessment equation proposed by the UNISDR (2002) was then used:

Disaster Risk =Hazard X VulnerabilityCapacity

8.2 Data Source

The disaster risk assessment data was collected from community ward structures known as Operation Sukuma Sakhe, mainly because these structures are constituted by diverse stakeholders and community leaders.

8.3 Data Collection Technique

Disaster risk assessment entails the systematic collection of data pertaining to certain variables of disaster risk i.e. hazards, vulnerability and capacity. Hence, a community participatory approach was used to administer a structured disaster risk assessment template (attached as annexure A).

9 Disaster Risk Assessment Presentations and Analysis

9.1. Hazard Identification

There are number of hazards that were identified by communities, however in the interest of comprehensive analysis, the data analysis will only be limited to 10 priority hazards identified in the assessment templates. Data will be presented in a form of graphs, tables and maps. The table below (table 2) indicates the type of hazards identified as well as the frequencies or the rate at which there were identified.

Shaluf (2007) developed a schematic representation (figure 5) that shows a variety of almost all possible disasters that can be encountered. The schematic representation includes natural, human induced and hybrid disasters, as well as a combination of natural and human-induced disasters. The Shaluf’s schematic representation of hazards was used to identify hazards during the community disaster risk assessment sessions.

Figure 2: Schematic representation of hazards identified by Shaluf (2007). Source: Shaluf, I., 2007, ‘An overview of disasters’, Disaster Prevention and Management 16(5), 687−703.

Table 2: Types of hazards and threats identified during the ward disaster risk assessment sessions.

| No. | Prevalent Hazards and Threats | Mpofana Municipal Ward Numbers |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 01 | 02 | 03 | 04 | 05 |
| 01 | Road Accidents | x | x | x | x | X |
| 02 | Rail Accidents | x | x | x | x | X |
| 03 | Drought | x | x | x | x | X |
| 04 | Disease: Animal (Amatele) | x | x | x | x | X |
| 05 | Disease: Human (HIV/AIDS) | x | x | x | x | X |
| 06 | Disease: Human (Malaria) | x | x | x | x | X |
| 07 | Disease: Human (Cholera) | x | x | x | x | X |
| 08 | Veld/Forest Fires | x | x | x | x | X |
| 09 | House Fires | x | x | x | x | X |
| 10 | Severe Storms (Heavy Rainfall) | x | x | x | x | X |
| 11 | Severe Storms (Floods) | x | x | x | x | X |
| 12 | Severe Storms (Wind) | x | x | x | x | X |
| 13 | Severe Storms (Lightning) | x | x | x | x | X |
| 14 | Severe Storms (Hail) | x | x | x | x | X |
| 15 | Extremely High Temperatures | x | x | x | x | X |
| 16 | Soil Erosion | x | x | x | x | X |
| 17 | Lack of Sanitation | x | x | x | x | X |
| 18 | Lack of Water | x | x | x | x | X |
| 19 | Lack of Proper Road Infrastructure | x | x | x | x | X |
| 20 | Civil Unrest - Crime | x | x | x | x | X |
| 21 | Water Pollution | x | x | x | x | X |
| 22 | Stock theft (ukwebiwakwemfuyo) | x | x | x | x | X |

  - Hazards Analysis

Table 3: Hazards analysis in terms of probability, frequency, predictability, severity and magnitude

| No. | Prevalent Hazards and Threats | Mpofana Municipal Ward Numbers |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | KZ 223 Hazard Score |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 01 | 02 | 03 | 04 | 05 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Very Low = 1 |  |  |  | Low = 2 |  |  |  | Medium = 3 |  |  |  | High = 4 |  |  |  | Very High = 5 |  |  |  |  |
| 01 | Road Accidents |  |  |  |  |  |
| 02 | Rail Accidents |  |  |  |  |  |
| 03 | Drought |  |  |  |  |  |
| 04 | Disease: Animal (Amatele) |  |  |  |  |  |
| 05 | Disease: Human (HIV/AIDS) |  |  |  |  |  |
| 06 | Disease: Human (Malaria) |  |  |  |  |  |
| 07 | Disease: Human (Cholera) |  |  |  |  |  |
| 08 | Veld/Forest Fires |  |  |  |  |  |
| 09 | House Fires |  |  |  |  |  |
| 10 | Severe Storms (Heavy Rainfall) |  |  |  |  |  |
| 11 | Severe Storms (Floods) |  |  |  |  |  |
| 12 | Severe Storms (Wind) |  |  |  |  |  |
| 13 | Severe Storms (Lightning) |  |  |  |  |  |
| 14 | Severe Storms (Hail) |  |  |  |  |  |
| 15 | Extremely High Temperatures |  |  |  |  |  |
| 16 | Soil Erosion |  |  |  |  |  |
| 17 | Lack of Sanitation |  |  |  |  |  |
| 18 | Lack of Water |  |  |  |  |  |
| 19 | Lack of Proper Road Infrastructure |  |  |  |  |  |
| 20 | Civil Unrest - Crime |  |  |  |  |  |
| 21 | Water Pollution |  |  |  |  |  |
| 22 | Stock theft (ukwebiwakwemfuyo) |  |  |  |  |  |
| Ward Hazard Score |  |  |  |  |  |  |

  - Vulnerability Analysis

Table 4: Vulnerability analysis in terms of the degree to which individuals, households, community or development may be adversely affected by the impact of a hazard

| No. | Prevalent Hazards and Threats | Mpofana Municipal Ward Numbers |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | KZ 223Vulner. Score |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 01 | 02 | 03 | 04 | 05 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Very Low = 1 |  |  |  | Low = 2 |  |  |  | Medium = 3 |  |  |  | High = 4 |  |  |  | Very High = 5 |  |  |  |  |
| 01 | Road Accidents |  |  |  |  |  |
| 02 | Rail Accidents |  |  |  |  |  |
| 03 | Drought |  |  |  |  |  |
| 04 | Disease: Animal (Amatele) |  |  |  |  |  |
| 05 | Disease: Human (HIV/AIDS) |  |  |  |  |  |
| 06 | Disease: Human (Malaria) |  |  |  |  |  |
| 07 | Disease: Human (Cholera) |  |  |  |  |  |
| 08 | Veld/Forest Fires |  |  |  |  |  |
| 09 | House Fires |  |  |  |  |  |
| 10 | Severe Storms (Heavy Rainfall) |  |  |  |  |  |
| 11 | Severe Storms (Floods) |  |  |  |  |  |
| 12 | Severe Storms (Wind) |  |  |  |  |  |
| 13 | Severe Storms (Lightning) |  |  |  |  |  |
| 14 | Severe Storms (Hail) |  |  |  |  |  |
| 15 | Extremely High Temperatures |  |  |  |  |  |
| 16 | Soil Erosion |  |  |  |  |  |
| 17 | Lack of Sanitation |  |  |  |  |  |
| 18 | Lack of Water |  |  |  |  |  |
| 19 | Lack of Proper Road Infrastructure |  |  |  |  |  |
| 20 | Civil Unrest - Crime |  |  |  |  |  |
| 21 | Water Pollution |  |  |  |  |  |
| 22 | Stock theft (ukwebiwakwemfuyo) |  |  |  |  |  |
| Ward Hazard Score |  |  |  |  |  |  |

  - Capacity Analysis

Table 5: Capacity analysis in terms of household income levels and municipal capacity to implement integrated disaster risk management

| No. | Prevalent Hazards and Threats | Mpofana Municipal Ward Numbers |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | KZ 223Capacity Score |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 01 | 02 | 03 | 04 | 05 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Very Low = 1 |  |  |  | Low = 2 |  |  |  | Medium = 3 |  |  |  | High = 4 |  |  |  | Very High = 5 |  |  |  |  |
| 01 | Road Accidents |  |  |  |  |  |
| 02 | Rail Accidents |  |  |  |  |  |
| 03 | Drought |  |  |  |  |  |
| 04 | Disease: Animal (Amatele) |  |  |  |  |  |
| 05 | Disease: Human (HIV/AIDS) |  |  |  |  |  |
| 06 | Disease: Human (Malaria) |  |  |  |  |  |
| 07 | Disease: Human (Cholera) |  |  |  |  |  |
| 08 | Veld/Forest Fires |  |  |  |  |  |
| 09 | House Fires |  |  |  |  |  |
| 10 | Severe Storms (Heavy Rainfall) |  |  |  |  |  |
| 11 | Severe Storms (Floods) |  |  |  |  |  |
| 12 | Severe Storms (Wind) |  |  |  |  |  |
| 13 | Severe Storms (Lightning) |  |  |  |  |  |
| 14 | Severe Storms (Hail) |  |  |  |  |  |
| 15 | Extremely High Temperatures |  |  |  |  |  |
| 16 | Soil Erosion |  |  |  |  |  |
| 17 | Lack of Sanitation |  |  |  |  |  |
| 18 | Lack of Water |  |  |  |  |  |
| 19 | Lack of Proper Road Infrastructure |  |  |  |  |  |
| 20 | Civil Unrest - Crime |  |  |  |  |  |
| 21 | Water Pollution |  |  |  |  |  |
| 22 | Stock theft (ukwebiwakwemfuyo) |  |  |  |  |  |
| Capacity Score |  |  |  |  |  |  |

  - Disaster Risk Analysis

Table 6: Overall disaster risk in terms of hazard, vulnerability and capacity: R = (H x V)/C.

| No. | Prevalent Hazards and Threats | Mpofana Municipal Ward Numbers |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | KZ 223 Risk Score |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 01 | 02 | 03 | 04 | 05 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Very Low = 1 |  |  |  | Low = 2 |  |  |  | Medium = 3 |  |  |  | High = 4 |  |  |  | Very High = 5 |  |  |  |  |
| 01 | Road Accidents |  |  |  |  |  |
| 02 | Rail Accidents |  |  |  |  |  |
| 03 | Drought |  |  |  |  |  |
| 04 | Disease: Animal (Amatele) |  |  |  |  |  |
| 05 | Disease: Human (HIV/AIDS) |  |  |  |  |  |
| 06 | Disease: Human (Malaria) |  |  |  |  |  |
| 07 | Disease: Human (Cholera) |  |  |  |  |  |
| 08 | Veld/Forest Fires |  |  |  |  |  |
| 09 | House Fires |  |  |  |  |  |
| 10 | Severe Storms (Heavy Rainfall) |  |  |  |  |  |
| 11 | Severe Storms (Floods) |  |  |  |  |  |
| 12 | Severe Storms (Wind) |  |  |  |  |  |
| 13 | Severe Storms (Lightning) |  |  |  |  |  |
| 14 | Severe Storms (Hail) |  |  |  |  |  |
| 15 | Extremely High Temperatures |  |  |  |  |  |
| 16 | Soil Erosion |  |  |  |  |  |
| 17 | Lack of Sanitation |  |  |  |  |  |
| 18 | Lack of Water |  |  |  |  |  |
| 19 | Lack of Proper Road Infrastructure |  |  |  |  |  |
| 20 | Civil Unrest - Crime |  |  |  |  |  |
| 21 | Water Pollution |  |  |  |  |  |
| 22 | Stock theft (ukwebiwakwemfuyo) |  |  |  |  |  |
| Disaster Risk Score |  |  |  |  |  |  |

  - Priority Disaster Risk Maps

  - Discussion and Interpretation of Disaster Risk Assessment Data

- Disaster Risk Reduction

  - Alignment/Integration between the IDP and DMP

  - Alignment with the Municipal Spatial Development Framework (SFP)

- Response and Recovery

- Information Management and Communication

- Education, Training, Public Awareness and Research

- Funding Arrangement for Disaster Management

  - Service Delivery and Budget Implementation Plan (SDBIP)

- Summary and Conclusion

- Recommendations and Implementation Plan

- Bibliography

Annexures

## STAKEHOLDERS DATABASE

| STAKEHOLDERS | CONTACT PERSON | CONTACT DETAILS | EMAIL ADDRESS |
| --- | --- | --- | --- |
| - Mpofana Municipality | Sfiso Ndlovu | Tel: 033 363 1221 Cell: 071 629 3488 | sfiso.ndlovu@mpofana.gov.za |
| - SAPS MOOI RIVER 2.1 SAPS RIETVLEI | BusaniMtshali B.S Khanyile | Tel: 033 263 7600 Cell: 082 787 1837 Tel: 033 417 0712 Cell: 082 418 4346 | MtshaliBusani@saps.gov.za Rietvlei-SAPS@saps.org.za |
| - Department of Social Development | MakhosiHlalukane | Tel: 033 263 2034 Cell: 082 804 8747 | makhosihlalukane@gmail.com |
| - Department of Public Works |  |  |  |
| - Department of Agriculture | KhayelihleMendu Karen Yardley | 0823476269/76 0769412207 | khayelihle.mendu@kzndae.gov.za karen.yardley@kzndard.goc.za |
| - Department of Health | ZeblonShabangu | Tel: Cells:072 526 7333 | zeblon.shabangu@kznhealth.gov.za |
| - EMRS | Thembelihle Ndlovu Nicholas Lembethe AnsuriMahabeer | 0333304341/ 0833124761 0333921600 Tel: 0333921600 | thembelihle.ndlovu2@kznhealth.gov.za nicholas.lembethe@kznhealth.gov.za ansuri.mahabeer@kznhealth.gov.za |
| - Road Traffic Inspectorate | Paul Greyling | Tel: 033 2632862 Cell: 082 888 7232 | greypaul@telkomsa.net |
| - Fire Department | SphiweXaba | Tel: Cell:082 297 3481 | xabas@umdm.gov.za |
| - ESKOM | tiyan | Tel: Cell: 0780740364 |  |
| - Red Cross | Thabang Ngubane | Tel: 033 330 3018 Cell: 072 309 0995 | tngubane@redcross.org.za |
| - Environmental Health | BongiweNzimande | Tel: 033 897 6856 Cell: | bongiwe.nzimande@umdm.gov.za |
| - KZN Wildlife | NoziphoSibeko Ntombenhlemthethwa | Tel:0363533718 Cell:0794974222 Tel:0363533707 Cell:0843638660 | sibekon@kznwildlife.com mtethwm@kznwildlife.com |
| - Department of Education | TholaMadlala | Tel: 033 263 1058 Cell:079 385 2157 | tholaella@gmail.com |
| - Farmers Association | TonnyLeroux | Tel: 0332631513 Cell: | mrfa@lantic.net |
| - Al – Imdaad Foundation | Abed Karim | Tel: 036 352 1557 Cell: 082 587 8602 | abed@alimdaad.com CC:info@alimdaad.com |
| - Mpofana Local Municipality Ward 5 | His worship – Mayor Cllr X. Duma | Tel: Cell:0713776629 | Xolani mayor@ Mpofana.gov.za Mayorduma.kz223@gmail.com |
| - Mpofana Local Municipality ward 1 | Cllr.Z.Ismael | Tel: 035 592 0680 Cell: 0795284435 | jayceesa@gmail.com |
| - Mpofana Local Municipality | Municipal Manager Max Moyo | Tel: 033 2631221 Cell: 0828096058 | Max.moyo@mpofana.gov.za |
| - Mpofana Local Municipality ward 2 | Cllr BhekiKhumalo | Cell: 0732872947 | thendelaflyfishing@gmail.com |
| - Mpofana Local Municipality ward 3 | Cllr Qiniso Mkhize | Cell:073 620 7773 | lqmkhize@gmail.com |
| - Mpofana Local Municipality ward 4 | Cllr NowaMthalane | Cell:082 660 4000 | Mboniseni.mthalane@mpofana.gov.za |
| - SASSA | NtombikayiseDludla | Cell: 072 047 1166 | ntombikayised@sassa.gov.za |
| - HOME AFFAIRS | BonginkosiXulu Sizwe Ndlovu | Cell: 063 684 6801 Cell: 0766930865 | bonginkosi.xulu@dha.gov.za sizwe.ndlovu52@gmail.com |
| - HUMAN SETTLEMENT | BongmusaMncwabe Morris Dladla | Cell: 0823758868 | bongumusa.mncwabe@dha.gov.za morris.dladla@kzndhs.gov.za |
| 26.SAWS | SyabongaMthethwa | Cell:0845087266 | siyabonga.mthethwa@weathersa.co.za |
| - N3TC | Praveen Sunderlall | Tel: 033 263 1327 Cell:082 491 4066 | praveens@n3tc.co.za |
| - UMDM | MduduziNxumalo Mbuyiseni Zuma | Cell:083 559 4334 Tel:033 897 6700 Cell:076 411 2078 | nxumalom@umdm.gov.za Mbuyiseni.Zuma@umdm.gov.za |
| - COGTA (PDMC) | Skhumbuzo Majola Bheki Phungula | Cell: 083 864 5060 Cell: 0725128601 | Skhumbuzo.Majola@kzncogta.gov.za Bheki.Phungula@kzncogta.gov.za |
| 29.MGENI WATER | JabulaniNyawose | Tel: 033 263 2751 Cell:082 661 3565 | jabulani.nyawose@umgeni.co.za |
| 30. Water Affairs | LindiweShange | Cell: 0828705546 | ShangeL@dws.gov.za |
| 31. Catchment Management Forum (CMF) | Graham Amstrong | Tel:033 263 1404 Cell: 082 854 5746 | gcarmstrong@bundunet.com |
| 32.PASTORS ASSOCIATION | MthunziNzama | Tel: Cell:0733789681 | Bishopmsnzama.cohec@workmail.co.za |
| 33. SPORT AND RECRIATION | NondumisoSidaki | 0338979400 | Nondumiso.sidaki@kzndrs.gov.za |
| 34. ART AND CULTURE | James Khanyezi | 0828057886 | james.khanyezi@umdm.gov.za |
| 35. SPCA | Phumlani Majola | 0833850807 | mooispca@mweb.co.za |
| 36. DOT | Sandile Dladla | 0769109287 | sandile.dladla@kzntransport.gov.za |
| 37. TRADITIONAL LEADERS | INKOSI MCHUNU | 0713478586 |  |
| 38. DIRECTOR SOCIAL SEVICES | BONGIWE MCHUNU | Tel:0332637717 Cell:0828886276 | bongiwe.mchunu@mpofana.gov.za |
| 39. DIRECTOR TECHNICAL SERVICES | STEADY ZAMISA | Tel: Cell:0607950622 | Steady.zamisa@mpofana.gov.za |
| 40. DIRECTOR FINANCE | PITSO MOLEFE | Tel:0332637708 Cell:0720979337 | msimasim@icluoud.com |
| 41.DIRECTOR COOPERATE/ HR | BONGANI NGUBANE | Tel: Cell:0725706645 | Bongani.ngubane@mpofana.gov.za |
| 42. IDP MANAGER | MTSHEZI MKHIZE | TEL:0828793189 CEL:0828793198 | mtshezana@yahoo.com |
| 43. PUBLIC PARTICIPATION | THEMBA MKHASIBE | Tel:0332637812 Cell: | thembamkhasibe@yahoo.com |
| 44. OSS | SANDILE NDAWONDE | Tel:0332637747 Cell:0716318426 | sandilendawonde44@gmail.com |
| 45. YOUTH | BONGINKOSI NKOSI | Tel:0332637812 Cell:0719717719 | nkosibm@yahoo.com |
| 46. AGRI PARKS | MHLENGI STHOLE | Tel:0332632194 Cell:0764115869 | mhlengi.sithole@yahoo.com |
| 47. SOCIAL OFFICER | BUHLE MCHUNU | Tel: 033 2631221 Cell: 0825321379 | buhle.mchunu@mpofana.gov.za |
| 48.INFORMATION TECHNOLOGY | THOBANI NTULI | Tel: 033 2631221 Cell: 0716317396 | thobani.ntuli@mpofana.gov.za |
| 49.SALGA | Sihle Ndlovu | Cell: 07249855525 | sndlovu@salga.org.za |
| 50. Water and Sanitation | Duncan Fowler | Cell: 0798757602 | duncan.folwer@umdm.gov.za |

Annexure A

Mapping

PRIMARY SCHOOLS

WARD BOUNDARIES

LOCATION WITHIN SOUTH AFRICA

LOCATION WITHIN KZN

AGRICULTURAL POTENTIAL

ECONOMIC NODES AND CORRIDORS

LAND DESIGNATIONS

LAND COVER

LAND OWNERSHIP

CRITICAL BIODIVERSITY

ENVIROMENTAL SENSITIVITY

GENERAL LAY OUT OF UMNGENI AND MOOI RIVER

Ground water potential of Umngeni and Mooi River

Proposed water resource infrastructures in Mooi river /umngeni

HOUSE-HOLD DISTRIBUTION

SETTLEMENTS

ROAD NETWORK

CLINICS